## Slide 1: DG3 gate 5: college readiness
REVIEW AND DISCUSSION
ctcLink Steering Committee
February 11, 2020

## Slide 2
CTCLINK QUALITY GATES & MILESTONES

## Slide 3: DG3 readiness ASSESSMENT development
KEY ELEMENTS OF QUALITY COLLEGE READINESS ASSESSMENT
Accuracy: true measurement of go-live readiness
Consistency: one tracking tool
Identification of Gaps (for college-specific items)
Establishment of Mitigation Plans
Collaborative Process: Involvement/Assessment by DG3 PMs, ctcLink & SBCTC teams
Transparency: Report Readiness to all levels of ctcLink Governance
Dec 2019-
Jan 2020
Jan 2020
Jan 2020
Feb. 7, 2020
College readiness spreadsheet developed by ctcLink PMO team
Reviewed by: ctcLink Team; DG3 PMs, Exec Sponsors, college project team, SMEs; Quality Assurance (Moran & OCIO)
Feedback incorporated and spreadsheet updated
DG3 PMs complete preliminary readiness spreadsheet, submit to Project Management Office
ctcLink Steering Committee review, discussion
Feb. 11, 2020
Feb. 18, 2020

## Slide 4: DG3 College readiness SUMMARY
 | COLLEGE | DATA |  | SECURITY |  | TESTING |  | SUPPORT PLAN |  | TRANSITION |  | COMMS & OCM | 
 | Cascadia College | Green | 2 of 3 | Red | 0 of 2 | Orange | 1 of 6 | Orange | Complete | Orange | 1 of 4 | Yellow | 4 of 6
 | Lower Columbia College | Green | 2 of 3 | Red | 0 of 2 | Orange | 1 of 6 | Green | 3 of 4 | Orange | 0 of 4 | Green | 5 of 6
 | Olympic College | Green | 2 of 3 | Yellow | 0 of 2 | Yellow | 1 of 6 | Green | Complete | Yellow | 1 of 4 | Yellow | 5 of 6
 | Peninsula College | Green | 2 of 3 | Red | 0 of 2 | Orange | 1 of 6 | Green | Complete | Orange | 0 of 4 | Yellow | 5 of 6
 | Pierce District | Yellow | 1 of 3 | Red | 0 of 2 | Orange | 0 of 6 | Orange | 2 of 4 | Orange | 1 of 4 | Orange | 2 of 6
 | RED - Critical system or organization issue, no mitigation available
 | ORANGE - System or organizational issue with workaround (mitigation plan)
 | YELLOW - Somewhat ready for Go-Live, small issues unresolved, doesn't impact Go-Live
 | GREEN - Ready for Go-Live

## Slide 5: Cascadia COLLEGE
College Overview | Completion | Status | Go/No-Go Status
Data | 2 of 3 |  | Green
Security | 0 of 2 |  | Red
Testing | 1 of 6 |  | Orange
Training | 1 of 4 |  | Orange
College Support Plan | 4 of 4 | Complete | Orange
Transition | 1 of 4 |  | Orange
Comms & OCM | 4 of 6 |  | Yellow
Comments and Mitigation, refer to slide #6.
 | RED - Critical system or organization issue, no mitigation available
 | ORANGE - System or organizational issue with workaround (mitigation plan)
 | YELLOW - Somewhat ready for Go-Live, small issues unresolved, doesn't impact Go-Live
 | GREEN - Ready for Go-Live

## Slide 6
CASCADIA | Comments | Mitigation Plan
Data: | Pillars are comfortable with the quality of their data for both cleanup and data validation cycle 4. | Known data cleanup issues will be addressed after Go-Live. Data validation OTM issues submitted, waiting for resolution. Finance budget depts and KK updated needing validation in cycle 5.
Security: | Employee security mapping as completed as possible w/out SACR and User Preferences. Have not received final security workbook, access to SVX, or training on security management. | Need security management training and minimum two to three weeks in SVX to input and then test employee security before quality end-user training can begin.
Testing: | UAT is overall 59% complete and continues to be delayed by system and security issues. Unlikely to complete UAT by Feb 14th. Sprint 1 = 91%, Sprint 2 = 51%, Sprint 3 = 55%, Sprint 4 = 9%. Payroll testing complete but with issues to resolve before payroll will work. FA testing is 50% complete and blocked due to system issues. SF testing is scheduled for Feb 10-21. | Continue focus on testing to complete, if possible, by Feb 14.
Training | SVX training environment and security for employee business process access in SVX is not available to train employees. Department training plans are complete and prioritized by critical core functions for 30-days post Go-Live. Canvas courses not completed, awaiting release of SVX in order to apply knowledge in PS simultaneous to learning the process in Canvas. | SBCTC provided in-person training requested. Training effort will begin when SVX is available. Desktop procedures will be QRG's and training material until business process procedures are drafted while training in SVX.
College Support Plan: | We don't know what we don't know. Expecting more fidelity from SBCTC on Tier 1 Help Desk expectations, ticket escalation process and security management training. | Draft plans for Local Help Desk, security assignment and escalation plans are in place. Security team is established and practiced during UAT, awaiting SVX security management training before turning green.
Transition: | Conversion weekend plans initiated but on-hold pending receipt of information from SBCTC for cut-off dates and cutover weekend schedule. dataLink connection established but unable to validate supplemental systems due to limited data available. Pillar data validators identified. | Departments identified potential shutdown activities. Initiated mitigation plans which will be verified after receipt of shut-down activities from SBCTC. Checklist for local changes discussed pending final review after receipt of Local Tier 1 Help Desk requirements.
Comms & OCM: | Communications plan is complete and being communicated. Crisis Plan complete and nested with SBCTC's plan. Website is being updated on schedule, OCM adoption ongoing, hindered by system and schedule delays. OCM sustainability plan projected and will be modified post Go-Live. | All activities will continue through Go-Live and system stabilization. Website update initiated. Standing policy review complete, new policy in development. OCM sustainability to be evaluated post Go-Live.

## Slide 7: Lower columbia COLLEGE
College Overview | Completion | Status | Go/No-Go Status
Data | 2 of 3 |  | Green
Security | 0 of 2 |  | Red
Testing | 1 of 6 |  | Orange
Training | 2 of 4 |  | Yellow
College Support Plan | 3 of 4 | Complete | Green
Transition | 0 of 4 |  | Orange
Comms & OCM | 5 of 6 |  | Green
Comments and Mitigation, refer to slide #8.
 | RED - Critical system or organization issue, no mitigation available
 | ORANGE - System or organizational issue with workaround (mitigation plan)
 | YELLOW - Somewhat ready for Go-Live, small issues unresolved, doesn't impact Go-Live
 | GREEN - Ready for Go-Live

## Slide 8
LCC | Comments | Mitigation Plan
Data: | All data validation for cycle 4 is complete, issues have been identified and submitted in OTM. Issue tickets are pending resolution. | Need resolution on OTM tickets submitted during cycle 4 data validation. Need access to validate data following each of the conversion phases (1-3). SBCTC provide assistance in making a plan of action for resolving issues that arise in cycle 5.
Security: | Updates to security workbook by SBCTC needed before security mapping can be completed. Have not received access to SVX environment to test roles or training for local security administrators. The ctcLink Reference Center materials are extremely helpful, but additional support is needed to complete Security Mapping Matrix. (See Mitigation Plan) | Need Q&A/ work sessions by pillar while Security Mapping Matrix is being completed. Require minimum of three full weeks in the SVX environment with ability to quickly adjust security roles, in order to be ready for go live.
Testing: | UAT is overall 71% complete- Sprint 1 92% complete, Sprint 2 92% complete, Sprint 3 62% complete, Sprint 4 35% complete. Due to a combination of security issues and functionality within environments, SME's do not feel confident in many of the processes they have tested. Testing has been disjointed due to many starts and stops within processes to address security access, lack of access to required configurations within environments (specifically switching from UAX to UAT) and wait time for functional analysts to assist. Canvas training courses and QRG's were not enough to support testing. Student financials parallel testing will begin on 2/10, leaving only 4 days to assess any issues or concerns before the readiness assessment is due. | Continue to focus on UAT to complete by February 14.
Training: | Training plan is complete, although there are gaps in information provided by the Canvas training courses. Self-Paced Canvas courses for Advisors, Faculty, Employees, Managers and Students have been released. Over 40 SME's have been engaged in Self-Paced Canvas courses since early November. End users do not have access to a training environment to apply knowledge from Canvas courses. Business process fit gap sessions were successful at preparing SME's to complete configuration assignments. Not enough information provided early on in the project to assess all business process and create business process guides/desktop procedures. | In person (or via WebEx) training for SME's staff provided by SBCTC per email request, prior to go-live. Would love to be able to check Canvas course progress for individual institutions (we understand this is in progress). Desktop procedures will be QRG's and Canvas training course material. We will continue to refine business processes and develop desktop procedures post go-live.
College Support Plan: | Security administrators have been identified and are awaiting training. | 
Transition: | Limited access to data in dataLink. We needed access to data in dataLink in November to sufficiently validate supplemental systems. This is a risk, and will likely cause a delay in having supplemental systems running for an undetermined amount of time post-go live. No replacement reports have been developed for ByRequest. Information about QARS Reporting has been unavailable. Cutover plan is under development. Information needed from Legacy team on specific shutdown procedures to complete the week of 3/2. Go-live weekend plan, including list of validators is in progress. Check-list for local changes in progress. | Once planning resources from SBCTC received we can finalize local plan.
Comms & OCM: | Work in this category will not be complete until we are live (especially web content and links). Policy and procedure updates are in process. | All activities noted here will continue through and beyond go live. GPA calculation and Academic Standing policy revisions are in process and should be complete by go live.

## Slide 9: OLYMPIC COLLEGE
College Overview | Completion | Status | Go/No-Go Status
Data | 2 of 3 |  | Green
Security | 0 of 2 |  | Yellow
Testing | 1 of 6 |  | Yellow
Training | 1 of 4 |  | Yellow
College Support Plan | 4 of 4 | Complete | Green
Transition | 1 of 4 |  | Yellow
Comms & OCM | 5 of 6 |  | Yellow
Comments and Mitigation, refer to slide #10.
 | RED - Critical system or organization issue, no mitigation available
 | ORANGE - System or organizational issue with workaround (mitigation plan)
 | YELLOW - Somewhat ready for Go-Live, small issues unresolved, doesn't impact Go-Live
 | GREEN - Ready for Go-Live

## Slide 10
OLYMPIC | Comments | Mitigation Plan
Data: | Completed Cycle 4, OTM tickets created. Data Quality has improved with each cycle. | Some open OTM tickets.
Security: | Nominal and Administrative end users defined. Stakeholder Analysis complete. | Require three full weeks in the SVX environment with ability to quickly adjust security roles, in order to be ready for go live.
Testing: | UAT behind schedule. | Plan to complete UAT by Feb 14. Campus wide push, using reduced services on Fridays to allow time for SMEs to test. Applying considerable overtime.
Training | Training plan for SMEs and nominal users complete. Stakeholder Analysis complete. Over 100 SMEs have been engaged in Self-Paced Canvas Courses since early November. Self-Paced Canvas courses for Employee, Manager and Students have been released. 50 local process maps have been created for College specific ctcLink business processes. Desktop procedures have been developed in specific areas where needed. | Training efforts will continue through go live. Development of local business process maps and desktop procedures will continue though, and after, go live.
College Support Plan: | Cutover Planning Team has completed support plans, including escalation process, for the several week period after go live and for the period after the system is stable. Resources have been assigned, training in process. Security Administrators have been assigned and are awaiting training. | 
Transition: | Cutover Planning Team has completed Preparing for Go Live and Week of Go Live planning. supplemental systems Team has completed analysis, surviving systems that will need data from new data store have been identified. Production activities are being monitored weekly. Sunday validators are being identified. | Anticipate completing all listed activities by 2/29.
Comms & OCM: | Cutover Planning Team communications plan completed and is being executed. Director of Communications is leading communications. Website revisions are being developed to remove references to legacy and include ctcLink. OCM activities are ongoing. | All listed activities will continue through go live. Can move to green when web revisions are complete.

## Slide 11: PENINSULA COLLEGE
College Overview | Completion | Status | Go/No-Go Status
Data | 2 of 3 |  | Green
Security | 0 of 2 |  | Red
Testing | 1 of 6 |  | Orange
Training | 1 of 4 |  | Red
College Support Plan | 4 of 4 | Complete | Green
Transition | 0 of 4 |  | Orange
Comms & OCM | 5 of 6 |  | Yellow
Comments and Mitigation, refer to slide #12.
 | RED - Critical system or organization issue, no mitigation available
 | ORANGE - System or organizational issue with workaround (mitigation plan)
 | YELLOW - Somewhat ready for Go-Live, small issues unresolved, doesn't impact Go-Live
 | GREEN - Ready for Go-Live

## Slide 12
PENINSULA | Comments | Mitigation Plan
Data: | Cycle 4 was our most successful validation, still following up on some items. | 
Security: | Have not received final security workbook, no access/training in SVX for security | Security leads need training in SVX environment. Three to four full weeks required to successfully setup and review security prior to go-live.
Testing: | Due to lack of security in multiple testing environments UAT has been behind since week 1. SME's have struggled to maintain a steady testing pace due to having to submit tickets for access on the majority of tests. | SME's continue to work to complete UAT's by extended deadline.
Training: | End users do not have a training environment, canvas courses being reviewed but not able to practice lessons. Canvas courses do not cover all areas, additional trainings being planned when we receive access. | Once environment received we will start more in depth training. This activity is dependent on when security setup is complete. Peninsula plans on creating desktop procedures post go-live.
College Support Plan: |  | 
Transition: | Local go-live weekend planned, no access to dataLink but plan in place for supplemental systems once access received. | Once planning resources from SBCTC received we can finalize local plan.
Comms & OCM: | Policy and procedure updates ongoing, we plan to update procedures post go-live. Communications/web team plan is complete and planning cutover timeline. | Continue to plan to work on procedures post go-live.

## Slide 13: pierce COLLEGE district
College Overview | Completion | Status | Go/No-Go Status
Data | 1 of 3 |  | Yellow
Security | 0 of 2 |  | Red
Testing | 0 of 6 |  | Orange
Training | 1 of 4 |  | Orange
College Support Plan | 2 of 4 | Complete | Orange
Transition | 1 of 4 |  | Orange
Comms & OCM | 2 of 6 |  | Orange
Comments and Mitigation, refer to slide #14.
 | RED - Critical system or organization issue, no mitigation available
 | ORANGE - System or organizational issue with workaround (mitigation plan)
 | YELLOW - Somewhat ready for Go-Live, small issues unresolved, doesn't impact Go-Live
 | GREEN - Ready for Go-Live

## Slide 14
PIERCE | Comments | Mitigation Plan
Data: | Data clean up for CS, FA, HCM & SF is complete - all critical errors corrected. FIN data clean up is incomplete due to recent earnings distribution errors -- estimated 60% errors. Data validation for Cycle 4 is complete. FIN has 10 outstanding OTM tickets. | Anticipate some HCM clean-up or modifications after GoLive. FIN OTM tickets pending resolution.
Security: | Have not received our final security matrix workbbook. No access to SVX environment to test roles. No training for local security administrators. Additional resources and/or support is needed from SBCTC to complete Security Matrix Mapping. | Accurate security roles for ALL employees is critical. Hands-on working sessions with SBCTC project staff is critical while completing Security Matrix Mapping workbook. Require minimum of three full weeks in the SVX environment with ability to quickly adjust security roles, in order to be ready for GoLive.
Testing: | UAT is behind schedule due to a combination of security role issues and availability/functionality of testing environments. Sprint 1 - 91% complete, Sprint 2 - 63% complete, Sprint 3 - 55%, Sprint 4 - 32% complete. Canvas training courses and QRG's were not enough to support testing. HCM working through Payroll to GL critical issues due to coding. FIN critical issues logged for Sprint 4. Payroll testing: HCM in progress, FIN no Payroll to GL. FA Dual Processing: FA in process, FIN no FA to GL. SF Parallel testing: SF in process, FIN no SF to GL. | SMEs are working to complete UAT by February 14th deadline.
Training | Canvas training courses have been rolled out to the college community. There are ongoing challenges with the self-enrollment process and gaps in the information provided in the Canvas courses. End users do not have access to a training environment to apply knowledge gained from Canvas courses. Desktop procedures in process. | Continue developing desktop procedures. Continue Canvas courses. Critical need for hands-on training provided by SBCTC prior to GoLive. Training for local IT Help Desk support is critical.
College Support Plan: | Training and information from SBCTC has not been provided regarding Help Desk support. Contingency Planning and discussions around security role assignment/administration are in process. | Continue developing security role assignment process. Detailed information and/or plan from SBCTC for local IT Help Desk support and responsibilities is critical.
Transition: | Have identified dates for process cut offs. FA in process to clean and reconcile accounts with FAM end dates for processing. FIN waiting to hear when SBCTC is running February EOM. Contingency plans developed for system and/or module failure. Recently received access to dataLink - delay in ability to validate and integrate supplemental systems. GoLive weekend plan and list of validators in process. Discussed and identified some local changes during contingency planning session. | Continue development of GoLive weekend plan, identify weekend validators, develop checklist for local changes.
Comms & OCM: | Policy and procedure updates are ongoing. Website and resource tool updates are ongoing. OCM adoption is ongoing - staff training, Q&A sessions, Canvas courses, etc. | Continue with staff training sessions, opportunity to support changes, address pressure points. All areas of assessment listed will continue up to and beyond implementation of ctcLink (PeopleSoft).

## Slide 15: Ctclink project readiness & Concerns
Discussion led by Christy Campbell, ctcLink Project Director
Activities | Risk /Concerns | Target Completion Date
Student Financials | Student Financials data and flow to General Ledger is still being validated by the project team and has not been tested by the colleges. | Project team complete Sunday, Feb. 16. College validation by Friday, Feb. 28. *Risks and solutions are known based on Clark’s deployment.
Security | Colleges have not had an opportunity to validate assignments of their users in the system. | Complete by Monday, March 2.
UAT / Parallel Testing | Testing has not been completed. | College validation by Friday, Feb. 28
Mock Run Cycle 5 | Project team needs to test the cutover plan to ensure a consistent process at go-live. | Feb. 25-27
Historical Class Load | This activity will be required if more than 2-3 colleges go-live. | Based on Steering Committee Decision
Training | Local college training has been limited due to the dependencies on system training. | All college SMEs should be trained in critical areas by Thursday, March 5 and ongoing training post go-live as desired.
Support Organization | Staffing levels to support six new colleges has not been complete. | Alignment initiated Feb. 10. Additional staffing and contract staff needs to be implemented.

## Slide 16: ctclink & College readiness SUMMARY
 | COLLEGE | DATA |  | SECURITY |  | TESTING |  | SUPPORT PLAN |  | TRANSITION |  | COMMS & OCM | 
 | Cascadia College | Green | 2 of 3 | Red | 0 of 2 | Orange | 1 of 6 | Orange | Complete | Orange | 1 of 4 | Yellow | 4 of 6
 | Lower Columbia College | Green | 2 of 3 | Red | 0 of 2 | Orange | 1 of 6 | Green | 3 of 4 | Orange | 0 of 4 | Green | 5 of 6
 | Olympic College | Green | 2 of 3 | Yellow | 0 of 2 | Yellow | 1 of 6 | Green | Complete | Yellow | 1 of 4 | Yellow | 5 of 6
 | Peninsula College | Green | 2 of 3 | Red | 0 of 2 | Orange | 1 of 6 | Green | Complete | Orange | 0 of 4 | Yellow | 5 of 6
 | Pierce District | Yellow | 1 of 3 | Red | 0 of 2 | Orange | 0 of 6 | Orange | 2 of 4 | Orange | 1 of 4 | Orange | 2 of 6
 | ctcLink Project Team ALL DG3 Colleges (based on cutover date: 3/6/2020) |  |  |  |  |  |  |  |  |  |  |  | 
 | ctcLink Project Team 1-3 Colleges (based on cutover date: 3/6/2020) |  |  |  |  |  |  |  |  |  |  |  | 
 | RED - Critical system or organization issue, no mitigation available
 | ORANGE - System or organizational issue with workaround (mitigation plan)
 | YELLOW - Somewhat ready for Go-Live, small issues unresolved, doesn't impact Go-Live
 | GREEN - Ready for Go-Live

## Slide 17: Assumptions
One to three colleges elect to keep to the current schedule.
All other colleges have the ability to achieve readiness for an April or May deployment.
Colleges understand the amount of work required to convert in a new term.
    Financial Aid Dual Processing (additional year of Dual Processing)
    Schedule of Classes (Summer and Fall Term Build)
    Faculty Workload (Assign Instructors for Summer & Fall Term)

## Slide 21: Deployment group risks/impacts
Go-Live Timeframe | Deployment Group 4 | Deployment Group 5 | Deployment Group 6
Any date in May 2020 (or earlier) | Realign some activities for DG4 Cycle 2 Impact to DG4 Go-Live Date (2 months) | Delay DG5 kickoff until Late May 2020 This moves DG5 BPFG after Fiscal Year-End which is a benefit to colleges No impact to DG5 Go-Live Date | DG6 timeline may be adjusted, but not significant delay
Any date after May 2020 | Extensive rescheduling of DG4 activities Delays and resource constraints during critical DG4 activities Impact to DG4 Go-Live Date (6-8 months) | Extensive rescheduling of DG5 activities Delays and resource constraints during critical DG5 activities Impact to DG5 Go-Live Date | DG6 timeline will be delayed significantly due to extensive realignments in former deployments

## Slide 22: College go-live preference
Go-Live Date Preference | March 9 | April 27 | May 11 | May 27
Cascadia |  | X |  | 
Lower Columbia | X |  |  | 
Olympic | X |  |  | 
Peninsula (Will report by 2/12/2020) |  |  |  | 
Pierce |  |  | X | 

## Slide 23: Steering Committee Motions & Recommendations
Approve 1, 2 or 3 colleges deploying on March 9, 2020.
Identify and approve new deployment date for remaining DG3 colleges.

## Slide 24: MEETING CLOSURE