## Slide 1: ctcLink Steering Committee
September 10, 2019
Choi Halladay - ctcLink Steering Committee Chair, Vice President for Administrative Services, Pierce College District
Christy Campbell – ctcLink Project Director

## Slide 2: agenda
Item | Description | Minutes | Facilitator
1 | Welcome | 1 | Christy
2 | Approval of Minutes | 3 | Choi
3 | Chart of Accounts Update | 10 | CCS, TCC, SBCTC
4 | Budget Planning Requirements – Discussion and Approval | 10 | Christy
5 | DG4 Initiation Phase Peer Review Results and Gate 1 Recommendation | 10 | Reuth Kim
6 | Go-Live Dates Discussion and Approval Deployment Group 3 Deployment Group 4 | 20 | Christy/Eli
7 | Deployment Readiness Documents Deployment Readiness Checklist Organizational Go/No-Go Recommendation Sign-off | 20 | Reuth/Christy
8 | Guided Pathways Workshop Update Facilitator Update New Requirements / Next Steps | 20 | Ligia/Christy
9 | ctcLink Governance Decision Options Template | 10 | Christy
10 | ctcLink Program Status Program Risk Implementation Colleges Pre-Implementation Colleges | 20 | Christy
11 | Remediation: Replacement Solutions Update Security Mapping Accessibility Testing Update Campus CE Negotiations OAA Next Steps Budget Planning Tool | 20 | Christy/Others
12 | Action Items Review and Agenda Items for Future Meetings | 5 | All
13 | Meeting Closure | 1 | Christy

## Slide 3: Meeting Minutes – Approval
August 13, 2019

## Slide 4: Chart of accounts UPDATE
Status Update
  Tacoma Community College
  Community Colleges of Spokane
  SBCTC

## Slide 5: Budget planning requirements
Steering Committee approval
  See Budget Requirements Spreadsheet for Detail

## Slide 6: Budget planning tool Work Group
Activities | Clark | Tacoma | RTC | Peninsula | Clover Park | SBCTC | Pierce | Yakima | Bellevue | Highline | Spokane
Work Group Participant (Volunteer) | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Budget Requirements Review and Feedback | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | No | No | No
Participate in Review Session #1 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No
Participate in Review Session #2 | Yes | Yes | Yes | No | Yes | Yes | No | Yes | Yes | No | Yes
Finalize and Recommend Approval of Requirements | Yes | Yes | Yes | N/A | Yes | N/A | N/A | Audit | Audit | Audit | Audit* Feedback will be provided)

## Slide 7: Budget planning tool Work Group Next Steps
Steering Committee approval – September 2019
Oracle/Mythics - September
  Send final and approved requirements
  Build Prototype PBCS  Planning and Budgeting Cloud Service  based on: (1.) Requirements, and (2.) Sample organizations based on prior templates for Pierce, Peninsula, Spokane, and SBCTC
  Present prototype to Budget Planning Work Group
Budget Planning Tool Work Group – September
  Recommend PBCS or RFP to ctcLink Governance

## Slide 8: Dg4 initiation phase peer review and gate 1 recommendation
  See DG4 Peer Review slide deck

## Slide 9: Dg3 proposed deployment date
March 9, 2020

## Slide 10: DG3 HIGH-LEVEL TIMELINE DRAFT
2018
2020
Today
Dec
Feb
Apr
Jun
Aug
Oct
Dec
Feb
2018
2019
2020
DG3 Kickoff
Jan 28
Legacy Snapshot #1
Feb 22
Legacy Snapshot #2
Apr 26
Legacy Snapshot #3
Jun 19
Legacy Snapshot #4
Nov 8
Legacy Snapshot #5
Feb 20
Go No-go Decision
Feb 18
Deployment
Mar 9
20 days
Jan 28 - Feb 22
GDA
61 days
Feb 13 - May 8
BPFG
13 days
Feb 5 - Feb 21
57 days
Feb 5 - Apr 24
Conversion #1
12 days
Apr 9 - Apr 24
DV
60 days
Apr 10 - Jul 2
Conversion #2
12 days
Apr 10 - Apr 25
LDC
15 days
Jun 12 - Jul 2
DV
72 days
Jun 3 - Sep 10
Conversion #3
12 days
Jun 3 - Jun 18
LDC
16 days
Aug 20 - Sep 10
DV
65 days
Oct 31 - Jan 29
Conversion #4
14 days
Oct 31 - Nov 19
LDC
16 days
Jan 8 - Jan 29
DV
10 days
Feb 17 - Feb 28
Conversion #5
93 days
Mar 22 - Jul 30
Functional Test
41 days
Aug 29 - Oct 24
SIT
64 days
Nov 12 - Feb 7
UAT
9 days
Nov 12 - Nov 22
15 days
Dec 2 - Dec 20
10 days
Jan 6 - Jan 17
10 days
Jan 27 - Feb 7
56 days
Dec 6 - Feb 21
End User Training
LEGEND
LDC Legacy Data Cleanup
DV Data Validation
S# User Acceptance Testing Sprint #
LDC
S2
S3
S4
S1

## Slide 11: Dg4 proposed deployment date
February 1, 2021

## Slide 12: DG4 HIGH-LEVEL TIMELINE DRAFT
2019
2021
Today
Sep
Nov
Jan
Mar
May
Jul
Sep
Nov
Jan
2019
2020
2021
DG4 Kickoff
Oct 14
Legacy Snapshot #1
Jan 13
Legacy Snapshot #2
Mar 18
Legacy Snapshot #3
Jun 5
Legacy Snapshot #4
Aug 28
Legacy Snapshot #5
Jan 11
Go No-go Decision
Jan 5
Deployment
Feb 1
40 days
Oct 15 - Dec 9
GDA
60 days
Dec 2 - Feb 21
BPFG
57 days
Jan 2 - Mar 20
Conversion #1
8 days
Jan 2 - Jan 13
LDC
11 days
Mar 6 - Mar 20
DV
63 days
Mar 4 - May 29
Conversion #2
11 days
Mar 4 - Mar 18
LDC
11 days
May 15 - May 29
DV
76 days
May 22 - Sep 4
Conversion #3
11 days
May 22 - Jun 5
LDC
11 days
Aug 21 - Sep 4
DV
61 days
Aug 14 - Nov 6
Conversion #4
11 days
Aug 14 - Aug 28
LDC
11 days
Oct 23 - Nov 6
DV
5 days
Jan 11 - Jan 15
Conversion #5
51 days
Feb 28 - May 8
Functional Test
51 days
May 15 - Jul 24
SIT
11 days
May 15 - May 29
Prep
11 days
Aug 24 - Sep 7
S1
66 days
Aug 24 - Nov 23
UAT
11 days
Sep 21 - Oct 5
S2
16 days
Oct 12 - Nov 2
S3
11 days
Nov 9 - Nov 23
S4
46 days
Nov 13 - Jan 15
End User Training
LEGEND
LDC Legacy Data Cleanup
DV Data Validation
S# User Acceptance Testing Sprint #

## Slide 13: Deployment readiness documents
Deployment Readiness Checklist
Organizational Go/No Go Recommendation Sign-off

## Slide 14: Guided pathways workshop update
Update – Ligia
Packaging of Guided Pathways Requirements
  cELC
    Package 1 = PeopleSoft System Not Met (Pre-workshop evaluation)
    Package 2 = PeopleSoft System Not Met (System Wide workshop decision)
  Steering Committee
    Package 3 = PeopleSoft System Partially Met (Need Changes to ctcLink Configuration or Customizations)
    Package 4 = PeopleSoft System Met (ctcLink currently Configured or Customized per requirement)

## Slide 15: ctcLink governance framework

## Slide 16: ctcLink Scope Management Process
Requirement Requests/Analysis
Working Group
Steering Committee
As detailed in the ctcLink Governance Charters, ctcLink requirements can be requested by the following channels: ctcLink Executive Sponsor(s), Commissions Chairs, Data Governance Co-Chairs, ERP Leaders, CPW Facilitators, External Mandates
Executive Leadership Committee
Escalates new, removed and/or changed requirements from the Steering Committee to be evaluated for approval
The SBCTC ERP and Project Team(s) analyze new requirements to understand impacts to the system, processes and level of work to implement the new or changed requirement.
Evaluates the new, changed or removed requirement to understand the impact and level of effort to implement the request
If there is a change to the budget or timeline the request will need to be escalated to the ctcLink Steering Committee for decision
Escalates new, removed and/or changed requirements from the Working Group to be evaluated for approval
Any requests that impact the ctcLink overall timeline or impact the approved overall budget will need to be escalated to the ctcLink Executive Leadership Committee
The ctcLink Scope Management Process includes management, monitoring and control of the following:
New Requirements
Change to Existing Requirements
Removal of Requirements

## Slide 17: Ctclink governance Decision Template
Option# | Description | Advantages (e.g. time, cost, reduce risk) | Disadvantages (e.g. impacts, risks, issues, cost) | In Budget Yes/No | In Scope Yes/No | Timeline Changes Yes/No | Recommend
1 | Describe proposed change |  |  |  |  |  | 
2 | Describe proposed change |  |  |  |  |  | 
3 | Describe proposed change |  |  |  |  |  | 
Problem Statement < describe >
Steering Committee discussion
Select preferred option
Vote to recommend/approve or decline

## Slide 18: Ctclink program status
Program Risk
Implementation Colleges
Pre-Implementation Colleges

## Slide 19
Top Risks Reported – as of August 30, 2019
Top Issues Reported – as of August 30, 2019
LEGEND: Critical High Moderate Low
C
H
L
M
LEGEND: High Moderate Low
H
L
M
Risk Level | Risk Description | Mitigating Actions | Submitted by (name, org/college), Deployment Group & Date | Risk Owner (s)
H | Chart of Accounts (CoA): User adoption and successful deployment (scheduled for July 1, 2019) is critical for Deployment Group 2 (DG2) timeline. | Update: Phase 1-Phase 3 completed. Solutions for long-term accounts receivable solution deployed in early August. Long-term General Ledger solution and rule/cross-walk updates for FY19 close to Production is slated to deploy end of August. | Emmett Folk, ctcLink PM for FIN & HCM Team DG2 Impacted, Risk Date:10/12/2018 *also Risk submitted by Matt Connelly, Spokane District PM on 10/23/2018 | Emmett Folk
H | Clark: SF, FA, FIN , GL – Clark submitted these risks. | Update: Items related to Student Financials, Financial Aid, General Ledger and coordination between Student Financials and Finance. Follow-up to be scheduled with Clark’s PM after Cycle 4B validation to better understanding what is outstanding. | Susan Maxwell, Clark College PM DG2 Impacted, Risk Date: 2/1/2019 Risks #50, #51, #52, #58 | John Henry Whatley, Emmett Folk, Chandan Goel
H | ctcLink Team: The GL & SF Conversion logic/requirements for the Go-Live term has still not been finalized. If not addressed soon, it creates a risk of being unavailable for college validation and meeting Cycle 4B and future cycles. | Update: Finance and Student Financials team continues to meet to discuss AR (Accounts Receivable) items and alignment in data conversion activities and processes. | John Henry Whatley DG2 Impacted, Risk Date: 7/8/2019 Risk #71 | John Henry Whatley, Christyanna Dawson
Issue Level | Issue Description | Status Update | Submitted by (name, org/college), Deployment Group & Date | Issue Owner (s)
H | Security Mapping activities to mitigate UAT timeline have not addressed the new Security Design Production user access. | Update: The ctcLink team is highly concerned about the Production Security Mapping for DG2 Colleges and entering new Security into the UAT cycles. SBCTC – Security mapping is not complete and doesn’t reflect roles/job. SBCTC SMEs are working with FIN/HCM leads to test security for specific modules/roles that are ready. | ctcLink PMO submitted for ctcLink CS, HCM, FIN Team DG2 Impacted, Issue Date: 4/16/2019 *also issue #37 submitted by Evelyn Williams, SBCTC on 6/26/19. | Tara Keen, Security Team
M | Clark – Accessibility items | Clark has submitted issues around accessibility items they have identified. We are tracking these items and have provided this first round of information to Level Access (vendor) in early August. Phase 1 testing by Level Access is complete and results will be shared with Clark and the ctcLink Team on September 9, 2019 to begin working with Oracle to solve some of the issues. Phase 2 testing slated to begin in early September. | Susan Maxwell, Clark College PM DG2 Impacted, Issue Dates: 6/27/2019 Issues: #39-48 | Owners Assigned
19

## Slide 20: ctcLink Quality Assurance Scorecard - Moran Technology Consulting , November 2018
LEGEND | GREEN | YELLOW | RED
Risk Description: | Low risks may be encountered. NO immediate action needed | Moderate risks may be encountered. Serious deficiency and action item recommended. | High risks may be encountered. Needs to be escalated and can impact project effort or cost.
ctcLink Quality Assurance Scorecard / Moran Technology Consulting Report August 2019 | Overall Status | Y
STATUS | PROJECT AREA | DESCRIPTION / NOTES
G | SBCTC/Governance | The Go/No Go Decision for DG2 implementation is planned to be made in late September by the ctcLink Steering Committee. This decision is considered most critical to meeting the schedule for success of DG2 and impacts all remaining Deployment Groups.
G | Project Management | The PMO continues to make adjustments in staffing, and team continues working well together. PMO was preparing the Readiness Template for intended use with DG2.
Y | Phase Scope | QA continues to remain concerned that the risk created by the number of solutions to be re-implemented to replace/augment current PeopleSoft functionality. Major scope changes will impact budget, schedule, and project and support staffing. The implementation of enhanced role security for ctcLink is a major Project and QA schedule risk concern.
Y | Schedule Status | The DG2 schedule is now less than 60 days from Go-live. Pressures are mounting on the project team and the DG2 Colleges and State Board. The PMO was actively detailing multi-step plans for DG2 Go-live data conversions and production cutover. FLC colleges will be going into a production upgrade state with new functionality, while Clark and the State Board will be first time implemented with PeopleSoft.
Y | Training | Training team and consultants continue working on preparing materials for the delivery of end-user training courses scheduled for September. This scope includes a combination of Self-Paced Courses and Instructor-Led Training workshops. However, considering the workstream schedule, QA continues to be concerned that considerable content development remains for the 56 courses to support range of end-user training. The majority of the planned 36 Instructor –Led courses is Finance pillar specific and requires support from functional project staff.
Y | Testing | The last of DG2 User Acceptance Testing (UAT) Sprints (Sprint #6) is now scheduled for the 1st week of September. DG2 has been executing a large testing workstream that includes parallel testing for payroll, financial-aid, and tuition calculation.
G | Configurations / Data Conversion | Technical staff supported the DG2 cycle 4B conversion for additional data validation by Clark and SBCTC. The data conversion and production implementation of the Bio-Demo data for Clark College and SBCTC has a September 7 target date. Performance Load Testing identified technical production to ensure ctcLink system meets increased student user usage projections (20, 000 active student users).
G | Organizational Change Management | PMO/OCM is actively engaged with all colleges now involved with their Deployment Groups. ctcLink management teams continue to meet with DG colleges via on-site check-ins. With 60 days until Go-live, QA remains concerned the PMO focuses on the DG2 schedule/priority activities.
G | Project Staffing | Project staffing is adequate at this time and continues to make staffing adjustments as appropriate. PMO is recruiting for open positions. PMO to begin using off-shore technical resources to perform and augment systems integration testing work.
Y | Technical Environment | The IT division continues addressing processes and critical staffing. Additional positions supporting ctcLink production have been approved and hiring underway. The ERP Change Management Board is being re-implemented to improve coordination and scheduling of changes. Service Level Agreement is awaiting final signatures.
20

## Slide 21
Executive Summary
The project is tracking per schedule and under budget. Scope review and definition for each deployment continues due to rework of key solutions. Each Deployment Group (DG) is engaged and all colleges now have an Initiation or Implementation Work Plan: DG2 is in the Transition Phase. Colleges and SBCTC are engaged in User Acceptance Testing sprints. ctcLink will be offline for the DG2 upgrade Oct. 11-14 and again for cutover activities Oct. 25-28. (Go/No-Go decision is scheduled for the Sept. 24, 2019 Steering Committee agenda). DG3 is in the Construct Phase, focused on Conversion and Data Validation. DG3 Testing/Training road shows were held in July. DG4 is in the Initiation Phase, with all colleges well past the halfway mark on deliverables. Gate 1 Initiation Phase Peer Review was held July 29-30 at Highline College. DG4 Implementation Phase kick-off slated for Oct. 14. DG5 colleges are in the Initiation Phase and continue Initiation Deliverables status reporting. Gate 1 Initiation Phase Peer Review slated for early Dec. 2019. DG6 is in the Initiation Phase and will start public status reporting this fall. The Initiation Phase Road Show are scheduled for Oct. 2019. Planning meetings continue with technical colleges to capture differences between technical and community college business practices. Contract negotiations continue for a new Continuing Education solution. An RFI is being developed for the Online Admissions Application (OAA), in parallel with additional improvements to the current OAA solution. The Budget Planning work group has finalized business and technical requirements. Vendor (Level Access) completed phase one (1) of Accessibility testing, focusing on Student and Employee Self Service and Mobile. Phase 2 continues this month, focused on online admissions application and continuing education tools (OSECE and CampusCE).
Project Overall Status – August 19 to 30, 2019 |  |  |  |  | 
Overall | Y | Program is on track, per timeline, scope and budget Activities for DG2 are being complete just in time and issues being mitigated to meet current timeline Current DG2 Schedule has no “float” remaining in timeline | Scope | Y | Requirements Traceability Matrix (RTM) needs to be updated to validate original RFP requirements have been implemented, tested, and end-users trained on the processes and functionality
Schedule | Y | Monitoring scope and timing of: Budgeting Tool, Continuing Education, Online Admissions Application, and OBIA implementations | Budget | G | Currently tracking under budget Allotment for Gate 4 funding has been partially approved Additional request for remaining Gate 4 funding will be submitted in late September.
Overall Status Summary per Deployment Group |  |  |  | 
DG# | PMO- Reported Status | Comments | College/ Agency | Self-Reported Status
DG2 | Y | Security Production Mapping is behind Cutover planning is being finalized Readiness criteria is being socialized | Clark | G
 |  |  | SBCTC | R
 |  |  | Spokane | R
 |  |  | Tacoma | G
DG3 | G | College Configuration in progress Conversion cycles have begun | Cascadia | G
 |  |  | LCC | G
 |  |  | Olympic | G
 |  |  | Peninsula | G
 |  |  | Pierce | G
DG4 | G | College teams working on Initiation Phase activities | Implementation begins Nov. 2019 | 
DG5 | G | College teams working on Initiation Phase activities | Implementation begins March 2020 | 
DG6 | G | College teams working on Initiation Phase activities | Implementation begins Nov 2020 | 
21

## Slide 22
DG4 Initiation Phase Completion Summary | 
 | Percentage of deliverables completed and tracked in Project Web App (PWA) by each college: College Orientation & Resourcing College Project Planning (from templates) Conduct Initial Data Cleansing Document Current Legacy Business Processes Supplemental Systems Analysis
Deployment Group 4 Dashboard Reports – August 19 to 30, 2019
DG4 General Timeline Draft |  | G
College/District | As of Aug. 30, 2019
Centralia College | 70%
Edmonds Community College | 60%
Highline College | 64%
Seattle Colleges (3) | 59%
Wenatchee Valley College | 68%

## Slide 23
DG5 Initiation Phase Completion Summary | 
 | Percentage of deliverables completed and tracked in Project Web App (PWA) by each college: College Orientation & Resourcing College Project Planning (from templates) Conduct Initial Data Cleansing Document Current Legacy Business Processes Supplemental Systems Analysis
Deployment Group 5 Dashboard Reports – August 19 to 30, 2019
DG5 Pre-Implementation and General Timeline |  | G
College/District | As of Aug. 30, 2019 | Target Percentage for August 2019
Bellevue College | 19% | 45%
Bellingham Technical College | 29% | 45%
Big Bend Community College | 22% | 45%
Everett Community College | 24% | 45%
Grays Harbor College | 36% | 45%
Green River College | 34% | 45%
Skagit Valley College | 34% | 45%
Whatcom Community College | 39% | 45%

## Slide 24: Replacement solutions update
Security Mapping (Security Delay Mitigation)
Accessibility Testing
Campus CE Negotiations
Online Admissions Application RFI
Budgeting Tool Next Steps

## Slide 25
Other ctcLink Project Activities – Status as of August 30, 2019
Solution | Status | RFP Publish | Solution Decision
Accessibility | Develop and published RFP, Work Group evaluated RFP Responses Final Decision on Vendors to be awarded Vendor contracts awarded Statement of Work completed Phase 1 Accessibility Testing has completed and results being evaluated (Student & Employee Self-Service and Mobile) | 5/10/2019 | Testing and Findings Prior to DG2 (October 2019)
Continuing Education | RFP was developed and approved by Governance RFP proposals were due November 15, 2018 3 Vendors responded and subgroup is evaluating solution Governance approved procurement and decision of Vendor Vendor contract being finalized for scope and cost | 10/15/2018 | Contract Draft Complete Overall Pricing in Negotiations
Online Admissions Application | Sub-Committee finalized OAA requirements Project Team performed Fit/Gap of ctcLink functionality OAA workgroup evaluated select solutions currently in use at other PeopleSoft universities and colleges OAA workgroup developing a short list of best/possible solutions to identify those solutions on 2/12/2019 RFI to understand possible solutions and costs before final decision on RFP or custom solution Continue to enhance current OAA based on requirements for RFI | TBD | RFI requested Current ctcLink OAA requirements being prioritized prior to continue improvements
Budget Planning Tool | Committee formed to review, finalize, approve Budgeting requirements Budget Planning Tool Work Group meetings underway to finalize requirements and vet Oracle PBCS Solution Oracle/Mythics building Prototype of PBCS Solution with templates from (Peninsula, Pierce, Spokane, and SBCTC) Work Group will recommend to ctcLink Governance if PBCS will meet requirements or if an RFP will need to be developed | TBD | Requirements pending Steering Committee Approval

## Slide 26: Action Items Review & Agenda Items for Future Meetings