## Instructions
ctcLink Deployment Group 2 Readiness Criteria
INSTRUCTIONS
(1) Select your college, agency or unit's checklist tab
(2) Review and assess readiness for Go-Live by Area (Column A). Refer to the STATUS KEY below.
(3) Insert missing components in Go-Live Criteria (Column B) in your college-specific spreadsheet ONLY
(4) Assign a SME(s) as Task Owner (Column C). This is the person leading this area/task.
(5) Assess Go/No-Go Status with red/yellow/green indicator (Column D)
(6) Insert important or relevant Comments (Column E)
(7) Spokane & Tacoma - insert and rate items in your college-specific Remediation Items tab if applicable
(8) Send spreadsheet back to ctcLink by deadline to compile in High-level Go/No-Go Status tab
GO/NO-GO OVERALL READINESS STATUS KEY
RED - Critical system or organization issue, no mitigation available | R
ORANGE - System or organizational issue with workaround (mitigation plan) | O
YELLOW - Somewhat ready for Go-Live small issues unresolved, doesn't impact Go-Live | Y
GREEN - Ready for Go-Live | G
DESCRIPTION OF GO-LIVE READINESS CRITERIA AREAS
Data - Assessment of data conversion and data validation activities. Has your college/organization completed five cycles?
Security - Assessment of security mapping activities and security tested. Has your college/organization completed the majority of these activities (mapped and validated) with the understanding that you can correct assignment of roles after Go-Live?
Testing - Review of User Acceptance Testing (UAT) issues and completion. Has your college/organization completed the majority of UAT sprints #1 - #6?
Training - Review of training schedule and registered participants for training. Has your college/organization developed an executable local training plan with desktop procedures?
Transition - Understanding the migration/cutover plan. Has your college/organization finished assessing and have a plan for managing supplemental systems that are or not part of ctcLink? Do you have a separate list of transition type of activities or changes that you are managing at the local college/organization level?
Support - Understand the SBCTC ERP/Help Desk process. Has your college/organization implemented a Help Desk that supports ctcLink? Who will be managing security at your college/organization? Do you have an escalation process in place? Has this information been communicated to all stakeholders on your campus?
Communications - Developed a communications plan for Go-Live with progress updates post Go-Live. Is the important information above laid out in a plan to provide future communication to all stakeholders in your organization?
Outstanding Items - Insert additional tems pertinent to your college/organization that need to be considered for Go-Live.

## High-level Go¦No-Go Status
ctcLink DG2 Readiness Dashboard (compiled results)
Area | Item # | Go-Live Criteria | Spokane | Tacoma | Clark | SBCTC Agency (Implementation) | ctcLink Project Team | SBCTC Production Support Team | Comments
Data | 1 | Data Clean Up | [5 empty] | N/A
| 2 | Data Validation Completed & Signed Off
Security | 1 | Security Mapping Matrix Completed
| 2 | Security PRD Roles Tested
Testing | 1 | UAT Critical Issues Resolved | [5 empty] | N/A
| 2 | UAT Completed & Signed Off | [5 empty] | N/A
| 3 | Payroll Parallel Testing | N/A |  |  |  |  | N/A
Training | 1 | End-User Training Plan
| 2 | Training Documentation / Availability
| 3 | End-User Registered for Training Courses
| 4 | Desktop Procedures | N/A |  |  |  | N/A
Transition | 1 | Migration/Cutover Plan
| 2 | Supplemental Systems | N/A |  |  |  |  | N/A
| 3 | Check-List for Local Changes | N/A | N/A |  |  | N/A
Support | 1 | ERP/Help Desk Resource Plan
| 2 | Security Assignment Process
| 3 | Escalation Plan
Communications | 1 | Communications Plan Complete & Communicated
Outstanding Items |  |  | See Spokane tab | no items | See Clark tab | See SBCTC Implementation tab | See ctcLink Project tab | See SBCTC Support tab
Other |  |  | See Spokane tab | no items | See Clark tab | See SBCTC Implementation tab | See ctcLink Project tab | See SBCTC Support tab

## Spokane Checklist
Community Colleges of Spokane
Readiness
| additional items added and measured by Spokane |  | R
O
Y
G
Area | Go-Live Criteria | Task Owner | Go-No Go Status? | Comments Required for Items Below | Mitigation Plan:
Data |  |  | Go | Request SBCTC Mitigation Plans
| Data Clean Up |  |  | HCM, FA, & CS are good with data clean up
Data Validation Completed & Signed Off
Security |  |  | Not blocking CS 9.2 Upgrade | Pending SVL Readiness & supporting documents so CCS can began testing. Not blocking Go Live.
| Security Mapping Matrix Completed | SBCTC |  | Not complete, only received CS SVL Role Assignments. | Pending completion prior to CS9.2/DG2
| Security PRD Roles Tested | SBCTC |  | Pending SVL Readiness & supporting documents so CCS can began testing. Not blocking Go Live.
Testing |  |  | Go
UAT Completed & Signed Off
| UAT Critical Issues Resolved |  |  | Pending SBCTC mitigation plan
Training |  |  | Go
| End-User Training Plan |  |  | CCS communications sent out to all staff to sign up for End User Training.
| Training Documentation/Availability |  |  | Key Fluid Navigation training not available until 9/30. Risk with not being able to provide training materials to our Students and Faculty. Some Instructor Lead Trainings not adequate for colleges. | Request SBCTC Mitigation Plan?
| End-User Registered for Training Courses |  |  | In progress, SBCTC to provide weekly registration and completion reports
| Desktop Procedures |  | N/A
Transition | Successful Migration/Cutover Plan | Conversion Schools |  | As part of the cutover plan; colleges will provide resources to validate their areas are working | SBCTC to provide cutover plan and health check with suggested testing and window to test on Sunday afternoon.
| Supplemental Systems | Conversion Schools | N/A | Production with CS 9.0 backup will be done in the CoA environment and accessible during Go Live validation testing
| Check-List for Local Changes | Conversion Schools | N/A
Support | ERP/Help Desk Resource Plan |  | Go
| Security Assignment Process |  |  | Not ready for CCS to test yet.
Escalation Plan
Communications |  |  | Go
| Communications Plan Complete & Communicated |  |  | Carolyn Casey (CIO) delivered Janelle Runyon our CCS Go Live communications plan on 9/13. CCS Marketing & Communications team will provide messaging and timeline for CCS target audiences; which will be delivered to the colleges for distribution.
Outstanding Items |  |  | Go
| Process Scheduling - schedule, dependencies, and status communications |  |  | Held meetings (Dec 2018 & Jan 2019) to review and update processes ran by SBCTC for each pillar. Deliverables from meetings: Improve and update latest process scheduling times, details, & dependencies on ERP Support site. Develop workflow diagrams for processes; including interdependencies between SBCTC and Colleges. | Request SBCTC Mitigation Plan?
Other |  |  | Go
| CCS Remediation Conditions are addressed by SBCTC prior to DG2 Go Live | SBCTC |  | Please see Spokane Remediation Checklist tab for details for each condition.
Data Integrity (PRD) | CS: Course catalog updates in our production environment required for future ctcLink deployment groups should not delete or impact our existing data. | Chantel Black/Alex Bailey |  | Continued risk to FLC data/functionality whenever production code is updated. DG3 course catalog updated in production caused our SCC ABE courses to be deleted/removed. | Request SBCTC Mitigation Plan?
| CS: Due to staff & students only being allowed 1 emplID in ctcLink; current email options allow for the overwriting of another college emails. | Chantel Black/Alex Bailey |  | ctcLink needs a solution for email address storage and usage for multiple colleges sharing the same employees or students. Solution proposed - no status on this fix. | Request SBCTC Mitigation Plan?
| All Pillars: Oracle Image updates and/or changes to Production won't continue to impact/break our normal business processes. |  |  | CCS continues to experience with work stoppage issues following scheduled updates to our production environment. | Request SBCTC Mitigation Plan?
| CoA: CCS continues to experience blocking issues as part of the CoA cutover. | Lisa Hjaltalin |  | Manually updating of journals affected by COA implementation is ongoing. Two major problems, resulting from COA implementation continue to be a problem. One, the combo edit rules are not consistently applied to COA chart string values, resulting in transactions not posting from CS journals. Two, not all item types were migrated into the new COA resulting in CS transactions not systematically moving from SFS in CS into GL. Spokane cannot fix either of these issues, and need the State Board to do so. | Request SBCTC Mitigation Plan?
FY Close /Data Integrity (PRD) | a. Ability to Close YE for (16, 17, 18, 19) | Lisa Hjaltalin |  | Exchanged emails with John Ginther today and asked for an update on why State Board has not posted all adjusting journals and run the closing rules. Also asked for State Board plan to export the adjustments for FY's 16, 17, and 18 into Excel in order to run the closing rules to obtain accurate opening and fund balances. John is looking into it, and will provide a response later. | Request SBCTC Mitigation Plan?
| b. Book to Bank Cash Reconciliation | Lisa Hjaltalin |  | State Board changed the accounts to be used for cash posting, and changed the chart strings on several item types to try and partially alleviate the ongoing problem, however, a total solution has not been identified. Spokane still needs reports that will assist the reconciliation process, and a complete list of Finance system processes that run with dependencies to help us troubleshoot discrepancies. | Request SBCTC Mitigation Plan?
| c.18 million dollar cash variance | Lisa Hjaltalin |  | Spokane has chosen to write off the $18 million book to bank cash variance as the State Board was not able to identify the underlying problem, or provide accurate data on how the variance occurred. We are very concerned a variance will remain, because it was not completely resolved. See response to previous item. | Request SBCTC Mitigation Plan?
Security | Security Role Redesign Signoff |  |  | We have not been delivered all the supporting documentation for CCS to even begin testing the new security roles; and we are waiting for confirmation that the SVL test environment is ready with all CTC and Z_ security roles installed correctly to ensure staff can continue doing their daily jobs post DG2. Even as we won't have time to test and implement all new Security roles by CS9.2/DG2, we do feel it is a blocking issue if 1) SBCTC cannot confirm the readiness of the SVL test environment with the installation of all existing CTC security roles and the new mapped Z_ security roles, 2) deliver the 3 mapping workbooks for each pillar to CCS/ctcLink PM, and 3) complete and publish all CS 9.2 Security mapping guide content on ctcLink Reference Center. We cannot began testing without all of above completed and ready for us to test priority to CS 9.2 and DG2 updates. | Pending completion of all mentioned deliverables
| Security Mapping Workbooks (ctcLink Reference Center) for all pillars completed | SBCTC |  | Not complete, pending completion of Fin and HCM. CS - not published, no status. | Pending completion prior to CS9.2/DG2
| Audit Logs - ready in production; reporting process documented and communicated to CCS | SBCTC |  | SBCTC postponing release to post DG2 due to implementation issues impacting Security Roles in DG2. | Pending completion prior to CS9.2/DG2
| Segregation of Duties - implemented and ready for colleges to use | SBCTC |  | Initial draft provided. Not clear when this will be implemented? | Pending completion prior to CS9.2/DG2
| Cross college data access security - across all pillars; CCS or TCC should not be able to complete financial transactions for other colleges, as well as see highly sensitive data at TCC. | SBCTC |  | Student records, employee addresses, social security numbers, and bank account information. Also brings up question about agreement between SFCC and SCC in regards to seeing each others student information. | Request SBCTC Mitigation Plan?
| QueryTree Security Redesign Implemented in Production | SBCTC |  | Old security query trees/access removed in Fin 9/10, HCM 10/2, and CS 10/15. No issues.
Testing | DG UAT Sprint 6: FISAP UAT Failed |  |  | Pending SBCTC to address FISAP issue. | Pending SBCTC fix for DG UAT
| SF: CS E-214 Fund Balancing Batch Process - Complete and Pass |  |  | CCS Fin was unable to test it to completion during DG2 UAT. We could not validate that transaction are going into GL Fund balanced. | Pending SBCTC response/action
| SF: Validating Tuition - Effective dating working |  |  | All changes to student accounts are impacted by effective dating. SBCTC said they were implementing “the fix” on 7.1.2019 in version 9.0, but it doesn’t work. We cannot yet produce reports out of the system to validate SF activity | Pending SBCTC response/action
| Validation that All CEMLI's tested by SBCTC in CS 9.2 and DG2 environments |  |  | Many CS/FA CEMLI's were tested as part of DG2 UAT's. Need validation that all CEMLI' tests were completed and passed for CS 9.2 and DG2. | ERP is identifying and testing all CEMLI's
Support | Ability for CCS & TCC to go back to normal business processes if Clark or SBCTC experience critical issues during cutover weekend. |  |  | Christy Campbell confirmed that FLC can go back to normal activities in pre DG2 update environment if Clark/SBCTC experience critical issues during upgrade. | Post CS 9.2 Upgrade Production Environment will be backed up to a CoA Environment.
| October payroll backup plan in place |  |  | Concern with Oct payroll potentially impacted by the upgrade weekends (Oct 11th - 14th, & Oct 25th to 28th). | Request SBCTC Mitigation Plan?

## Spokane Remediation Checklist
Spokane Remediation Items
Readiness
R
O
Y
G
Area | Go-Live Criteria | Task Owner | Go-No Go Status? | Comments Required for Items Below | Mitigation Plan:
CCS Remediation Conditions
FY Close
a. Ability to Close YE for (16, 17, 18, 19) |  |  |  | Exchanged emails with John Ginther today (9/18/2019) and asked for an update on why State Board has not posted all adjusting journals and run the closing rules. Also asked for State Board plan to export the adjustments for FY's 16, 17, and 18 into Excel in order to run the closing rules to obtain accurate opening and fund balances. John is looking into it, and will provide a response later.
b. Book to Bank Cash Reconciliation |  |  |  | State Board changed the accounts to be used for cash posting, and changed the chart strings on several item types to try and partially alleviate the ongoing problem, however, a total solution has not been identified. Spokane still needs reports that will assist the reconciliation process, and a complete list of Finance system processes that run with dependencies to help us troubleshoot discrepancies.
c.18 million dollar cash variance |  |  |  | Spokane has chosen to write off the $18 million book to bank cash variance as the State Board was not able to identify the underlying problem, or provide accurate data on how the variance occurred. We are very concerned a variance will remain, because it was not completely resolved. See response to previous item.
Internal Controls (Security)
| Security Role Redesign Signoff |  |  | We have not been delivered all the supporting documentation for CCS to even begin testing the new security roles; and we are waiting for confirmation that the SVL test environment is ready with all CTC and Z_ security roles installed correctly to ensure staff can continue doing their daily jobs post DG2. Even as we won't have time to test and implement all new Security roles by CS9.2/DG2, we do feel it is a blocking issue if 1) SBCTC cannot confirm the readiness of the SVL test environment with the installation of all existing CTC security roles and the new mapped Z_ security roles, 2) deliver the 3 mapping workbooks for each pillar to CCS/ctcLink PM, and 3) complete and publish all CS 9.2 Security mapping guide content on ctcLink Reference Center. We cannot began testing without all of above completed and ready for us to test priority to CS 9.2 and DG2 updates. | Pending completion of all mentioned deliverables
| Security PRD Roles Tested | SBCTC |  | Pending SVL Readiness & supporting documents so CCS can began testing. Not blocking Go Live.
| Security Mapping Matrix Completed | SBCTC |  | Not complete, only received CS SVL Role Assignments. | Pending completion prior to CS9.2/DG2
| Security Mapping Workbooks (ctcLink Reference Center) for all pillars completed | SBCTC |  | Not complete, pending completion of Fin and HCM. CS - not published, no status. | Pending completion prior to CS9.2/DG2
| Audit Logs - ready in production; reporting process documented and communicated to CCS | SBCTC |  | SBCTC postponing release to post DG2 due to implementation issues impacting Security Roles in DG2. | Pending completion prior to CS9.2/DG2
| Segregation of Duties - implemented and ready for colleges to use | SBCTC |  | Initial draft provided. Not clear when this will be implemented? | Pending completion prior to CS9.2/DG2
| Cross college data access security - across all pillars; CCS or TCC should not be able to complete financial transactions for other colleges, as well as see highly sensitive data at TCC. | SBCTC |  | Student records, employee addresses, social security numbers, and bank account information. Also brings up question about agreement between SFCC and SCC in regards to seeing each others student information. | Request SBCTC Mitigation Plan?
| Query Tree Security Redesign | SBCTC |  | Old security query trees/access removed in Fin 9/10, HCM 10/2, and CS 10/15. No issues.
Absence Management
Accurate leave accruals for PT & Adjunct faculty | Leave accruals calculate correctly | Brian Lanier (SBCTC) |  | Sick leave accrual was fixed. Adjunct not working; fix available but SBCTC pushed back. Follow-up on this decision in process. | SBCTC communicates via ticket or email confirming their decision to block the fix from going into Production.
Accurate Reporting for Department of Retirement Services (DRS) | DRS calculates correctly | Brian Lanier (SBCTC) |  | Existing calc issues only impacting 19 employees. SBCTC looking at enhancement for redistribution process and request to CPW for a Global Solution. | Manual processing for 19 employees, until Global automated solution is available.
Faculty Workload Contracts
FWL Package 2 Enhancements | FWL package 2 feature enhancements implemented | SBCTC |  | Most features were implemented March 2019. 2 outstanding critical issues listed below. | Request SBCTC Mitigation Plan?
Dean Approval Process | Viable approval process that can be done in ctcLink | SBCTC |  | FWL package 2 enhancement included a new Dean Approval process, which was not part of the UAT nor communicated to CCS. You can only approve a contract via an email link ONLY. No progress or communications from SBCTC on this fix since March 2019. | Request SBCTC Mitigation Plan?
FWL approval process with multiple supervisors in one department | Ability for departments with more than one supervisor to approve contracts. | SBCTC |  | With Faculty Work Load, when there are more than one supervisor in the same department it does not allow approval of the contract.
Student Billing
Student Statements | Student statement has new detailed format and batch processing working | SBCTC |  | Student statement was improved. Batch processing does not work. | Update by SBCTC to address batch processing.
3rd Party Billing | 3rd Party Invoices has new detailed format and batch processing is working. | SBCTC |  | 3rd Party Invoice - passed UAT in test environment but broken in Production. SBCTC asking CCS to test in DG2 UAT. | Looking for confirmation that 3rd party invoice will be fixed, Batch processing not addressed

## Tacoma Checklist
Tacoma Community College
Readiness
R
O
Y
G
Area | Go-Live Criteria | Task Owner | Go-No Go Status? | Comments Required for Items Below | Mitigation Plan:
Data | Data Clean Up | Disney | G
| Data Validation Completed & Signed Off | Disney | G
Security | Security Mapping Matrix Completed | Disney | Y
| Security PRD Roles Tested | Disney | Y |  | Go-live with old (CTC) roles and cross-walked new (Z) roles for 9.2 functionality. We will add and remove after go-live.
Testing | UAT Critical Issues Resolved | Krauss | G |  | We will receive issue list (2 outstanding) to ascertain criticality level of issues.
| UAT Completed & Signed Off | Krauss | G |  | We are planning to continue testing, with an emphasis on Sprints without a majority tested.
| Payroll Testing | Smith | G
Training | End-User Training Plan | Krauss | Y |  | We are in the middle of end user training as some training will not be released until close to go live. We are confident with training on critical data processing functions.
| Training Documentation / Availability | Krauss | G |  | We will continue to review these for availability and accuracy. Will update local training resources.
| End-User Registered for Training Courses | Krauss | Y |  | We will continue to message about training and monitor/review individual who are signed up.
| Desktop Procedures | Pillar Leads | G |  | We will update these procedures as necessary on an ongoing basis.
Transition | Migration/Cutover Plan | Krauss | Y | Not yet published | SBCTC to send over migration/cutover plan for TCC to review.
| Supplemental Systems | Krauss | G |  | We anticipate any issues but we will monitor.
| Check-List for Local Changes | Krauss | N/A
Support | ERP/Help Desk Resource Plan | Krauss | G | We will be closing some public facing ctcLink dependent services at 4pm on Friday, opening at 10am on Monday.
| Security Assignment Process | Disney | G
| Escalation Plan | Krauss | G
Communications | Communications Plan Complete & Communicated | Krauss | Y | In-progress | We will continue execution of the already-developed communication plan.
Outstanding Items
Other

## Clark Checklist
Clark College
Readiness
| additional items added and measured by Clark |  | R
Area | Go-Live Criteria | Task Owner | Go-No Go Status? | Comments Required for Items Below: | Mitigation Plan:
Data | Data Clean-Up | Susan Maxwell | Y | Have been doing regular cleanup. Julie creating / running queries | Clark cleanup of final issues
| Data Validation Completed & Signed Off | Ryan Paulos | Y | 1,2,3,4,4B - completed. | Review cycle 5 data
| Data Validation Issues Resolved | Ryan Paulos | Y | No outstanding issues. | Review cycle 5 data
| Reports / Queries needed at Go Live are identified or created | Ryan Paulos | Y | in progress, Ryan contacting SMES | Ensure queries SBCTC wrote are in our environment, especially finance.
Data Migration | Utilize college recommended process for SF conversion and migration | Sabra Sand | Y | SBCTC has agreed to return to original conversion plan. | Need documentation for SF - how is it being converted tuition calc turned off
Security | Security Mapping Matrix Completed | Josh Giha | R | 1,610 staff have self-service security (ZZ Navigation Bar Access and ZZ People Soft User). Instruction has been set-up. Financial Aid has been set-up. | Need access to queries that will allow us to audit.
| Security PRD Roles Tested | Josh Giha | R | have SVL - just starting to review with minimal roles. Tanya has begun auditing. PSQ CTC_SEC_ROLEUSER_VW provides a list of all people with a specific role. | Continue to review and audit.
| College Security People Assigned / trained | Josh Giha | O | need training. Susan creating documentation. | Training to be scheduled by SBCTC
| CS-SACR and FM-Preferences mapped | Josh Giha | R | need information about what needs to be set. | need information about what needs to be set.
| College plan for approving / monitoring security roles after Go-Live | Susan Maxwell | Y | agreed upon, need business process for collecting information. | Susan finalize plan. Josh revise tool
Testing | UAT Completed & Signed Off | Ryan Paulos | G | Sprints 1,2,3,4,5 completed; 6 in progress
| UAT Critical Issues Resolved | Ryan Paulos | Y | Test through to resolution | OAA international - GL; SF Hi Low, early alert, Acad Standing (testing limited), fluid staff home page. HCM - absence management - need resolution. WE NEED TO SCHEDULE END TO END TESTING;
| System experience/navigation by end users | Ryan Paulos | G | Most core staff have been in UAT. See if we can use Kael's tool to get out to employees
| Parallel Testing (Dual Processing/SF & Payroll) Completed | Ryan Paulos / Chippi / Sabra / Sherri | Y | Payroll done. SF and FA have more to test. | Resolve issues in SF and FA and complete testing.
| Parallel Testing (Dual Processing/SF & Payroll) Critical Issues Resolved | Ryan Paulos / Chippi / Sabra / Sherri | O | What critical issues exist? | FA: issues - need a in person session to be scheduled by SBCTC; retest disbursement
Training | End-User Training Plan | Jennifer Ward | G | working on review and scheduling, continuing to add as needs are identified
| End-User Registered for Training Courses | Jennifer Ward | Y | We are registering staff for courses now (new process)
| End-User training materials (training document/availability) | Jennifer Ward / Susan Maxwell | Y | Need to complete | Identify and create documents
| Desktop Procedures Created | Tanya Kerr / Andrea Sanchez-Turner | Y | Many in various forms | Review list and finalize
Transition | College Migration/Cutover Plan | Susan Maxwell | G | Dates & Deadlines to college, system takedown and close out
| Supplemental Systems | Andy Barsotti | Y | Met with users, plan in place. Critical applications will not be available at Go Live. Financial aid - top priority | Monitor, build reports as soon as data is available.
| Check-List for Local Changes (Change Action Plans) | Susan Maxwell | Y | Created | Continue to address issues from plan.
| Go Live weekend plan, phone list, Sunday workers | Susan Maxwell | Y | Have plans, missing details - people | Create phone list, finalize room reservations, schedule of people to support (SBCTC and colleges)
Support | College/Help Desk Resource & Escalation Plan | Susan Maxwell | Y | Have flow chart and SME list | Provide names to SBCTC for Solar Winds. Work on FAQ's. Hold training session for IT Service Center, Tech Hub, Student Ambassadors, Tutors
| Security Assignment Process | Susan Maxwell | Y | Have an agreed upon process, need a way to document and workflow. Josh's tool needs updating. | Write up post go live process.
| Accessibility Plan | Susan Maxwell | R | Plan is written. Contracting with someone to create documents and hold labs for students. | Monitor.
Communications | Communications Plan Complete & Communicated | Susan Maxwell | G | In place and following
| Student Communication Plan | Susan Maxwell | Y | In place. | Contracting with graphic designer to create some student templates.
Production | Course Catalog final | Susan Maxwell | G | needs a final verification
| Classes built | Susan Maxwell | Y |  | Fees and instructors
| Requisites built | Susan Maxwell | Y |  | Build multi part requisites
| Transfer rules built | Susan Maxwell | Y |  | Complete as we are able
| AARs built | Susan Maxwell | Y | almost 60 built | Build remaining AARs
Outstanding Items | See WA140 Go Live Conditions.docx

## Clark Conditions
Conditions and Concerns for Go-Live Decision
Conditions to GoLive SBCTC will:
· Written documentation provided to Clark that outlines data conversion for Student Finance, in consultation with Sabra.
· Turn off tuition calculation for fall 2019 and older.
· Complete the security mapping. Completed by October 4th.
· Assign Clark College people to the security roles. Completed by October 4th.
· Complete workflow of the requisition to Purchase Order to Accounts Payable process, as well as the travel process; need SBCTC to focus on workflow and ensure it works as expected
· Resolve the following issues from User Acceptance Testing (UAT):
o Human Capital Management (HCM) - absence management - need resolution.
o Posting of funds from our financial management system (FAM) to Student Finance.
· Convene in-person training session for Financial Aid to demonstrate and train on the whole dual process from application to award of financial aid.
o Student Finance (SF)/Financial Aid – Clark needs to see financial aid disbursements come over correctly to SF in Dual Processing
o SF – Clark needs to see converted SF data convert correctly for financial aid (i.e. FAEXP file)
o External file for PeopleSoft Service Indicator Assignment
· Provide training on adding fees and instructors to classes/courses.
· Remedy issues with posting to general ledger for online admissions application (OAA) and OSECE application for continuing ed.
· Purchasing process needs an approval override mechanism, and there is a security role for this process.
· Provide clarification regarding the accounts payable flow.
· Clarify time and labor outstanding questions from common process workshops:
When employees create a timesheet, we do not know if the they have the option to submit or save for later.
Schedules for employees. We have not received confirmation on who is authorized to change the schedule.
o Provide information to Clark to clearly understand the process for late timesheets.
· Develop a report to identify students who are subject to financial aid repayment of all aid as a result of a complete withdrawal.
· Test the extract job for Financial Aid to capture FAM rollover track codes.
· Timeline for adoption of Policy 188 Accessibility Plan that outlines identified timelines and reporting expectations for SBCTC and Oracle to correct accessibility.
Confirm what changes Oracle and SBCTC have made (or will be made) by the time we go live to be accessible.
Weekly status report of these conditions and concerns from SBCTC, along with who they are assigned to.
HighPoint Mobile available at GoLive.
Additional Areas of Concern to be Addressed by the SBCTC:
· SBCTC staff will ensure that queries they have developed are available to Clark in SVL (i.e., testing environment) and production environment, especially those related to Finance.
· SBCTC staff will provide training to Clark employees regarding understanding and assigning security roles and SACR/Finance preferences. Completed by October 4th.
· SBCTC staff will work with Clark to identify all screens that should have limited access by Clark staff.
General Ledger (GL) – need to see the VPA Process (i.e., state funds compared to reimbursed - John Ginther)
· Provide the ability to run the running start billing in parallel for fall quarter.
· At GoLive, all of self-service needs to be fully accessible.
· Resolve the following issues from UAT:
o Admission application for international to GL;
o Student Finance Hi Low,
o Early Alert,
o Academic Standing (testing limited),
o Fluid staff home page
· Develop training on the new Centralized Absence Management Process to include the following:
o Run, Identify and Calculate - this is now a SBCTC process
o Correct errors
o Finalize absences
o Process for Personal Holiday and Personal Leave Day, meaning if in PeopleSoft a day equals 8 hours how do we at the college level adjust the hours to reflect the actual work shift the employee has. This was a concern brought up last summer and we do not have a documented process yet.
o How do we make manual adjustments / corrections.
Conditions to GoLive Clark will:
· Test security mapping after the security mapping is completed by the SBCTC.
· Test the entire business/workflow process from beginning to end, once the SBCTC has corrected the critical issues as outlined from UAT. Faculty workload is a priority and include Clark’s Human Resource staff.
· Identify and create end-user training documents.
· Complete GoLive weekend planning and documentation.
· Provide training sessions for IT Service Center, Tech Hub, Student Ambassadors, Tutors, and Library.
· Communicate with students regarding upcoming myClark changes.
· Complete requisite and transfer rules.
· Verify direct deposit banking info one last time
· Develop business process in Financial Aid to capture enrollment changes and manually assign service indicators.
· Submit to SBCTC the prioritization of accessibility issues that have been reported by Level Access.
· Data sharing agreement or memorandum of understanding (MOU) must be signed by the person responsible and has full access for/to dataLink. (This does not include employees with access only to the local ODS or data warehouses.)
Additional Areas of Concern to be Addressed by Clark:
· Clark needs to develop a process to request, approve, and monitor security roles after GoLive.
· Clark needs to continue to work on documenting business processes.
· Build reports as soon as data is available, with Financial Aid reports prioritized.
· Create a replacement report for data currently accessed through FMS Query.
· Continue to address issues from change action plans, as identified from the fit/gap analysis.
· Monitor the myClark ctcLink accessibility plan.
· Build remaining Academic Advisement Reports (AARs)
· Determine the amount of costs incurred by Clark regarding compliance with myClark ctcLink accessibility plan to advocate for financial resources from SBCTC.
· Washington Administrative Code (WAC) for Clark College needs to be updated to address the change from a 7 year catalog to a 4 year catalog, to better support ctcLink.

## SBCTC Agency Checklist
SBCTC Agency (Implementation)
Readiness
| additional items added and measured by SBCTC Implementation Team |  | R
O
Y
G
Area | Go-Live Criteria | Task Owner | Go-No Go Status? | Comments Required for Items Below: | Mitigation Plan:
Data | Data Clean Up | Teri Sexton/Ed McCallister/Lisa Espedal
| Data Validation Completed & Signed Off | Teri Sexton/Ed McCallister/Lisa Espedal J. Boesenberg Sign Off |  | Cycle 5 validation not available at this time. Experienced several issues in several places in previous validations. | Fix anything that does not convert correctly via journal entries after go-live. We believe this will be manageable.
Security | Security Mapping Matrix Completed | Teri Sexton/Ed McCallister/Lisa Espedal |  | Mapping for 90% of staff is 90% complete - still need additional layers of security identified and AWE mapped. | Remaining 10% are accounting/accounting related staff that could have elevated access at go-live. This access will need to be reviewed and fixed after go-live.
| Security PRD Roles Tested | Teri Sexton/Ed McCallister/Lisa Espedal |  | Roles that affect the 90% have been reviewed. Issues found have not yet been fixed but we anticipate them being addressed prior to go live. | Any roles not reviewed will be addressed through tickets submitted after go-live. Check with security staff to ensure capacity to address. Teri to create query to validate the security at go-live.
Testing | UAT Critical Issues Resolved | Teri Sexton |  | No regression testing done due to security/AWE not being complete. | Prepare staff to address issues after go-live.
| UAT Completed & Signed Off | John Boesenberg Sign Off |  | Due to regression testing/security | Prepare staff to address issues after go-live.
| Payroll Parallel Testing | Sharon McDaniel/Lisa Espedal |  | Rate used for L&I premiums was dated due to recent increase. All else was as expected. | Monitor
Training
| End-User Training Plan | Dylan Jilek
| Training Documentation / Availability |  |  | Under development but anticipate being completed prior to go-live, except all local training.
| End-User Registered for Training Courses | Training Coordinators |  | Training is ongoing, being updated based on feedback. | Continue to communicate on training opportunities. Monitor participation. Enlist directors to support participation.
| Desktop Procedures | John Boesenberg |  | Dependencies on global training for ESS. | Reminder to staff to develop desktop procedures will be communicated in global messaging.
| Local Training | Thomas Oliver, Ed McCallister, Teri Sexton |  | Need global training to be complete prior to developing local training. | Will develop ASAP after global training is completed. Will likely continue after go-live.
Transition
| Migration/Cutover Plan | John Ginther
| Supplemental Systems | John Ginther |  | Dependent on OBIS | May be completed prior to go-live; if not, manual entries will be made.
| Check-List for Local Changes | John Ginther |  | Examples: CS/EDUC division impact, reporting | Working with ED division to identify training coordinator to facilitate participation of staff in areas of assignment/interest.
Support
| ERP/Help Desk Resource Plan | Teri Sexton
| Security Assignment Process | Teri Sexton |  | Awaiting approval
| Escalation Plan | Teri Sexton
Communications
| Communications Plan Complete & Communicated | Katie Rose
| Website/Tools Updated | Thomas Oliver, Ed McCallister |  | Travel, leave, purchasing references on website under review. | Identifying website links, forms, etc. to update
Outstanding Items
| OCM / Staff Readiness | John Boesenberg |  | Completed ADKAR, continuing efforts to prepare staff for change through communications and training.
Other
Reporting
| SMES set up for queries, reviewed and validated current reports |  |  | Training component for SMEs. | Training material and opportunities made available; Specific queries/reports identified for day-to-day work. Support continues after go-live. Continue communication on learning opt.

## ctcLink Project Checklist
ctcLink Project Team
Readiness
R |  | Assessments by all areas of the ctcLink Project.
O
Y |  | additional items identified by team
G
Area | Go-Live Criteria | OCM/COMMS/TRG | Testing | Technical (TECH) | CS Core | Financial Aid (FA) | Student Financials (SF) | Finance (FIN) | Human Capital Mgmt (HCM) | Consolidated Rating | Comments Required for Items Below: | Mitigation Plan:
Data | Data Clean Up | N/A | N/A | N/A | [6 empty] | CS Core: Enrollment and duplicate cleanup FA: No issues for FA for Data Clean up FIN: Clark has some work still with Job data, as this is impacting Travel and Expenses. SBCTC has had staff turnover going into the most recent data validation cycles. This has led to issues be uncovered. HCM: Data Cleanup updates that have yet to be made will require manual clean up effort post go-live. The data clean up issues have been logged across TL, FWL, Core HR, Absence to track these issues. | FIN: Providing post go live clean up instructions HCM: We are tracking full cleanup detail per entity and have provided this detail and pertinent steps to take to those with cleanup required. We will be meeting as a team to discuss each area of concern each week leading up go-live with follow up to the responsible entity.
| Data Validation Completed & Signed Off | N/A | N/A | N/A | [6 empty] | CS Core: Not aware of formal signoff process, not aware of bio/demo signoff prior to establishing employee oprIDs FA: Fall out occurring and workaround in place FIN: No outstanding issue HCM: Consistent data validation has not occurred and therefore manual cleanup and/or rework will be required post go-live. The data validation issues have been logged across TL, FWL, Core HR, Absence to track these issues. | HCM: We are tracking full data validation detail per entity and have provided this detail and pertinent steps to take to those with validation concerns. We will be meeting as a team to discuss each area of concern each week leading up go-live with follow up to the responsible entity.
| Data Conversion Plan | N/A | N/A | [7 empty] | CS Core: Outstanding conversion issues unresolved, New and recurring issues identified each cycle. Functional team validating technical updates for cycle 5. FA: Waiting on Dry Run Outcomes FIN: Dry run has identified areas where greater coordination in needed. Example how budgets and projects fit together with the GL conversion. SF conversion approach could require additional post conversion steps in finance. TECH: Student Financials needs resolution, executed, tested end to end. Another area is enrollment. We also need a quality management technique to solve problem of upstream source files from Legacy extract process. Also working with FIN/HCM team on other conversion related process concerns. SF: Historical data conversion approach is established and is worked as expected. GL approach is still in testing phase. | FIN: Currently working with the SF team to determine any GL impacts of their conversion approach. Finance is incorporating lessons learned from the dry run into our go live conversion strategy. TECH: Student Financials needs to finalize go-live conversion approach. Actively working with CS team on enrollment resolution. Need a quality control measure for the source files.
Security | Security Mapping Matrix Completed | N/A | N/A | N/A | [6 empty] | CS Core: Previously identified holes in Z role mapping, fluid security gaps. Have provided security team know gaps and working with them to resolve. FA: Reviewed but not tested end to end/Project has been setting up their own SACR Security FIN: There are some gaps that have been identified during the dry run. HCM: No visibility SF: Still needs ZD roles for view only access.
| Security PRD Roles Tested | N/A | N/A | N/A | [6 empty] | CS Core: Not aware of security testing to date FA: Reviewed but not tested end to end FIN: Security role definitions is 65% validated HCM: Security that was defined, has not yet been developed and tested to successfully. Role mappings and the removal of non-pertinent existing roles has not yet been completed. Configuration associated to security may be adjusted based on tested final roles. SF: Still needs to test these roles. | FIN: Actively working on this HCM: Mitigation requires finalization of security role development, testing, and assignment of tested roles to end users. The Functional team has provided feedback for role development and will work with security to test roles when ready. The assignment of roles tested is required to ensure all configured functions are operating as designed. Security must confirm final mapping of designed roles.
| Matrix Validated | N/A | N/A | N/A | [6 empty] | FA: Reviewed but not tested end to end FIN: Security role definitions is 65% validated SF: Validation needs to occur and new roles need to be created. | FIN: Actively working on this
Testing | UAT Critical Issues Resolved | N/A | [8 empty] | FA: Outstanding UAT issues FIN: SBCTC has completed this, Clark is 60-70% complete HCM: FWL UAT has not be completed.10% remaining. UAT for centralized absence is pending with 5% remaining. | TECH: Functional testing needs to complete this testing in UAT.
| UAT Completed & Sign-Off | N/A |  | N/A | [6 empty] | CS Core: Not all functionality tested, including OSECE Cybersource payments, Mobile FA: Outstanding UAT issues FIN: SBCTC has completed this, Clark is 60-70% complete HCM: FWL UAT has not be completed.10% remaining. UAT for centralized absence is pending with 5% remaining. | FIN: Continuing to provide UAT support beyond the scheduled Sprint end dates
| Payroll Parallel Testing | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | FA: Not FA
Training | End-User Training Plan |  |  | N/A | N/A |  | N/A |  |  |  | FA: Owned by Training team - FA Project has worked with FA Trainer FIN: Due to staffing challenges with material development and delivery the original training plan as been significantly altered. This shift could impact post go live support needs. | Mitigation Plan has not been identified by Functional team members, further decision is needed by ctcLink PMO.
| Training Documentation / Availability |  |  | N/A | N/A |  | N/A |  |  |  | FA: Owned by Training team - FA Project has worked with FA Trainer TRG: Courses are still being built FIN: There are still some gaps/missing items in the modules | Mitigation Plan has not been identified by Functional team members, further decision is needed by ctcLink PMO.
| End-User Registered for Training Courses |  |  | N/A | N/A |  | N/A | N/A | N/A |  | FA: Owned by Training team - FA Project has worked with FA Trainer
| Desktop Procedures | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | FA: Owned by Training team - FA Project has worked with FA Trainer
Transition | Migration/Cutover Plan | N/A | N/A |  | N/A | [5 empty] | FA: Waiting on Dry Run Outcomes/Dual Processing setup to be added to Project Plan FIN: Needs to be shared (Check list for security, technical, functional). Updates need to be made based on the dry run results. TECH: Plan is solid with a few adjustments to finalize. FA: Dual Processing set -up needs to be finalized. SF: Cutover plan is dependent on our conversion approach which is undetermined.
| Supplemental Systems | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A |  | FA: Connections to AXWAY and others tied to Dual Processing. SF: Nelnet still not successful post back to PeopleSoft.
| Check-List for Local Changes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Support | ERP/Help Desk Resource Plan | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | FA: Unaware of Support Plan
| Security Assignment Process | N/A | N/A | N/A | N/A |  |  | N/A | N/A |  | FA: Unaware of Support Plan SF: Once the security team is complete, the SF project team will be able to pass this knowledge to the ERP team. New roles also need to be completed.
| Escalation Plan | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A |  | FA: Unaware of Support Plan
Communications | Go-Live Communications Plan |  |  | N/A | [6 empty] | COMMS: Finalize external stakeholders comms process for status announcements; Update go-live talking points; Confirm media/legislative inquiries protocol with DG2 PIOs/PMs; Finalize DG2 Go-Live Plan with PMO
OTHER ITEMS BELOW WERE IDENTIFIED BY OUR TEAM:
TECH | Issues involving Integration broker were encountered during the dry run | [9 empty] | FIN: Certain configuration items require Integration broker. IB was originally turned off during the dry run. After this was turned on encountered issues receiving the required data to support those configuration items | FIN: Issue was raised with the technical team during the dry run.
| Integration Broker - Cross Data Pillar Concerns | [9 empty] | HCM: The dry run upgrade and conversion events made clear the strong reliance on cross pillar data integration consistency. It is concerning that the dry run events are the project's last opportunity to nail down any integration issues. The timing to start/stop/pause various IB messaging is critical. | HCM: Request tech review and IB approach and cross pillar IB impact analysis prior to go-live.
| FWL for Clark | [9 empty] | TECH Approach to get the FWL up to date for Clark to use it after DG2 go-live is not finalized.
OCM | Awareness (College) |  |  | N/A
| Desire (College) |  |  | N/A | [6 empty] | OCM: Finish EUT
| Knowledge (College) |  |  | N/A | [6 empty] | OCM: Post go-live utilization
| Ability (College) | Future - TBD |  | N/A | [6 empty] | OCM: Part of the Local Training Plan
| Reinforcement (College) | Future - TBD |  | N/A
| Awareness (Project) |  |  | N/A
| Desire (Project) |  |  | N/A | [6 empty] | OCM: Cutover/migration plan still being planned - based on Dry Run
| Knowledge (Project) |  |  | N/A | [6 empty] | OCM: Ability to support (ERP & Project) the colleges with current resources? What will this look like? Who will be on site/Clark? What does this look like for FirstLink?
| Ability (Project) |  |  | N/A | [6 empty] | OCM: Effectiveness of ERP support/plan.
| Reinforcement (Project) |  |  | N/A
All Pillars | ERP Support Training and KT | [9 empty] | FIN/HCM: Limited training and knowledgebase on new modules and/or functionality such as TAM or MSS/ESS. TECH: FTDD needs to be updated for all DG2 Developments. | FIN/HCM: Request / Confirm input to what ERP support training has occurred to date. Firm up options to have the ERP team review Training Team's content prior to go-live.
HCM | Oracle Bug - Fluid Timesheets |  |  | N/A | [6 empty] | HCM: The primary fluid timesheet issue has been addressed. ERP however does need to monitor the issue at go-live and going forward. | HCM: ERP support monitoring.
| FWL - Data Cleanup |  |  | N/A | [6 empty] | HCM: Converted Course, Class, and Job Data cleanup has not occurred and as it stands it will not allow calculation and eventually allow payments. Large effort of cleanup. | HCM: Course build and Class build workshop has been and will be held to assist in addressing the issues on the build.
FIN | Bank (positive pay, pcard test file) not confirmed |  |  | N/A | [7 empty] | FIN: Currently working on these items
| Clark has requested changes to PO AWE configuration after scheduled UAT Sprint closed. | [10 empty] | FIN: Currently working on this request. Holding risk discussions with Clark.
CS CORE | Fluid issues in Student Homepage Resolved
| Conversion Issues Resolved | [9 empty] | CS Core: Critical conversion issues for go-live term not resolved. Functional team validating technical updates for cycle 5 run. TECH: Comments updated under the Data Conversion Plan sections. | HCM: Currently working with TECH team to resolve the critical conversion issues. At go-live, we expect the impact to be manual entries if it doesn’t get resolved prior.
| OAA Quick Wins Issues Resolved | [9 empty] | CS Core: Existing PRD issues. .
| Fluid Indexing JobSet Plan | [9 empty] | CS Core: JobSets mocked up and in testing
| Batch AAR JobSet Plan |  |  | N/A | [6 empty] | CS Core: Initial planning stage, JobSets require mock up and testing
| Fluid Knowledge Transfer to ERP Support | [9 empty] | TECH: Provide App Services with update FTDD for Fluid CEMLI's.
Configurations Finalized & Migrated to GLD
Go-Live Plan for Mobile
Plan for Adding Advisors to Instr/Adv Table
Fluid Development Complete & Tested
Waiver Code Customization Developed & Tested
FA | Configuration
Dual Processing
Conversion
SF | ABE - Tuition is not calculating correctly for this population of students | [9 empty] | SF: Ongoing testing is being completed to determine the issue.

## SBCTC Prod. Support Checklist
SBCTC Production Support Team
| additional items added and measured by SBCTC Support Team |  | Readiness
| The support teams: Finance, HCM, Campus Solutions, Security, Data Management, Applications Support, Legacy support and Training. |  | R
O
Y
G
Area | Go-Live Criteria | Task Owner | Go-No Go Status? | Comments Required for Items Below: | Mitigation Plan:
Data | Data Clean Up |  | N/A | Does not apply to production support
| Data Validation Completed & Signed Off |  | O | Suppliers/Customers and HCM comp-time clean-up plan is green. Marked orange for Banking by FIN | Unknown mitigation to address Banking.
Security | Security Mapping Matrix Completed |  | Y | Need to scheduled and train Clark security admins. Marked yellow by Data Services and Security
| Security PRD Roles Tested |  | G | Each area to review critical roles (i.e. super user)
(new) | Query tree redesign |  | G
(new) | College user training on query tree security |  | Y | Need to scheduled and train Clark security admins. Marked yellow by Data Services and Security
(new) | Role grant access for college security admins |  | Y | Finalizing role list in all pillars. Marked yellow by Security
Testing | UAT Critical Issues Resolved |  | N/A | Does not apply to production support
| UAT Completed & Sign-Off |  | N/A | Does not apply to production support
Training | End-User Training Plan |  | Y | Time constraints for staff to participate in training. Marked yellow by Security, Training, Application Services and Legacy
| Training Documentation / Availability |  | Y | Training QRGs need to be updated. Marked yellow by FIN, HCM, Security and Legacy
| End-User Registered for Training Courses |  | Y | Need to scheduled and train Clark security admins. Marked yellow by FIN, HCM, Security and Legacy
| Desktop Procedures |  | Y | Marked yellow by FIN, HCM and Legacy
(new) | Knowledge transfer of new features/functions |  | O | Knowledge transfer needs to happen between team members. Marked orange by CS, FIN, HCM, Testing and Application Services | Meeting with production and project leads scheduled for 10/1/19
(new) | Review of configuration guides |  | O | Knowledge transfer needs to happen between team members. Marked orange by CS, FIN, HCM, Testing and Application Services | Meeting with production and project leads scheduled for 10/1/19
Transition | Migration/Cutover Plan |  | O | No cutover plans at this time. Marked orange by CS, FIN and HCM | Meeting with production and project leads scheduled for 10/1/19
| Supplemental Systems |  | N/A | Does not apply to production support
| Check-List for Local Changes |  | O | Marked orange by CS, FIN and HCM | Meeting with production and project leads scheduled for 10/1/19
(new) | Check-list for production support go-live activities |  | O | Marked orange by CS, FIN, HCM, Data Services, Security, Training, Testing, and Application Services | Meeting with production and project leads scheduled for 10/1/19
Support | ERP/Help Desk Resource Plan |  | O | Will know more after DG2. No current support plans. Marked orange by CS, FIN and HCM | No mitigation plan
| Security Assignment Process |  | O | Will know more after DG2. Marked orange by CS, FIN and HCM | Need list of approvers.
| Escalation Plan |  | O | Will know more after DG2. Marked orange by CS, FIN and HCM | No mitigation plan
(new) | Post go-live support model |  | O | Marked orange by CS, FIN, HCM, Testing, Training and Application Services. | Meeting with production and project leads scheduled for 10/1/19
(new) | Service level agreement |  | G | Agreement signed by Deputy Executive Directors and ITC chair. Still need to do visits with DG2 organizations. Communication plan in development.
(new) | Process and standard operating procedure documentation |  | G | Process identification completed and up for review. Standard operating procedures (SOP) development next.
(new) | Support website redesign |  | G | Initial analysis/review/testing of existing website completed. Recommendation current being drafted.
Communications | Communications Plan Complete & Communicated |  | O | Marked orange by Legacy | No mitigation plan
Outstanding Items
(new) | Staff needs |  | Y | Will know more after DG2. Security currently staffed at 1.5 FTE, plan to be 2.0 FTE in March 2020. Testing may required additional staff when more colleges are added. Application support has two unfilled positions. Marked yellow by CS, FIN, HCM, Security, Testing and Application Services
Other
(new) | Educ division staff training in CS pillar (related to customer support) |  | O | Marked orange by CS | Plan to address actual needs by individual employees.
(new) | Accessibility |  | O | Marked orange by CS and HCM | In progress.