## Sheet1
DG2 Security Delay Mitigation Plan
Week of: | 2019-08-26 | [6 empty] | 2019-09-02 | 2019-09-09 | 2019-09-16 | 2019-09-23 | 2019-09-30 | 2019-10-07 | 2019-10-14 | 2019-10-21 | 2019-10-28
Dates: | 2019-08-26 | 2019-08-27 | 2019-08-28 | 2019-08-29 | 2019-08-30 | 2019-08-31 | 2019-09-01
Activities
HCM Roles In SVL | bar: 2019-08-26
CS Roles in SVL | bar: 2019-08-26
FIN Roles in SVL | bar: 2019-08-28
SBCTC and Colleges Map Assignments and Validate (SVL) | bar: 2019-08-26 to 2019-08-31
Project Team Migrate Security from SVL to UAT | bar: 2019-09-01
SBCTC and Colleges Validate in UAT (Priority UAT Users)
SBCTC and College Go/No-Go Recommendations
DG2 Go/No-Go Steering Committee Decision Point
SBCTC and Colleges Validate any Remaining Users
Clark and SBCTC (Any Conditions Complete/Mitigated)
Clark and SBCTC Cutover and Go-Live
COLOR LEGEND:
SBCTC/Project = Yellow
SBCTC & College Implementation Teams = Light Blue
SBCTC & College Recommendations for Go/No-Go = Light Green
DG2 Governance Decisions = Dark Green
SBCTC and Clark Cutover Activities and Go-Live = Dark Blue