## Slide 1: ctcLink DG3-B Conversion go-Live plan
Summary of Activities and Support Planned for DG3-B Go-Live Weekend and Beyond
Presented April 29, 2020

## Slide 2: dg3-b Conversion Weekend Activities begin: Thursday, may 7, 3 p.m. | end: Monday, May 11 by 8 a.m.
Conversion Activities Begin: Thursday, May 7, 2020
Thursday, May 7
  Legacy System Takedown begins at 3:00pm
Friday, May 8
  PeopleSoft System Takedown begins at 5 p.m.
  Run Conversion Loads begin at approximately 9:00 p.m.
Saturday, May 9
  Security Migration begins in the morning
  Missing Supervisor IDs around 3:00 pm
Sunday, May 10
  College SME College Go-Live Validation, 1-5 p.m.
  College PM/SMEs and ctcLink/SBCTC hold Go/No-Go discussions, 5:00 pm – 6:00 pm
  Go/No-Go Review Call with College PMs, College Executive Sponsor/President: Convene with decision 6:00 pm – 7:00 pm
DG3 Conversion Complete
Monday, May 11, by 8 a.m. GO LIVE!
Post Conversion CyberSource Configuration 10:00 am

## Slide 3: Sme/college leadership engagement in conversion activities
Task Name | Duration | Start | Finish | Stakeholders from College
DG3 B College Conversion Engagement - Please review Conversion Schedule form more details | 7.08d | Fri 5/8/2020 9:50 AM | Sun 5/10/2020 6:30 PM | 
College SME Availability for Functional Questions During Delta Configuration | 3h | Fri 5/8/2020 9:50 AM | Fri 5/8/2020 12:50 PM | College PM/SME
Missing Supervisor IDs | 1 h | Sat 5/9/2020 3:00 PM | Sat 5/9/2020 4:00 PM | College PM/ HCM SMES
College SME Go-Live Validation | 4h | Sun 5/10/2020 1:00 PM | Sun 5/10/2020 5:00 PM | College PM/SME
College SMEs Provide Validation Feedback to College PM; Information is Consolidated/Summarized for Go/No-Go Decision | 15m | Sun 5/10/2020 5:00 PM | Sun 5/10/2020 6:00 PM | College PM/SME
College PM & Leadership Go/No-Go Decision & Discussion with ctcLink PMO & SBCTC Leadership | 15m | Sun 5/10/2020 6:00 PM | Sun 5/10/2020 7:00 PM | College PM, Executive Sponsor, President
CyberSource Configuration | 1h | Mon 5/11/2020 10:00 AM | Mon 5/11/2020 11:00AM | College PM/SME

## Slide 4: Tier 1 - Support Levels & Responsibilities
Support Level | Function | Support Methodology | Responsible Parties/Staff Needs
TIER 1 College Staff | Self-help and user-retrieved information from college staff | Users retrieve support information, security access, and log-in support from web, mobile pages, and learning software (including QRGs and Canvas courses). Users consult with college Business Analysts (Pillar SMEs), Security administrators and approvers and Help Desk staff. | Responsible Parties: College Staff Support Staff Needs: Help Desk staff to assist with technical support for staff and students, including web browser issues and to resolve log-in issues. Security Administrators equipped to assign and remove security roles to staff. Knowledgeable Business Analysts or Pillar SMEs who can provide guidance on best practices, college policies and procedures as it pertains to local business processes Experienced staff to provide local training opportunities to staff who are onboarding, transitioning positions, or need to learn new tasks as it applies to their college role. Tier 2 personnel will respond to requests received through email, web sites (Reference Center and SBCTC Training page), or Canvas.

## Slide 5: Tier 2 - Support Levels & Responsibilities
Support Level | Function | Support Methodology | Responsible Parties/Staff Needs
Tier 2 ctcLink Customer Support Training Team | First point of contact for basic triage | Experienced trainers provide support for basic customer issues such as navigation paths, solving usage problems, and basic configuration. If no solution is available, Tier 2 personnel escalate issues to a higher tier and submit a ticket. | Responsible Parties: Training Team Support Staff Needs: Training staff equipped to solve known problems and training-related issues

## Slide 6: Tier 3 - Support Levels & Responsibilities
Support Level | Function | Support Methodology | Responsible Parties/Staff Needs
Tier 3 ctcLink PeopleSoft Customer Support | In-depth, expert system functional support | Experienced and knowledgeable functional analysts assess issues and provide solutions for issues unresolved by Tier 2. If no solution is available, Tier 3 personnel escalate issues to a higher tier and makes notes in the associated ticket. | Responsible Parties: ctcLink PeopleSoft Customer Support Support Staff Needs: Support staff with deep understanding of system functionality and service, but not necessarily the staff responsible for designing and configuring the system.

## Slide 7: Tier 4 - Support Levels & Responsibilities
Support Level | Function | Support Methodology | Responsible Parties/Staff Needs
Tier 4 ctcLink Project Support | Expert system configuration, integration and implementation support | Access to the highest functional and technical resources available for problem resolution or new feature creation. Tier 4 Support, sometimes in tandem with Tier 3 Support, attempts to duplicate problems and define root causes using product design, configuration, validation, or other specifications. Once a cause is identified, SMEs decide whether to create a new fix, depending on the cause of the problem. New fixes are documented for use by Tier 1 and Tier 2 support staff. | Responsible Parties: Project Functional and Technical Support Support Staff Needs: Advanced functional and technical staff highly skilled in configuration, conversion, integration and implementation of the system. May include consultants and other technical staff responsible for configuring the system.

## Slide 8: Conversion support
We are here to support you!
Sunday, May 10, 2020: 1 to 5 p.m.
  College Go-Live Validation session - WebEx support by pillar
Monday, May 11 – Friday, May 29, 2020 (three weeks, one Support Line)
  Monday through Thursday, 8:30 a.m. to 4 p.m.
  Friday, 8:30 a.m. to 2 p.m.
  No Support Line on Monday, May 25 Holiday
WebEx Links: DG3-B Sunday College Go-Live Validation Session & Post Go-Live Support

## Slide 9: Go-live Milestone communications
DG3-B Milestones email distribution list
  Includes college "ctcLinkAlerts" email addresses
Milestone updates begin Friday, May 8, 3:30 p.m.
Updates continue through Sunday, May 10 – one morning, one midday, one evening
Final Milestone Message when DG3-B is live
College ctcLinkAlerts email converts to official email used by SBCTC-IT for ctcLink downtime, maintenance alerts
  DG3-B college PMs may need to downsize membership on local ctcLinkAlerts email
    Remove executives that were receiving go-live milestones that do not need to receive standard maintenance alerts for live ctcLink colleges.

## Slide 10: DG3-B Conversion Plan links
PWA: https://ctclink.sharepoint.com/sites/pwa/project%20detail%20pages/schedule.aspx?projuid=b632b190-9073-ea11-85a9-00216ae8b43e&ret=0