## Slide 1: DG4 gate 1: peer review
Discussion & Recommendation for Gate 2: Implementation
ctcLink Steering Committee, September 10, 2019
Reuth Kim

## Slide 2: DG4 GATE 1: milestones
Milestones | Target Date | Status
Dashboard Reporting in Status Reports | March 2019 - Present | Ongoing
OCM/College Relations Onsite Visit | March 2019 | Complete
Monthly Check-Ins to Prepare for Peer Review | May, June, July 2019 | Complete
Deliverables for Gate #1 Uploaded to cDR | July 2019 | Complete
College Leadership Approves/Sign-Off Deliverables | July 2019 - Present | *In Progress / Complete
Peer Review | July 29-30, 2019 | Complete
Steering Committee Recommendation/Decision | September 10, 2019 | In Progress
*In Progress for Centralia (refer to slides #7-8) and Wenatchee Valley (refer to slides #12-13).

## Slide 3: Peer Review Participants
Held July 29-30, 2019, hosted by Highline College
DG4 College PM Participants
DG5 & DG6 College PM Observers (non-evaluators)
ctcLink Project Team Members
Centralia, Carrie Powell | Seattle, Daniel Cordas
Edmonds, Ligia Cicos | Wenatchee Valley, Jason Hetterle
Highline, Pat Daniels | 
Bates TC, Beth Cummings (6) | Green River, Sherry Felchlin (5)
Bellingham TC, Nat Reilly (5) | South Puget Sound, Missy Yates (6)
Clover Park TC, Brian Lee (6) | Whatcom, Ken Bronstein (5)
Everett, Tim Rager (5) | 
Christy Campbell | Reuth Kim
Roger Curry | Kristy Snow
Eli Hayes | 

## Slide 4: Gate 1: peer evaluation/rubrics SUMMARY
Item | Deliverable | Centralia | Edmonds | Highline | Seattle | Wenatchee
1 | College Project Charter | 3 | 3 | 3 | 3 | 3
2 | Resource Plan & Budget | 3 | 3 | 3 | 3 | 2
3 | Baseline MS-Project Schedule | 3 | 3 | 3 | 3 | 3
4 | OCM Plan | 3 | 3 | 3 | 3 | 3
4a | Begin Change Impact Analysis | 3 | 3 | 3 | 3 | 3
5 | Communication Plan | 3 | 3 | 3 | 3 | 3
6 | Training Plan | 3 | 3 | 3 | 3 | 3
7 | Risk Management Plan | 2 / 3 | 3 | 3 | 3 | 3
8 | Data Cleansing Plan | 3 | 3 | 3 | 3 | 3
9 | Legacy Business Process Mapping | 3 | 3 | 3 | 3 | 2 / 3
10 | Initial Supplemental Systems Analysis | 2 | 3 | 3 | 3 | 2 / 3
RATING SCALE | 1= LOWEST Missing all components, deliverable not complete | 2= MIDDLE Missing some components, deliverable almost complete | 3= HIGHEST All components identified, deliverable complete

## Slide 5: Additional discussion/Recommendations
DG4 deliverables/comments
DG5 and DG6 PM observations
Next steps
  DG4 - Estimated to begin Global Design Adoption Courses in October 2019
  DG5 - Peer Review slated for early December 2019
Reference Links
  DG4 Peer Review Rubrics – Google sheet
  CDR > College Readiness > DG4 Peer Review

## Slide 6: Appendix
Instructions
Please refer to the appendices for college-specific rubrics summary
College deliverable documents are hyperlinked to cDR in each college’s rubric slide
Appendix Contents, slides 7-13
Rubric Results by College
Status of Items Scored “2”

## Slide 7: Centralia college
GATE#1: CENTRALIA DELIVERABLES | Evaluated by Edmonds | Evaluated by Highline | Evaluated by Seattle | Evaluated by WVC
Item #1 College Project Charter | 3 | 3 | 3 | 3
Item #2 Resource Plan & Budget | 3 | 3 | 3 | 3
Item #3 Baseline MS-Project Schedule | 3 | 3 | 3 | 3
Item #4 OCM Plan | 3 | 3 | 3 | 3
Item #4a Begin Change Impact Analysis | 3 | 3 | 3 | 3
Item #5 Communication Plan | 3 | 3 | 3 | 3
Item #6 Training Plan | 3 | 3 | 3 | 3
Item #7 Risk Management Plan | 3 | 2 | 2 | 2
Item #8 Data Cleansing Plan | 3 | 3 | 3 | 3
Item #9 Legacy Business Process Mapping | 3 | 3 | 3 | 3
Item #10 Initial Supplemental Systems Analysis | 2 | 2 | 2 | 2
*Items scored “2” are targeted to be completed by end of September 2019, refer to slide #8. |  |  |  | 
RATING SCALE | 1= LOWEST Missing all components, deliverable not complete | 2= MIDDLE Missing some components, deliverable almost complete | 3= HIGHEST All components identified, deliverable complete

## Slide 8: Centralia status for items rated “2”
Item No. | Discrepancy | Action | Estimated Time to Complete
Item #7: Risk Management Plan | Needs mitigation, stakeholders/owners and tracking tool. | Risk Log will be distributed to Centralia College Executive Steering Committee and Working Group on Aug. 23, 2019 with a request for feedback. Follow up with one-on-one conversations with the various risk owners. Finalize at the September Working Group Meeting on Sept. 25, 2019. Present to Centralia College Executive Sponsor for sign-off. | End of September 2019
Item #10: Supplemental Systems Analysis | Additional work and analysis needs to be completed. Requires IT involvement. | Centralia IT Department has initiated a comprehensive Supplemental Systems analysis which they expect to complete by Sept. 16, 2019. Executive Management Team will review and is expected to approve on Sept. 27, 2019. | Sept. 27, 2019

## Slide 9: Edmonds community college
GATE 1: EDMONDS DELIVERABLES | Evaluated by Centralia | Evaluated by Highline | Evaluated by Seattle | Evaluated by WVC
Item #1 College Project Charter | 3 | 3 | 3 | 3
Item #2 Resource Plan & Budget | 3 | 3 | 3 | 3
Item #3 Baseline MS-Project Schedule | 3 | 3 | 3 | 3
Item #4 OCM Plan | 3 | 3 | 3 | 3
Item #4a Begin Change Impact Analysis | 3 | 3 | 3 | 3
Item #5 Communication Plan | 3 | 3 | 3 | 3
Item #6 Training Plan | 3 | 3 | 3 | 3
Item #7 Risk Management Plan | 3 | 3 | 3 | 3
Item #8 Data Cleansing Plan | 3 | 3 | 3 | 3
Item #9 Legacy Business Process Mapping | 3 | 3 | 3 | 3
Item #10 Initial Supplemental Systems Analysis | 3 | 3 | 3 | 3
RATING SCALE | 1= LOWEST Missing all components, deliverable not complete | 2= MIDDLE Missing some components, deliverable almost complete | 3= HIGHEST All components identified, deliverable complete

## Slide 10: Highline college
GATE 1: HIGHLINE DELIVERABLES | Evaluated by Centralia | Evaluated by Edmonds | Evaluated by Seattle | Evaluated by WVC
Item #1 College Project Charter | 3 | 3 | 3 | 3
Item #2 Resource Plan & Budget | 3 | 3 | 3 | 3
Item #3 Baseline MS-Project Schedule | 3 | 3 | 3 | 3
Item #4 OCM Plan | 3 | 3 | 3 | 3
Item #4a Begin Change Impact Analysis | 3 | 3 | 3 | 3
Item #5 Communication Plan | 3 | 3 | 3 | 3
Item #6 Training Plan | 3 | 3 | 3 | 3
Item #7 Risk Management Plan | 3 | 3 | 3 | 3
Item #8 Data Cleansing Plan | 3 | 3 | 3 | 3
Item #9 Legacy Business Process Mapping | 3 | 3 | 3 | 3
Item #10 Initial Supplemental Systems Analysis | 3 | 3 | 3 | 3
RATING SCALE | 1= LOWEST Missing all components, deliverable not complete | 2= MIDDLE Missing some components, deliverable almost complete | 3= HIGHEST All components identified, deliverable complete

## Slide 11: Seattle COLLEGE district
GATE 1: SEATTLE DELIVERABLES | Evaluated by Centralia | Evaluated by Edmonds | Evaluated by Highline | Evaluated by WVC
Item #1 College Project Charter | 3 | 3 | 3 | 3
Item #2 Resource Plan & Budget | 3 | 3 | 3 | 3
Item #3 Baseline MS-Project Schedule | 3 | 3 | 3 | 3
Item #4 OCM Plan | 3 | 3 | 3 | 3
Item #4a Begin Change Impact Analysis | 3 | 3 | 3 | 3
Item #5 Communication Plan | 3 | 3 | 3 | 3
Item #6 Training Plan | 3 | 3 | 3 | 3
Item #7 Risk Management Plan | 3 | 3 | 3 | 3
Item #8 Data Cleansing Plan | 3 | 3 | 3 | 3
Item #9 Legacy Business Process Mapping | 3 | 3 | 3 | 3
Item #10 Initial Supplemental Systems Analysis | 3 | 3 | 3 | 3
RATING SCALE | 1= LOWEST Missing all components, deliverable not complete | 2= MIDDLE Missing some components, deliverable almost complete | 3= HIGHEST All components identified, deliverable complete

## Slide 12: Wenatchee valley COLLEGE
GATE 1: WVC DELIVERABLES | Evaluated by Centralia | Evaluated by Edmonds | Evaluated by Highline | Evaluated by Seattle
Item #1 College Project Charter | 3 | 3 | 3 | 3
Item #2 Resource Plan & Budget | 2 | 2 | 2 | 2
Item #3 Baseline MS-Project Schedule | 3 | 3 | 3 | 3
Item #4 OCM Plan | 3 | 3 | 3 | 3
Item #4a Begin Change Impact Analysis | 3 | 3 | 3 | 3
Item #5 Communication Plan | 3 | 3 | 3 | 3
Item #6 Training Plan | 3 | 3 | 3 | 3
Item #7 Risk Management Plan | 3 | 3 | 3 | 3
Item #8 Data Cleansing Plan | 3 | 3 | 3 | 3
Item #9 Legacy Business Process Mapping | 2 | 3 | 3 | 3
Item #10 Initial Supplemental Systems Analysis | 2 | 3 | 2 | 3
*Items scored “2” are targeted to be completed by end of September. Refer to slide #13. |  |  |  | 
RATING SCALE | 1= LOWEST Missing all components, deliverable not complete | 2= MIDDLE Missing some components, deliverable almost complete | 3= HIGHEST All components identified, deliverable complete

## Slide 13: Wenatchee status for items rated “2”
Item No. | Discrepancy | Action | Estimated Time to Complete
Item #2: Budget | No approved budget for this fiscal year. | Cabinet is still finalizing details of this year’s budget. In the meantime, WVC’s PM is allowed to operate from last year’s budget amounts. This allows the PM to make purchases and move forward with ctcLink. There is no barrier to required spending at this point. Budget will go to the Board of Trustees on Sept. 11, 2019 for approval. | Sept. 15, 2019
Item #9: Legacy Business Process Mapping | Correlate IWP processes to specific maps. | While not required, WVC PM thinks this process is very valuable. This is additional work, but will help the SMEs with more engagement and understanding of the current process. FIN is complete. | Sept. 30, 2019
Item #10: Supplemental Systems Analysis | Add budget impacts (if any). Further impact analysis required. | Adding a project assistant to help with this task. WVC has completed the work from IT-developed applications. No currently listed applications have a quantifiable budget impact. We will use the Legacy Business Process Maps to complete the rest with a review from the SMEs. | Sept. 30, 2019