## Slide 1: DG5 gate 1: peer review
Discussion & Recommendation for Gate 2: Implementation
ctcLink Steering Committee, Dec. 17, 2019
Reuth Kim, ctcLink Quality Assurance, Risk & Issue Management PM
Christy Campbell, ctcLink Project Director

## Slide 2: DG 5 GATE 1: milestones
Milestones | Target Date | Status
Dashboard Reporting in Status Reports | June 2019 to Present | Ongoing
OCM/College Relations Onsite Visit | June 2019 | Complete
Monthly Check-Ins to Prepare for Peer Review | September, October, November 2019 | Complete
Deliverables for Gate #1 Uploaded to cDR | November 2019 | Complete
College Leadership Approves/Sign-Off Deliverables | November 2019-Present | *In Progress / Complete
Peer Review | December 9-11, 2019 | Complete
Steering Committee Recommendation/Decision | December 17, 2019 | In Progress
*In progress for Green River College. See appendix slides #13-#14

## Slide 3: Peer review participants
DG5 College PM and Teams Bellevue: Alec Campbell, Rodger Harrison Bellingham: Nat Reilly Big Bend: Linda Schoonmaker (ES), Angela Garza, Patrick Steele Everett: Sindie Howland, Tim Rager, Pat Sisneros (ES) Grays Harbor: Andrew Glass, Jason Lake Green River: Sherry Felchlin Skagit Valley: Benjamin St. Germain Whatcom: Kenneth Bronstein | DG6 Observers Columbia Basin: Brian Dexter, Janet Garza Renton: Dennis Chin, Marzena Sasin, Paul Corigliano (ES) Shoreline: Joe Chiappa Walla Walla: Lisa Chamberlin Yakima Valley: Clarissa Wolfe, Justin Busby ctcLink Project Team Members Christy Campbell Reuth Kim Roger Curry Eli Hayes

## Slide 4: Gate 1: peer evaluation/rubrics SUMMARY
Item | Deliverable | Bellevue | Bellingham | Big Bend | Everett
1 | College Project Charter | 3 | 3 | 3 | 3
2 | Resource Plan & Budget | 3 | 3 | 3 | 3
3 | Baseline MS-Project Schedule | 3 | 3 | 3 | 3
4 | OCM Plan | 3 | 3 | 3 | 3
4a | Begin Change Impact Analysis | 3 | 3 | 3 | 3
5 | Communication Plan | 3 | 3 | 3 | 3
6 | Training Plan | 3 | 3 | 3 | 3
7 | Risk Management Plan | 3 | 3 | 3 | 3
8 | Data Cleansing Plan | 3 | 3 | 3 | 3
9 | Legacy Business Process Mapping | 3 | 3 | 3 | 3
10 | Initial Supplemental Systems Analysis | 3 | 3 | 3 | 3
RATING SCALE | 1 = LOWEST Missing all components, deliverable not complete | 2 = MIDDLE Missing some components, deliverable almost complete | 3 = HIGHEST All components identified, deliverable complete

## Slide 5: Gate 1: peer evaluation/rubrics SUMMARY
Item | Deliverable | Grays Harbor | Green River | Skagit | Whatcom
1 | College Project Charter | 3 | 3 | 3 | 3
2 | Resource Plan & Budget | 3 | 2/3 | 3 | 3
3 | Baseline MS-Project Schedule | 3 | 3 | 3 | 3
4 | OCM Plan | 3 | 3 | 3 | 3
4a | Begin Change Impact Analysis | 3 | 3 | 3 | 3
5 | Communication Plan | 3 | 3 | 3 | 3
6 | Training Plan | 3 | 3 | 3 | 3
7 | Risk Management Plan | 3 | 3 | 3 | 3
8 | Data Cleansing Plan | 3 | 3 | 3 | 3
9 | Legacy Business Process Mapping | 3 | 3 | 3 | 3
10 | Initial Supplemental Systems Analysis | 3 | 3 | 3 | 3
RATING SCALE | 1 = LOWEST Missing all components, deliverable not complete | 2 = MIDDLE Missing some components, deliverable almost complete | 3 = HIGHEST All components identified, deliverable complete

## Slide 6: Additional discussion/Recommendations
DG5 deliverables/comments
DG6 PM observations
Executive Sponsor participation
Next steps
  DG5 - Estimated to begin Global Design Adoption (GDA) courses end of March 2020
  DG6 - Peer Review slated for July 2020
Reference Links
  DG5 Peer Review Rubrics – Google sheet
  CDR > College Readiness > DG5 Peer Review

## Slide 7: Appendix
Refer to the appendices for college-specific rubrics summary
College deliverable documents are hyperlinked to cDR in each college’s rubric slide
Appendix Contents
Rubric Results by College: slides 8-16
Status of Items with a “2” Score: slide 14

## Slide 8: Bellevue college
 | Rating per peer college |  |  |  |  |  |  |  | 
GATE #1: BELLEVUE DELIVERABLES | Bellingham | Big Bend | Everett | Grays Harbor | Green River | Skagit | Whatcom | Missing Components/ Recommendations from Peer Review: | Additional Comments
Item #1 College Project Charter | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | strong signature, support
Item #2 Resource Plan & Budget | 3 | 3 | 3 | 3 | 3 | 3 | 3 | recommend to flesh out the budget | 
Item #3 Baseline MS Project Schedule | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 
Item #4 OCM Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 
Item #4a Begin Change Impact Analysis | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 
Item #5 Communication Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 
Item #6 Training Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 
Item #7 Risk Management Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 | tracking log is recommended as new PM comes on board | 
Item #8 Data Cleansing Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 
Item #9 Legacy Business Process Mapping | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 
Item #10 Initial Supplemental Systems Analysis | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 

## Slide 9: Bellingham technical college
 | Rating per peer college |  |  |  |  |  |  |  | 
GATE #1: BELLINGHAM TC DELIVERABLES | Bellevue | Big Bend | Everett | Grays Harbor | Green River | Skagit | Whatcom | Missing Components/ Recommendations from Peer Review: | Additional Comments
Item #1 College Project Charter | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | great it is in one doc
Item #2 Resource Plan & Budget | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | impressed with development of budget
Item #3 Baseline MS-Project Schedule | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 
Item #4 OCM Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 
Item #4a Begin Change Impact Analysis | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 
Item #5 Communication Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 
Item #6 Training Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 
Item #7 Risk Management Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | great model for future DGs
Item #8 Data Cleansing Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 
Item #9 Legacy Business Process Mapping | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 
Item #10 Initial Supplemental Systems Analysis | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 

## Slide 10: BIG BEND COMMUNITY college
 | Rating per peer college |  |  |  |  |  |  |  | 
GATE #1: BIG BEND DELIVERABLES | Bellevue | Bellingham | Everett | Grays Harbor | Green River | Skagit | Whatcom | Missing Components/ Recommendations from Peer Review: | Additional Comments
Item #1 College Project Charter | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 
Item #2 Resource Plan & Budget | 3 | 3 | 3 | 3 | 3 | 3 | 3 | recommend adding a line item to address FY20-21 and through go-live | 
Item #3 Baseline MS-Project Schedule | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 
Item #4 OCM Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 
Item #4a Begin Change Impact Analysis | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | great model
Item #5 Communication Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 
Item #6 Training Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 
Item #7 Risk Management Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 
Item #8 Data Cleansing Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 
Item #9 Legacy Business Process Mapping | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 
Item #10 Initial Supplemental Systems Analysis | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 

## Slide 11: EVERETT COMMUNITY college
 | Rating per peer college |  |  |  |  |  |  |  | 
GATE #1: EVERETT DELIVERABLES | Bellevue | Bellingham | Big Bend | Grays Harbor | Green River | Skagit | Whatcom | Missing Components/ Recommendations from Peer Review: | Additional Comments
Item #1 College Project Charter | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | excellent
Item #2 Resource Plan & Budget | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | great layout
Item #3 Baseline MS-Project Schedule | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 
Item #4 OCM Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 
Item #4a Begin Change Impact Analysis | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 
Item #5 Communication Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 
Item #6 Training Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 
Item #7 Risk Management Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 
Item #8 Data Cleansing Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 
Item #9 Legacy Business Process Mapping | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 
Item #10 Initial Supplemental Systems Analysis | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 

## Slide 12: Grays harbor college
 | Rating per peer college |  |  |  |  |  |  |  | 
GATE #1: GRAYS HARBOR DELIVERABLES | Bellevue | Bellingham | Big Bend | Everett | Green River | Skagit | Whatcom | Missing Components/ Recommendations from Peer Review: | Additional Comments
Item #1 College Project Charter | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 
Item #2 Resource Plan & Budget | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | great job on budget development and structure
Item #3 Baseline MS-Project Schedule | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 
Item #4 OCM Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 
Item #4a Begin Change Impact Analysis | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | realistic OCM/training/comms plans
Item #5 Communication Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 
Item #6 Training Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 
Item #7 Risk Management Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 
Item #8 Data Cleansing Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 
Item #9 Legacy Business Process Mapping | 3 | 3 | 3 | 3 | 3 | 3 | 3 | DG5 PMs recommend BPM work continue at 90% of target by start of implementation | despite challenges GHC has faced, tremendous progress has been accomplished
Item #10 Initial Supplemental Systems Analysis | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 

## Slide 13: Green river college
 | Rating per peer college |  |  |  |  |  |  |  | 
GATE #1: GREEN RIVER DELIVERABLES | Bellevue | Bellingham | Big Bend | Everett | Grays Harbor | Skagit | Whatcom | Missing Components/ Recommendations from Peer Review: | Additional Comments
Item #1 College Project Charter | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | appreciate list of staff/structure
Item #2 Resource Plan & Budget | 2 | 2 | 3 | 2 | 2 | 2 | 2 | forecast budget for future years | 
Item #3 Baseline MS-Project Schedule | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 
Item #4 OCM Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 
Item #4a Begin Change Impact Analysis | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 
Item #5 Communication Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 
Item #6 Training Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 
Item #7 Risk Management Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 
Item #8 Data Cleansing Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 
Item #9 Legacy Business Process Mapping | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 
Item #10 Initial Supplemental Systems Analysis | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 

## Slide 14: Green River COLLEGE status for item rated “2”
Item No. | Discrepancy | Assumptions | Action | Estimated Time to Complete
Item #3 Resource Plan & Budget | Although Green River provided a “Budget" document, it did not represent budget forecasting; but rather, the actual budget line items incurred for ctcLink from academic years 2013 - 2020. No budget was established for the ctcLink project from the current period through Go-Live (10/2021) and the expected stabilization period. | Assumptions regarding resources were provided in a narrative: GRC is investing $250,000 annually for the ctcLink Project. GRC is investing in a full-time Project Manager Existing College Staff will add the roles of training lead, security lead, report lead, testing lead, pillar leads to their job duties. Existing computer labs and rooms will be used for trainings, meetings, testing, command center, helpdesk, and support. ctcLink training will be delivered via Canvas and WebEx per current SBCTC plan. The expected Go-Live date for GRC is February 2021. Pillar leads will be the Organizational Change Managers. The expected Go-Live date for GRC is February 2021. However, these were not provided as annualized expenses and did not include estimates for travel, training or hosting events associated with the project. | Green River will provide a budget reflective of anticipated income/revenue and expense for the expected duration of the ctcLink implementation in 2022. | January 2020

## Slide 15: SKAGIT VALLEY college
 | Rating per peer college |  |  |  |  |  |  |  | 
GATE #1: SKAGIT VALLEY DELIVERABLES | Bellevue | Bellingham | Big Bend | Everett | Grays Harbor | Green River | Whatcom | Missing Components/ Recommendations from Peer Review: | Additional Comments
Item #1 College Project Charter | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | great inclusion of guiding principles
Item #2 Resource Plan & Budget | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | great model
Item #3 Baseline MS-Project Schedule | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 
Item #4 OCM Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 
Item #4a Begin Change Impact Analysis | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 
Item #5 Communication Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 | recommend to provide narrative | 
Item #6 Training Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 
Item #7 Risk Management Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 
Item #8 Data Cleansing Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 
Item #9 Legacy Business Process Mapping | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 
Item #10 Initial Supplemental Systems Analysis | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | commended for finding shadow systems

## Slide 16: Whatcom community college
 | Rating per peer college |  |  |  |  |  |  |  | 
GATE #1: WHATCOM DELIVERABLES | Bellevue | Bellingham | Big Bend | Everett | Grays Harbor | Green River | Skagit | Missing Components/ Recommendations from Peer Review: | Additional Comments
Item #1 College Project Charter | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 
Item #2 Resource Plan & Budget | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | nice inclusion of longevity of SMEs
Item #3 Baseline MS-Project Schedule | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 
Item #4 OCM Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 
Item #4a Begin Change Impact Analysis | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 
Item #5 Communication Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 
Item #6 Training Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 
Item #7 Risk Management Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 
Item #8 Data Cleansing Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 
Item #9 Legacy Business Process Mapping | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 
Item #10 Initial Supplemental Systems Analysis | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | GREAT NARRATIVE