## Slide 1: DG6 gate 1: peer review
Discussion & Recommendation for Gate 2: Implementation
ctcLink Steering Committee, August 11, 2020
Reuth Kim, ctcLink Quality Assurance, Risk & Issue Management PM
Christy Campbell, ctcLink Project Director

## Slide 2: DG6 GATE 1: milestones
Milestones | Target Date | Status
Dashboard Reporting in Status Reports | December 2019 to Present | Ongoing
OCM/College Relations Onsite Visit | Fall 2019 | Complete
Monthly Check-Ins to Prepare for Peer Review | January 2020-June 2020 | Complete
Deliverables for Gate #1 Uploaded to cDR | June 2020 | Complete
College Leadership Approves/Sign-Off Deliverables | June 2020 | Complete
Virtual Peer Review | July 13-16, 2020 | Complete
Steering Committee Recommendation/Decision | August 11, 2020 | In Progress

## Slide 3: Peer review participants, July 13-16, 2020
DG6 COLLEGES Bates: Beth Cummings Clover Park: Brian Lee Columbia Basin: Juri Tikerpuu Lake Washington: Lauren Heller Renton: Dennis Chin, Marzena Sasin, Sanjana Gaddam, Paul Corigliano (ES) Shoreline: Joe Chiappa South Puget Sound: Missy Yates Walla Walla: Lisa Chamberlin Yakima Valley: Clarissa Wolfe, Teresa Rich | CTCLINK PROJECT TEAM MEMBERS Christy Campbell Reuth Kim Roger Curry Susan Maxwell Eli Hayes

## Slide 4: Gate 1: peer evaluation/rubrics SUMMARY
Item | Deliverable | Bates | Clover Park | Columbia Basin | Lake WA | Renton
1 | College Project Charter | 3 | 3 | 3 | 3 | 3
2 | Resource Plan & Budget | 2 | 3 | 3 | 3 | 3
3 | Baseline MS-Project Schedule | 3 | 3 | 3 | 3 | 3
4 | OCM Plan | 3 | 3 | 3 | 3 | 3
4a | Begin Change Impact Analysis | 3 | 3 | 3 | 3 | 3
5 | Communication Plan | 3 | 3 | 3 | 3 | 3
6 | Training Plan | 3 | 3 | 3 | 3 | 3
7 | Risk Management Plan | 3 | 3 | 3 | 3 | 3
8 | Data Cleansing Plan | 3 | 3 | 3 | 3 | 3
9 | Legacy Business Process Mapping | 2/3 | 3 | 3 | 3 | 2/3
10 | Initial Supplemental Systems Analysis | 3 | 3 | 3 | 3 | 3
RATING SCALE | 1 = LOWEST Missing all components, deliverable not complete | 2 = MIDDLE Missing some components, deliverable almost complete | 3 = HIGHEST All components identified, deliverable complete

## Slide 5: Gate 1: peer evaluation/rubrics SUMMARY
Item | Deliverable | Shoreline | South Puget Sound | Walla Walla | Yakima Valley
1 | College Project Charter | 3 | 3 | 3 | 3
2 | Resource Plan & Budget | 3 | 3 | 3 | 3
3 | Baseline MS-Project Schedule | 3 | 3 | 3 | 3
4 | OCM Plan | 3 | 3 | 3 | 3
4a | Begin Change Impact Analysis | 3 | 3 | 3 | 3
5 | Communication Plan | 3 | 3 | 3 | 3
6 | Training Plan | 3 | 3 | 3 | 3
7 | Risk Management Plan | 3 | 3 | 3 | 3
8 | Data Cleansing Plan | 3 | 3 | 3 | 3
9 | Legacy Business Process Mapping | 3 | 3 | 3 | 3
10 | Initial Supplemental Systems Analysis | 3 | 3 | 3 | 3
RATING SCALE | 1 = LOWEST Missing all components, deliverable not complete | 2 = MIDDLE Missing some components, deliverable almost complete | 3 = HIGHEST All components identified, deliverable complete

## Slide 6
DG6 Initiation Phase Completion Summary Dashboard – July 20-31, 2020
College/District | As of July 31, 2020 | Target Percentage Pre-Implementation
Bates Technical College | 55% | 75%
Clover Park Technical College | 70% | 75%
Columbia Basin College | 70% | 75%
Lake Washington Inst. of Technology | 68% | 75%
Renton Technical College | 49% | 75%
Shoreline Community College | 74% | 75%
So. Puget Sound Community College | 71% | 75%
Walla Walla Community College | 72% | 75%
Yakima Valley College | 75% | 75%
Percentage of deliverables completed and tracked in Project Web App (PWA) by each college Project Manager:
College Orientation & Resourcing
College Project Planning (from templates)
Conduct Initial Data Cleansing
Document Current Legacy Business Processes
Supplemental Systems Analysis

## Slide 7: Additional discussion/Recommendations
DG6 deliverables/comments
DG6 PM observations
Executive Sponsor participation
Next steps
  DG6 - Estimated to begin Global Design Adoption (GDA) courses October 2020
Reference Links
  DG6 Peer Review Rubrics – Google sheet
  CDR > College Readiness > DG6 Peer Review

## Slide 8: Appendix
Refer to the appendices for college-specific rubrics summary
College deliverable documents are hyperlinked to cDR in each college’s rubric slide
Appendix Contents
Rubric Results by College: slides 9-19
Status of Items with a “2” Score: slide 10 & 15

## Slide 9: BATES technical college
 | Rating per peer college |  |  |  |  |  |  | 
GATE #1: DELIVERABLES | Clover Park | Columbia Basin | Lake Washington | Renton | Shoreline | South Puget Sound | Walla Walla | Yakima Valley
Item #1 College Project Charter | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #2 Resource Plan & Budget | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Item #3 Baseline MS Project Schedule | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #4 OCM Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #4a Begin Change Impact Analysis | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #5 Communication Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #6 Training Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #7 Risk Management Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #8 Data Cleansing Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #9 Legacy Business Process Mapping | 3 | 2 | 2 | 3 | 2 | 2 | 3 | 2
Item #10 Initial Supplemental Systems Analysis | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3

## Slide 10: Bates technical COLLEGE status for items rated “2”
Item No. | Discrepancy | Assumptions | Action | Estimated Time to Complete
Item #3 Resource Plan & Budget | Budget categories referenced as “To Be Determined” | Schedule: Earlier deployment groups are successful and timelines are constant. Project Scope remains defined. Financial: Economic downturn does not exceed expectations allowing for college staffing levels to stay the same. ctcLink is a prioritized college initiative. Technology: Increased use of cloud services and remote collaboration reduces need for travel. | Vice President of Finance & Admin Services was an open position prior to Peer Review. Senior College officials engaged and actively reviewing budget requirements. | Completed 8/1/2020 Nicholas Lutes named VP 10/31/2020
Item # 9 Legacy Business Process Mapping | Percent complete did not meet expectations. | Schedule: Completion of business process maps are prioritized college initiative. Change Impact Analysis and BP Fit Gap sessions is scheduled. Project Scope: Focus on value chain inventory in preparation for business process fit gap sessions. Financial: College resources directed to data breech recovery will be redirected to supporting ctcLink related project activities. Technology: Employees on remote assignment will continue to collaborate via LucidChart and O365 to create and verify value chain inventory is both accurate and well understood. | Inventory tracking is monitored by PM/OCM and completion goals identified. Finance: 25% per week during month of August which aligns with lighter schedules. Sept/Oct for Review. IT & Security: New Service Desk HelpDesk implementation and updated protocols for account creation/mgmt. | Ongoing 9/1/2020 10/1/2020 All – 10/15/2020

## Slide 11: CLOVER PARK technical college
 | Rating per peer college |  |  |  |  |  |  | 
GATE #1: DELIVERABLES | Bates | Columbia Basin | Lake Washington | Renton | Shoreline | South Puget Sound | Walla Walla | Yakima Valley
Item #1 College Project Charter | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #2 Resource Plan & Budget | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #3 Baseline MS Project Schedule | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #4 OCM Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #4a Begin Change Impact Analysis | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #5 Communication Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #6 Training Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #7 Risk Management Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #8 Data Cleansing Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #9 Legacy Business Process Mapping | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #10 Initial Supplemental Systems Analysis | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3

## Slide 12: Columbia basin college
 | Rating per peer college |  |  |  |  |  |  | 
GATE #1: DELIVERABLES | Bates | Clover Park | Lake Washington | Renton | Shoreline | South Puget Sound | Walla Walla | Yakima Valley
Item #1 College Project Charter | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #2 Resource Plan & Budget | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #3 Baseline MS Project Schedule | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #4 OCM Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #4a Begin Change Impact Analysis | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #5 Communication Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #6 Training Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #7 Risk Management Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #8 Data Cleansing Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #9 Legacy Business Process Mapping | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #10 Initial Supplemental Systems Analysis | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3

## Slide 13: Lake Washington inst. of technology
 | Rating per peer college |  |  |  |  |  |  | 
GATE #1: DELIVERABLES | Bates | Clover Park | Columbia Basin | Renton | Shoreline | South Puget Sound | Walla Walla | Yakima Valley
Item #1 College Project Charter | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #2 Resource Plan & Budget | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #3 Baseline MS Project Schedule | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #4 OCM Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #4a Begin Change Impact Analysis | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #5 Communication Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #6 Training Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #7 Risk Management Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #8 Data Cleansing Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #9 Legacy Business Process Mapping | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #10 Initial Supplemental Systems Analysis | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3

## Slide 14: Renton technical college
 | Rating per peer college |  |  |  |  |  |  | 
GATE #1: DELIVERABLES | Bates | Clover Park | Columbia Basin | Lake Washington | Shoreline | South Puget Sound | Walla Walla | Yakima Valley
Item #1 College Project Charter | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #2 Resource Plan & Budget | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #3 Baseline MS Project Schedule | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #4 OCM Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #4a Begin Change Impact Analysis | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #5 Communication Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #6 Training Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #7 Risk Management Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #8 Data Cleansing Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #9 Legacy Business Process Mapping | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2
Item #10 Initial Supplemental Systems Analysis | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3

## Slide 15: RENTON TECHNICAL COLLEGE status for item rated “2”
Item No. | Discrepancy | Assumptions | Action | Estimated Time to Complete
Item # 9 Legacy Business Process Mapping | Due to ctcLink staff turnover, RTC did not kick off the project until November 2019 and process mapping did not begin until that time. The percentage (25%) provided at Peer Review time was lower than the actual percentage (30%) at RTC as we were given Process Maps a day before the Peer Review and didn’t update the plan. The percentage of completion for Renton Technical College’s Business Processes was presented to its Deployment Group 6 peers was at 25% and the goal was 75%. | Renton Technical College has an established structure and plan to map legacy business processes, but there was concern expressed by DG6 Peer colleges that there wouldn’t be time to complete the maps before implementation begins. | Since the Peer Review, RTC has conducted a workshop focused on ironing out questions and concerns with its Steering Committee about Business Process Mapping and the current state of RTC’s overall percentage of completion. The project team enhanced the tracking tool after Peer Review to add provisions for accountability and addition monitoring. In addition, the RTC Project Team will regularly schedule individual (rather than group) Business Process Mapping sessions with specific Pillar Leads to review their progress and work closely with them to chart their processes. | August 31, 2020

## Slide 16: SHORELINE COMMUNITY COLLEGE
 | Rating per peer college |  |  |  |  |  |  | 
GATE #1: DELIVERABLES | Bates | Clover Park | Columbia Basin | Lake Washington | Renton | South Puget Sound | Walla Walla | Yakima Valley
Item #1 College Project Charter | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #2 Resource Plan & Budget | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #3 Baseline MS Project Schedule | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #4 OCM Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #4a Begin Change Impact Analysis | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #5 Communication Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #6 Training Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #7 Risk Management Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #8 Data Cleansing Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #9 Legacy Business Process Mapping | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #10 Initial Supplemental Systems Analysis | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3

## Slide 17: South Puget sound
 | Rating per peer college |  |  |  |  |  |  | 
GATE #1: DELIVERABLES | Bates | Clover Park | Columbia Basin | Lake Washington | Renton | Shoreline | Walla Walla | Yakima Valley
Item #1 College Project Charter | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #2 Resource Plan & Budget | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #3 Baseline MS Project Schedule | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #4 OCM Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #4a Begin Change Impact Analysis | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #5 Communication Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #6 Training Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #7 Risk Management Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #8 Data Cleansing Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #9 Legacy Business Process Mapping | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #10 Initial Supplemental Systems Analysis | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3

## Slide 18: Walla walla COMMUNITY COLLEGE
 | Rating per peer college |  |  |  |  |  |  | 
GATE #1: DELIVERABLES | Bates | Clover Park | Columbia Basin | Lake Washington | Renton | Shoreline | South Puget Sound | Yakima Valley
Item #1 College Project Charter | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #2 Resource Plan & Budget | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #3 Baseline MS Project Schedule | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #4 OCM Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #4a Begin Change Impact Analysis | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #5 Communication Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #6 Training Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #7 Risk Management Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #8 Data Cleansing Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #9 Legacy Business Process Mapping | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #10 Initial Supplemental Systems Analysis | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3

## Slide 19: Yakima valley COLLEGE
 | Rating per peer college |  |  |  |  |  |  | 
GATE #1: DELIVERABLES | Bates | Clover Park | Columbia Basin | Lake Washington | Renton | Shoreline | South Puget Sound | Walla Walla
Item #1 College Project Charter | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #2 Resource Plan & Budget | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #3 Baseline MS Project Schedule | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #4 OCM Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #4a Begin Change Impact Analysis | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #5 Communication Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #6 Training Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #7 Risk Management Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #8 Data Cleansing Plan | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #9 Legacy Business Process Mapping | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Item #10 Initial Supplemental Systems Analysis | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3