## Slide 1: Ctclink Top PROGRAM Risks
# | Risk Description | Mitigation | Deployment Focused
1. | College Project Manager/Executive Sponsor Engagement | Hire a Project Manager Identify engaged and supportive Executive Sponsor | Deployment Group 5 Deployment Group 6
2. | College Resource Availability Other College and Systemwide Initiatives Daily Operations Staff Retention (Retirement/Role Changes) | Create ctcLink resource plan Backfill or add additional staff as needed for your college | All Deployment Groups
3. | College leadership understanding of ctcLink project methodology and resource participation requirements Pre-implementation Implementation Post-implementation | ctcLink Project Management Office to provide detailed resource plan to colleges for implementation College Project Managers need to account for additional college tasks | All Deployment Groups
4. | ctcLink Permanent Support Organization – A clear plan and understanding of the sizing, service capacity and service levels provided by SBCTC | SBCTC working on Service Level Agreements with colleges to structure the evolving ctcLink support plan Plan will need to include appropriate staffing levels for all deployments as well as post implementation | All Deployment Groups
Prepared for WACTC, April 25, 2019

## Slide 2: ctcLink executive leadership committee key messages for wACTC – april 26, 2019
TOPIC | KEY MESSAGES
Changes to Deployment Groups | ctcLink Steering Committee approved moving Shoreline from Deployment Group 5 to Deployment Group 6 ctcLink Governance to discuss risk of any more changes to deployment groups
Pre-Work | Later deployment groups can be working on this now: Legacy Business Process Documentation Local Governance Early planning for staffing needs (e.g., pre-hire backfill)
Planning Ahead for Implementation | High stress for employees Tight timelines must be met Need leadership support to free up staff to complete ctcLink activities on time
ctcLink – A People Project | ctcLink is a business transformation project Plan ahead to manage this monumental change