Legacy Transcript Project

**Report Date**: May 8, 2020 **Overall Project Health:**

# Timelines

Project duration – May 8 – Sept 23, 2020

Test Website: <https://devapps.sbctc.edu/LegacyTranscripts>

| Phases/Milestones | Start | End | % Complete |
| --- | --- | --- | --- |
| Sprint 1 – Setup and Student accounts | 4/20/20 | 5/6/20 | 100% |
| Sprint 2 – Staff portal and search | 5/7/20 | 5/22/20 | 10% |
| Sprint 3 – Transcript basic grid display | 5/26/20 | 6/9/20 | 0% |
| Sprint 4 – Staff edit and unofficial transcript | 6/10/20 | 7/1/20 | 0% |
| Sprint 5 – Transcript transmittal process | 7/2/20 | 7/23/20 | 0% |
| Sprint 6 – Official transcript printing | 7/24/20 | 8/14/20 | 0% |
| User Acceptance Testing (UAT) | 8/17/20 | 9/7/20 | 0% |
| Deployment Prep | 9/8/20 | 9/23/20 | 0% |

# Accomplishments

* Completed Sprint 1.
  + Database design
  + Sample data import
  + Website framework created
  + Website to database connections made
  + Student account and portal pages
  + Search functionality for student record
  + Social Security protection

# Current Activities

* Sprint 2 work underway
  + Query ctcLink for Staff login verification
  + Staff login page and portal
  + Administrator maintenance page
  + Student search screen
  + Student display/edit page
  + Initial transcript print research

# Outstanding Items

* New legislation for suppressing transcripts for punitive actions
  + If continues, discuss which actions prevent which transcript output
* Set next meeting with working group
  + Wording for not found student search – Next Steps
  + Demo Sprint 1 Student Access
  + Students with multiple SIDs in same school, search failures
  + Junk records – (missing names or marked with \*\*, etc)

# Risks

* None reported at this time.

# Issues

* None reported at this time.

Prepared David Coffman, SBCTC