## Major Project Report
OFFICE OF FINANCIAL MANAGEMENT
2025-27 Biennium
WASHINGTON STATE MAJOR PROJECT STATUS REPORT
December 2025
| Agency | 699
| Project Name | Grays Harbor College Student Services Instructional Building
| OFM Project Number(s) | 30000127
Contact Information
| Name | Floyd Plemmons
| Phone Number | 360-580-5173
| Email | floyd.plemmons@ghc.edu
Project Information
| Project Description: (Include a brief summary of the project and the programs it supports.) | The Student Services & Instructional Building (SSIB) is a replacement for our current student services building. In addition to replacing obsolescent space, it will consolidate student service programs that are dispersed among other buildings on campus, and provide instructional space for a culinary arts/hospitality program.
| Project Status: (Include scope or budget changes, phase updates, identified project delivery issues, discussion of critical path for construction and any potential for project cost overruns or claims.) | Closeout procedures for the building, including punch list and administrative work are currently ongoing, substantial completion was achieved 3/5/2024. There are currently 3 outstanding COPs under dispute, which if paid as presented by the GC, may result in exceeding the project budget. GHC is working with DES to resolve the outstanding disputes. The subcontractor responsible for all 3 of the COPs did not agree to a negotiated settlement. Mediation is scheduled for February 2025. Delays and disputed COPs are both the result of a permit delay in March 2022. The subcontractor responsible for all 3 of the COP’s did not agree to a negotiated settlement during the mediation held in February of 2025. The dispute is now scheduled for Arbitration in June of 2026.
Funding
All State & Local Sources, Project Transfers and Amounts
|  | Expenditures |  | Current Plan
| Phase & Fund Type | Prior Expended | 2025-27 Expended | 2025-27 Remaining | 2027-29 Plan | Future Plan | TOTAL | Notes
| Predesign | 0 | 0 | 0 | 0 | 0 | 0
| 057 - State Bldg. Const Acct | [5 empty] | 0
| XXX - Other State Funding | [5 empty] | 0
| Local Funds | [5 empty] | 0
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| Design | 4651000 | 0 | 0 | 0 | 0 | 4651000
| 057 - State Bldg. Const Acct | 4151000 |  |  |  |  | 4151000 | U88
| XXX - Other State Funding | 500000 |  |  |  |  | 500000 | N265
| Local Funds | [5 empty] | 0
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| Construction | 47222219 | 0 | 3781 | 0 | 0 | 47226000
| 057 - State Bldg. Const Acct | 44022219 |  | 3781 |  |  | 44026000 | C00
| XXX - Other State Funding | [5 empty] | 0
| Local Funds | 3200000 |  |  |  |  | 3200000 | Q583-COP
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| TOTALS | 51873219 | 0 | 3781 | 0 | 0 | 51877000
Details
| Construction Type | College classroom facilities |  | Project Administered By |  | College classroom facilities
| % of Bldg. Area that is being remodeled | 0% |  | Art Requirement Applies |  | 0%
| Procurement Method | Design-Bid-Build |  | Higher Ed Institution |  | Design-Bid-Build
Statistics
| Complete the table below with information from the cost estimate submitted with the predesign study, the cost estimate of the project as funded and the actual cost data to date or at completion. Explain any variances in the Notes column or below. |  |  | Estimate at Approved Predesign | Estimate of the Project as Currently Funded | Actuals to Date | Estimate as Currently Funded to Actuals Variance | Notes
| Gross Sq Ft (GSF) |  |  | 69985 | 69985 |  | -69985
| Usable Sq Ft (USF) |  |  | 45490 | 45490 |  | -45490
| Space Efficiency (USF/GSF %): |  |  | 65% | 65%
| Site Work SF: | [5 empty] | 0
| Demolition SF (provide building names in comments): |  |  | 35080 | 35080 |  | -35080
| MACC/Bid Award COST/GSF |  |  | 498.2614 | 573.4093
| Construction Subtotal COST/GSF (Includes change orders) |  |  | 569.9411 | 656.7622
Milestone Dates
| Predesign Complete |  |  | 2018-12-01 | 2019-12-01 | 2018-11-05 |  | OFM approved
| Start Design |  |  | 2019-01-01 | 2020-01-01 | 2018-11-06
| Bid Due Date |  |  |  |  | 2021-12-14 | 1463.5 mo.
| Notice to Proceed |  |  | 2020-04-01 | 2021-07-01 | 2022-01-25 | 7 mo.
| Substantial Completion |  |  | 2021-08-01 | 2022-10-01 | 2024-03-05 | 17 mo.
Final Acceptance/Project Close-out Date
Project Costs
| Complete the table below with information from the cost estimate submitted with the predesign study, the cost estimate of the project as funded and the actual cost data to date or at completion. Explain any variances in the Notes column or below. |  |  | Cost Estimate at Approved Predesign | Cost Estimate of the Project as Currently Funded | Actual Costs to Date | Estimate as Currently Funded to Actuals Variance | Notes
Acquisition
|  |  | Acquisition Costs Total |  |  |  | 0
Consultant Services
| Pre-Schematic Design Services |  |  | 447759 | 462974 | 472113 | 9139
| AE Basic Service Fee - Construction Documents |  |  | 1647664 | 1901671 | 1412997 | -488674
| Extra Services - Pre-Bid |  |  | 1722868 | 880996 | 1000720.15 | 119724.15
| AE Basic Service Fee - Bid/Construction/Closeout |  |  | 770897 | 835045.7726 | 614047 | -220998.7726
| Other Services - Post Bid |  |  | 700953 | 174285 | 179292 | 5007
| Design Services Contingency |  |  | 272442 | 213544 |  | -213544
|  |  | Consultant Services Total | 5562583 | 4468515.7726 | 3679169.15 | -789346.6226
Construction
| Site Work |  |  | 3270752 | 3561411 | 3375596 | -185815
| Related Project Costs | [5 empty] | 0
| Facility Construction |  |  | 31600075 | 36568636 | 36044600.65 | -524035.35
|  |  | Maximum Allowable Construction Cost (MACC) Subtotal | 34870827 | 40130047 | 39420196.65 | -709850.35
| Construction Contingencies |  |  | 1746569 | 2007375 | 1768016 | -239359
| Non-Taxable Items |  |  |  |  | 128463 | 128463 | bldg. permit
| Sales Tax |  |  | 3269934 | 3826078 | 3704083.08 | -121994.92
0
0
|  |  | Construction Contracts Total | 39887330 | 45963500 | 45020758.73 | -942741.27
Other Project Costs
| Equipment |  |  | 2769056 | 982761 | 953001.9 | -29759.1
| Art Work |  |  | 174354 | 258096 | 206685.7 | -51410.3
| Project Management |  |  | 204183 | 203862 | 108363.33 | -95498.67 | Campus PM
| Other Costs (describe) |  |  | 415975 |  |  | 0
|  |  | Other Project Costs Total | 3563568 | 1444719 | 1268050.93 | -176668.07
| Total Project Costs |  |  | 49013481 | 51876734.7726 | 49967978.81 | -1908755.9626
Additional comments:
Demolish Building 100 (UFI A00146) 22,643 gsf and building 200 (UFI A00079) 12,437 gsf.
Permit delay for NPDES stormwater has resulted in 3 disputed COPs that are currently scheduled for mediation in February 2025.
The SSIB is currently officially named tulalW Student Center by the Grays Harbor College Board of Trustees.
Wa Art was installed in May 2025.
NPDES stormwater disputed COPs are now scheduled for arbitration in February 2026.

## Photo Gallery (2)
Photo Gallery
Steel structure 12/2022
Overhead 12/22
HUB Demo 08/2022
HUB demo 08/2022
SIte 08/2022
Auger cast piles, grade beams 08/23

## Photo Gallery (3)
Photo Gallery
Side view 3/18/2024
Side view 3/18/2024
Student Services Center 3/1/2024
Student Services Center 3/1/2024
Overhead 4/1/2024
Front view 3/1/2024

## Photo Gallery (4)
Photo Gallery
Interior - Board Room 9/19/2024
Interior - Bookstore 9/19/2024
Interior - Student Life 9/19/2024
Side View 9/19/2024
Front View 9/19/2024
Interior - Event Center Lobby 9/19/2024
Interior - Culinary Classroom 9/19/2024
Side View 9/19/2024
Front View 9/19/2024
Interior - Event Center 9/19/2024

## Lists (hidden)
Construction Type | Y/N | PM Admin |  |  | Date | Type of Report
Apartment | Yes | DES | 2003-05 | Design-Bid-Build | Select Date from Dropdown | WASHINGTON STATE MAJOR PROJECT STATUS REPORT
Archive building | No | Agency | 2004 | GCCM | January 2026 | WASHINGTON STATE MAJOR PROJECT FINAL CLOSE-OUT REPORT
Armories |  | Other (explain below) | 2005-07 | Design-Build | February 2026
Art galleries |  |  | 2006 | Other (explain below) | March 2026
Auditorium with stage |  |  | 2007-09 |  | April 2026
Auditorium without stage |  |  | 2008 |  | May 2026
Civil Construction | Estimate at PD to Estimate as Funded Variance |  | 2009-11 |  | June 2026
College classroom facilities | Estimate at PD to Actuals Variance |  | 2010 |  | July 2026
Communications Building | Estimate as Currently Funded to Actuals Variance |  | 2011-13 |  | August 2026
Computer rooms |  |  | 2012 |  | September 2026
Convention facilities |  |  | 2013-15 |  | October 2026
Courthouses |  |  | 2014 |  | November 2026
Day care facilities |  |  | 2015-17 |  | December 2026
Detention/correctional facilities - maximum |  |  | 2016 |  | January 2027
Detention/correctional facilities - min & max |  |  | 2017-19 |  | February 2027
Dining halls/institute |  |  | 2018 |  | March 2027
Dormatories |  |  | 2019-21 |  | April 2027
Emergency generator facilities |  |  | 2020 |  | May 2027
Exposition building |  |  | 2021-23 |  | June 2027
Extended care facilities |  |  | 2022 |  | July 2027
Farm structures |  |  | 2023-25 |  | August 2027
Fire and police stations |  |  | 2024 |  | September 2027
Fish hatcheries |  |  |  |  | October 2027
Greenhouses |  |  |  |  | November 2027
Guard towers |  |  |  |  | December 2027
Gymnasiums
Heating and power plants
Hospitals
Industrial buildings without special facilities
Laboratories (Research)
Laundry and cleaning facilities
Libraries
Medical office and clinics
Mental Institutions
Museums
Neighborhood centers and similar recreation facilities
Nursing homes
Observatories
Office buildings
Parking structures and garages
Printing plants
Prototype facilities
Recreational building
Research Facilities
Residence
Schools (primary and secondary)
Science labs (teaching)
Service garages
Sewer treatment plants
Shop and maintenance facilities
Simple loft-type structures (w/o special equipment)
Special schools for physically disadvantaged
Stadium-grandstand type
Stadiums multi-purpose
Storage-cold
Theaters and similar facilities
Transportation terminals
Veterinary hospitals
Vocational schools
Warehouses
Water treatment plants
Other Sch. A Projects
Other Sch. B Projects
Other Sch. C Projects
Formulas:
Date = TEXT(DATE(YEAR(TODAY()), MONTH(TODAY())+ROWS(M2:[Date])-1, DAY(1)), "MMMM YYYY")