## Major Project Report
OFFICE OF FINANCIAL MANAGEMENT
2025-27 Biennium
WASHINGTON STATE MAJOR PROJECT FINAL CLOSE-OUT REPORT
December 2025
| Agency | 699
| Project Name | Shoreline College Allied Health, Science, and Manufacturing
| OFM Project Number(s) | 30000990
Contact Information
| Name | Kimberlee Clark
| Phone Number | 425-210-0534
| Email | kclark@shoreline.edu
Project Information
| Project Description: (Include a brief summary of the project and the programs it supports.) | Demolition of 2400, 2500, 2600, 2700, and 2800 buildings, to be replaced by one building. Approx. 51,600 sf will house chemistry, biology, MLT, manufacturing, general classrooms, and faculty offices.
| Project Status: (Include scope or budget changes, phase updates, identified project delivery issues, discussion of critical path for construction and any potential for project cost overruns or claims.) | The HSAMCC building is in full use. Al punch list items have been resolved. The second phase of HSAMCC consists of installation of the PV array, wayfinding signage, construction of the greenhouse and pond. The PV array and wayfinding signate has been completed. Forma is 75% complete with the greenhouse/pond/landscape. The Greenhouse/pond/landscape should be completed by Spring 2026.
Funding
All State & Local Sources, Project Transfers and Amounts
|  | Expenditures |  | Current Plan
| Phase & Fund Type | Prior Expended | 2025-27 Expended | 2025-27 Remaining | 2027-29 Plan | Future Plan | TOTAL | Notes
| Predesign | 0 | 0 | 0 | 0 | 0 | 0
| 057 - State Bldg. Const Acct | [5 empty] | 0
| XXX - Other State Funding | [5 empty] | 0
| Local Funds | [5 empty] | 0
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| Design | 3592000 | 0 | 0 | 0 | 0 | 3592000
| 057 - State Bldg. Const Acct | 3592000 |  |  |  |  | 3592000 | U81
| XXX - Other State Funding | [5 empty] | 0
| Local Funds | [5 empty] | 0
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| Construction | 46959671.15 | 0 | 3016329 | 0 | 0 | 49976000.15
| 057 - State Bldg. Const Acct | 42955000 |  | 893000 |  |  | 43848000 | C03
| XXX - Other State Funding | [5 empty] | 0
| 147 - Local Funds | 4004671.15 |  | 2123329 |  |  | 6128000.15 | P409/local/COP
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| TOTALS | 50551671.15 | 0 | 3016329 | 0 | 0 | 53568000.15
Details
| Construction Type | Science labs (teaching) |  | Project Administered By |  | DES
| % of Bldg. Area that is being remodeled | 0% |  | Art Requirement Applies |  | Yes
| Procurement Method | GCCM |  | Higher Ed Institution |  | Yes
Statistics
| Complete the table below with information from the cost estimate submitted with the predesign study, the cost estimate of the project as funded and the actual cost data to date or at completion. Explain any variances in the Notes column or below. |  |  | Estimate at Approved Predesign | Estimate of the Project as Currently Funded | Actuals at Final Completion | Estimate as Currently Funded to Actuals Variance | Notes
| Gross Sq Ft (GSF) |  |  | 69595 | 51600 | 51600 | 0
| Usable Sq Ft (USF) |  |  |  | 35088 | 35088 | 0
| Space Efficiency (USF/GSF %): |  |  | 0% | 68% | 68% | 0%
| Site Work SF: | [5 empty] | 0
| Demolition SF (provide building names in comments): |  |  | 46852 | 46852 | 46852 | 0 | See Notes
| MACC/Bid Award COST/GSF |  |  | 419.8741 | 588.1841 | 674.2769 | 86.0928
| Construction Subtotal COST/GSF (Includes change orders) |  |  | 485.0241 | 743.2876 | 760.9699 | 17.6823
Milestone Dates
| Predesign Complete |  |  | 2016-10-01 | 2016-10-01 | 2017-07-05 | 9 mo. | OFM approved
| Start Design |  |  | 2017-07-01 | 2018-05-01 | 2017-07-08
| Bid Due Date |  |  |  |  | 2021-04-09 | 1455.5 mo.
| Notice to Proceed |  |  | 2019-07-01 | 2021-07-01 | 2021-07-01 | 0 mo.
| Substantial Completion |  |  | 2020-12-01 | 2023-10-06 |  |  | Ph 1 10/6/23 & Ph 2 Fall of 2025
Final Acceptance/Project Close-out Date
Project Costs
| Complete the table below with information from the cost estimate submitted with the predesign study, the cost estimate of the project as funded and the actual cost data to date or at completion. Explain any variances in the Notes column or below. |  |  | Cost Estimate at Approved Predesign | Cost Estimate of the Project as Currently Funded | Actual Cost Data at Final Completion | Estimate as Currently Funded to Actuals Variance | Notes
Acquisition
|  |  | Acquisition Costs Total |  |  |  | 0
Consultant Services
| Pre-Schematic Design Services |  |  | 192633 | 192633 | 192633 | 0
| AE Basic Service Fee - Construction Documents |  |  | 1555051 | 1373665 | 1381291 | 7626 | Mithun
| Extra Services - Pre-Bid |  |  | 1633222 | 2396548 | 1936133 | -460415
| AE Basic Service Fee - Bid/Construction/Closeout |  |  | 663038 | 663418.3258 | 610379 | -53039.3258
| Other Services - Post Bid |  |  | 950810 | 1039329 | 351942 | -687387 | Includes Arch Amendments
| Design Services Contingency |  |  | 171959 | 968414 |  | -968414 | Costs are tracked in Other Services and should be Owner Consultant
|  |  | Consultant Services Total | 5166713 | 6634007.3258 | 4472378 | -2161629.3258
Construction
| Site Work |  |  | 4443349 |  |  | 0
| Related Project Costs | [5 empty] | 0
| Facility Construction |  |  | 24777788 | 30350301 | 34792690.09 | 4442389.09
|  |  | Maximum Allowable Construction Cost (MACC) Subtotal | 29221137 | 30350301 | 34792690.09 | 4442389.09
| Construction Contingencies |  |  | 1465457 | 1214012 | 491712 | -722300
| Non-Taxable Items | [5 empty] | 0
| Sales Tax |  |  | 3068660 | 3549974 | 3584624.17 | 34650.17
| GCCM Costs |  |  |  | 3239353 | 397022 | -2842331
| GCCM Risk Contingency | [5 empty] | 0
|  |  | Construction Contracts Total | 33755254 | 38353640 | 39266048.26 | 912408.26
Other Project Costs
| Equipment |  |  | 2814935 | 3635621 | 1801899 | -1833722
| Art Work |  |  | 146106 | 236655 | 236655 | 0
| Project Management |  |  | 177645 | 959645 | 915026 | -44619
| Other Costs (describe) |  |  | 457420 | 3748168 | 3221249 | -526919 | Traffic mitigation, permit, utility
|  |  | Other Project Costs Total | 3596106 | 8580089 | 6174829 | -2405260
| Total Project Costs |  |  | 42518073 | 53567736.3258 | 49913255.26 | -3654481.0658
Close-Out Information
NOTES
| Number of Change Orders | 79
| Total Value of Change Orders | 2812514.84
| Outstanding Liabilities | Unknown |  | Currently under audit review
| Unsettled Claims | None
Additional comments:
Demolish UFI A04825 = 1,500 gsf / UFI A06611 = 25,952 gsf / UFI A06410 = 5,820 gsf / UFI A09157 = 9,400 gsf / UFI A01606 = 4,180 gsf
Wa Arts Commission Dec 2025: Artist Andrea Wilbur-Sigo, art installed.

## Photo Gallery (2)
Photo Gallery
Brick on South side
Window framing on North side
Interior framing on 2nd floor

## Lists (hidden)
Construction Type | Y/N | PM Admin |  |  | Date | Type of Report
Apartment | Yes | DES | 2003-05 | Design-Bid-Build | Select Date from Dropdown | WASHINGTON STATE MAJOR PROJECT STATUS REPORT
Archive building | No | Agency | 2004 | GCCM | March 2026 | WASHINGTON STATE MAJOR PROJECT FINAL CLOSE-OUT REPORT
Armories |  | Other (explain below) | 2005-07 | Design-Build | April 2026
Art galleries |  |  | 2006 | Other (explain below) | May 2026
Auditorium with stage |  |  | 2007-09 |  | June 2026
Auditorium without stage |  |  | 2008 |  | July 2026
Civil Construction | Estimate at PD to Estimate as Funded Variance |  | 2009-11 |  | August 2026
College classroom facilities | Estimate at PD to Actuals Variance |  | 2010 |  | September 2026
Communications Building | Estimate as Currently Funded to Actuals Variance |  | 2011-13 |  | October 2026
Computer rooms |  |  | 2012 |  | November 2026
Convention facilities |  |  | 2013-15 |  | December 2026
Courthouses |  |  | 2014 |  | January 2027
Day care facilities |  |  | 2015-17 |  | February 2027
Detention/correctional facilities - maximum |  |  | 2016 |  | March 2027
Detention/correctional facilities - min & max |  |  | 2017-19 |  | April 2027
Dining halls/institute |  |  | 2018 |  | May 2027
Dormatories |  |  | 2019-21 |  | June 2027
Emergency generator facilities |  |  | 2020 |  | July 2027
Exposition building |  |  | 2021-23 |  | August 2027
Extended care facilities |  |  | 2022 |  | September 2027
Farm structures |  |  | 2023-25 |  | October 2027
Fire and police stations |  |  | 2024 |  | November 2027
Fish hatcheries |  |  |  |  | December 2027
Greenhouses |  |  |  |  | January 2028
Guard towers |  |  |  |  | February 2028
Gymnasiums
Heating and power plants
Hospitals
Industrial buildings without special facilities
Laboratories (Research)
Laundry and cleaning facilities
Libraries
Medical office and clinics
Mental Institutions
Museums
Neighborhood centers and similar recreation facilities
Nursing homes
Observatories
Office buildings
Parking structures and garages
Printing plants
Prototype facilities
Recreational building
Research Facilities
Residence
Schools (primary and secondary)
Science labs (teaching)
Service garages
Sewer treatment plants
Shop and maintenance facilities
Simple loft-type structures (w/o special equipment)
Special schools for physically disadvantaged
Stadium-grandstand type
Stadiums multi-purpose
Storage-cold
Theaters and similar facilities
Transportation terminals
Veterinary hospitals
Vocational schools
Warehouses
Water treatment plants
Other Sch. A Projects
Other Sch. B Projects
Other Sch. C Projects
Formulas:
Date = TEXT(DATE(YEAR(TODAY()), MONTH(TODAY())+ROWS(M2:[Date])-1, DAY(1)), "MMMM YYYY")