## Major Project Report
OFFICE OF FINANCIAL MANAGEMENT
2025-27 Biennium
WASHINGTON STATE MAJOR PROJECT STATUS REPORT
December 2025
| Agency | 699
| Project Name | Olympic College Innovation and Technology Learning
| OFM Project Number(s) | 40000103
Contact Information
| Name | Brent Palmason
| Phone Number | 360-475-7121
| Email | bpalmason@olympic.edu
Project Information
| Project Description: (Include a brief summary of the project and the programs it supports.) | The plan is for a 31,864 square foot innovation and technology center. A two story building designed to support 23 faculty/staff and 258 students at peak occupancy. The ITLC building will provide state of the art labs for computer information systems, computer science, cybersecurity, digital media arts and water flow research engineering programs. Included will be classrooms, labs, offices and support areas for students.
| Project Status: (Include scope or budget changes, phase updates, identified project delivery issues, discussion of critical path for construction and any potential for project cost overruns or claims.) | The project is in Construction Documents phase and floor plan layouts and programming have been locked in. Mechanical, electrical, plumbing and low voltage designs are complete through permit level and have incorporated the Owner's Project Requirements as prepared by McKinstry. Finish material and color selections are underway. We submitted for permit in December 2025 with an expected permit review time of 9 - 12 months. The project would bid in fall 2026 with construction start in late fall 2026. Construction is estimated at 18 months with occupancy in summer 2028. An art selection committee has been formed and will be starting work with the State Arts Commission in January 2026.
Funding
All State & Local Sources, Project Transfers and Amounts
|  | Expenditures |  | Current Plan
| Phase & Fund Type | Prior Expended | 2025-27 Expended | 2025-27 Remaining | 2027-29 Plan | Future Plan | TOTAL | Notes
| Predesign | 0 | 0 | 0 | 0 | 0 | 0
| 057 - State Bldgs. Const Acct | [5 empty] | 0
| XXX - Other State Funding | [5 empty] | 0
| Local Funds | [5 empty] | 0
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| Design | 1095573.11 | 247748 | 1200725 | 0 | 0 | 2544046.11
| 057 - State Bldgs. Const Acct | 1095573.11 | 342507.94 | 1113918.9 |  |  | 2551999.95 | A08
| XXX - Other State Funding | [5 empty] | 0
| Local Funds | [5 empty] | 0
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| Construction | 0 | 0 | 31054000 | 0 | 0 | 31054000
| 057 - State Bldgs. Const Acct |  |  | 31054000 |  |  | 31054000 | E00
| XXX - Other State Funding | [5 empty] | 0
| Local Funds | [5 empty] | 0
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| TOTALS | 1095573.11 | 247748 | 32254725 | 0 | 0 | 33598046.11
Details
| Construction Type | College classroom facilities |  | Project Administered By |  | DES
| % of Bldgs. Area that is being remodeled | 0% |  | Art Requirement Applies |  | Yes
| Procurement Method | Design-Bid-Build |  | Higher Ed Institution |  | Yes
Statistics
| Complete the table below with information from the cost estimate submitted with the predesign study, the cost estimate of the project as funded and the actual cost data to date or at completion. Explain any variances in the Notes column or below. |  |  | Estimate at Approved Predesign | Estimate of the Project as Currently Funded | Actuals to Date | Estimate as Currently Funded to Actuals Variance | Notes
| Gross Sq Ft (GSF) |  |  | 31864 | 31864 |  | -31864
| Usable Sq Ft (USF) |  |  | 20162 | 20162 |  | -20162
| Space Efficiency (USF/GSF %): |  |  | 63.28% | 63.28%
| Site Work SF: | [5 empty] | 0
| Demolition SF (provide building names in comments): | [5 empty] | 0
| MACC/Bid Award COST/GSF |  |  | 738.0319 | 738.0319
| Construction Subtotal COST/GSF (Includes change orders) |  |  | 738.0319 | 738.0319
Milestone Dates
| Predesign Complete |  |  | 2022-07-01 | 2022-07-01 | 2024-06-28 | 24 mo. | Variance due to hiring new architect and having to amend the original pre-design
| Start Design |  |  | 2022-11-01 | 2023-02-01 | 2023-02-01 | 0 mo.
| Bid Due Date |  |  |  | 2026-09-30
| Notice to Proceed |  |  | 2026-04-01 | 2026-11-01
| Substantial Completion |  |  | 2027-12-01 | 2028-03-31
| Final Acceptance/Project Close-out Date |  |  |  | 2028-06-01
Project Costs
| Complete the table below with information from the cost estimate submitted with the predesign study, the cost estimate of the project as funded and the actual cost data to date or at completion. Explain any variances in the Notes column or below. |  |  | Cost Estimate at Approved Predesign | Cost Estimate of the Project as Currently Funded | Actual Costs to Date | Estimate as Currently Funded to Actuals Variance | Notes
Acquisition
|  |  | Acquisition Costs Total |  |  |  | 0
Consultant Services
| Pre-Schematic Design Services |  |  | 211995 | 211995 | 193095 | -18900 | Miller Hull PDR
| AE Basic Service Fee - Construction Documents |  |  | 1192642 | 1192642 | 772164 | -420478 | Actual SWL billing
| Extra Services - Pre-Bid |  |  | 1900328 | 1900328 | 453633 | -1446695 | Actual SWL billing+McKinstry OPR+Roen & Associates VE
| AE Basic Service Fee - Bid/Construction/Closeout |  |  | 584745 | 584744.7 | 0 | -584744.7
| Other Services - Post Bid |  |  | 551107 | 551107.3 |  | -551107.3
| Design Services Contingency |  |  | 237128 | 237128 |  | -237128
|  |  | Consultant Services Total | 4677945 | 4677945 | 1418892 | -3259053
Construction
| Site Work |  |  | 3244262 | 3244262 |  | -3244262
| Related Project Costs |  |  | 0 | 0 |  | 0
| Facility Construction |  |  | 20272386 | 20272386 |  | -20272386
|  |  | Maximum Allowable Construction Cost (MACC) Subtotal | 23516648 | 23516648 | 0 | -23516648
| Construction Contingencies | [5 empty] | 0
| Non-Taxable Items | [5 empty] | 0
| Sales Tax | [5 empty] | 0
0
0
|  |  | Construction Contracts Total | 23516648 | 23516648 | 0 | -23516648
Other Project Costs
| Equipment |  |  | 2008872 | 2008872 |  | -2008872
| Art Work |  |  | 172060 | 171172 | 0 | -171172
| Project Management |  |  | 272825 | 272825 |  | -272825
| Other Costs (describe) |  |  | 483165 | 483165 | 283.95 | -482881.05
|  |  | Other Project Costs Total | 2936922 | 2936034 | 283.95 | -2935750.05
| Total Project Costs |  |  | 31131515 | 31130627 | 1419175.95 | -29711451.05
Additional comments:
Wa Arts Commission - Dec 2025 - Committee formation underway, 1st committee meeting expected Dec./early Jan.

## Photo Gallery
Photo Gallery
Construction document rendering from 15th & Lincoln
Aerial Perspective
1st floor plan
Maker space concept
Site plan
South Elevation
2nd Floor Corridor
2nd Floor Plan

## Lists (hidden)
Construction Type | Y/N | PM Admin |  |  | Date | Type of Report
Apartment | Yes | DES | 2003-05 | Design-Bid-Build | Select Date from Dropdown | WASHINGTON STATE MAJOR PROJECT STATUS REPORT
Archive building | No | Agency | 2004 | GCCM | January 2026 | WASHINGTON STATE MAJOR PROJECT FINAL CLOSE-OUT REPORT
Armories |  | Other (explain below) | 2005-07 | Design-Build | February 2026
Art galleries |  |  | 2006 | Other (explain below) | March 2026
Auditorium with stage |  |  | 2007-09 |  | April 2026
Auditorium without stage |  |  | 2008 |  | May 2026
Civil Construction | Estimate at PD to Estimate as Funded Variance |  | 2009-11 |  | June 2026
College classroom facilities | Estimate at PD to Actuals Variance |  | 2010 |  | July 2026
Communications Building | Estimate as Currently Funded to Actuals Variance |  | 2011-13 |  | August 2026
Computer rooms |  |  | 2012 |  | September 2026
Convention facilities |  |  | 2013-15 |  | October 2026
Courthouses |  |  | 2014 |  | November 2026
Day care facilities |  |  | 2015-17 |  | December 2026
Detention/correctional facilities - maximum |  |  | 2016 |  | January 2027
Detention/correctional facilities - min & max |  |  | 2017-19 |  | February 2027
Dining halls/institute |  |  | 2018 |  | March 2027
Dormatories |  |  | 2019-21 |  | April 2027
Emergency generator facilities |  |  | 2020 |  | May 2027
Exposition building |  |  | 2021-23 |  | June 2027
Extended care facilities |  |  | 2022 |  | July 2027
Farm structures |  |  | 2023-25 |  | August 2027
Fire and police stations |  |  | 2024 |  | September 2027
Fish hatcheries |  |  |  |  | October 2027
Greenhouses |  |  |  |  | November 2027
Guard towers |  |  |  |  | December 2027
Gymnasiums
Heating and power plants
Hospitals
Industrial buildings without special facilities
Laboratories (Research)
Laundry and cleaning facilities
Libraries
Medical office and clinics
Mental Institutions
Museums
Neighborhood centers and similar recreation facilities
Nursing homes
Observatories
Office buildings
Parking structures and garages
Printing plants
Prototype facilities
Recreational building
Research Facilities
Residence
Schools (primary and secondary)
Science labs (teaching)
Service garages
Sewer treatment plants
Shop and maintenance facilities
Simple loft-type structures (w/o special equipment)
Special schools for physically disadvantaged
Stadium-grandstand type
Stadiums multi-purpose
Storage-cold
Theaters and similar facilities
Transportation terminals
Veterinary hospitals
Vocational schools
Warehouses
Water treatment plants
Other Sch. A Projects
Other Sch. B Projects
Other Sch. C Projects
Formulas:
Date = TEXT(DATE(YEAR(TODAY()), MONTH(TODAY())+ROWS(M2:[Date])-1, DAY(1)), "MMMM YYYY")