## Major Project Report
OFFICE OF FINANCIAL MANAGEMENT
2025-27 Biennium
WASHINGTON STATE MAJOR PROJECT STATUS REPORT
December 2025
| Agency | 699
| Project Name | Whatcom Technology and Engineering Center
| OFM Project Number(s) | 40000137
Contact Information
| Name | Brian Keeley
| Phone Number | 360.383.3375
| Email | Bkeeley@shatcom.edu
Project Information
| Project Description: (Include a brief summary of the project and the programs it supports.) | The Technology and Engineering Center (TEC) will be a new building of approximately 52,000-gsf located on the north end of campus between Kulshan Hall and the Phyllis & Charles Self Learning Commons. The new TEC will provide programmed space for computer science, computer information systems, IT networking, cybersecurity, engineering, and tech-equipped instructional spaces to support community learning and basic education offerings. These will include program specific labs, technology rich classrooms, and general-purpose classrooms. The building will also include staff and faculty offices along with student-focused spaces such as collaborative learning labs and study locations. This project includes design and construction of a new building and related infrastructure using the GC/CM delivery method. The building programming may include purposefully designed lab spaces to meet the physical security requirements of a Sensitive Compartmentalized Information Facility (SCIF) as defined by National Security Agency (NSA).
| Project Status: (Include scope or budget changes, phase updates, identified project delivery issues, discussion of critical path for construction and any potential for project cost overruns or claims.) | The TEC is currently in the pre-design phase with Perkins & Will Architects to satisfy the OFM pre-design requirement. The pre-design effort is scheduled for completion in mid-December, 2025. The GC/CM selection process is currently in progress and a contract for pre-construction services is anticipated for mid January, 2026.
Funding
All State & Local Sources, Project Transfers and Amounts
|  | Expenditures |  | Current Plan
| Phase & Fund Type | Prior Expended | 2025-27 Expended | 2025-27 Remaining | 2027-29 Plan | Future Plan | TOTAL | Notes
| Predesign | 0 | 0 | 0 | 0 | 0 | 0
| 057 - State Bldgs. Const Acct | [5 empty] | 0
| XXX - Other State Funding | [5 empty] | 0
| Local Funds | [5 empty] | 0
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| Design | 0 | 152420.03 | 2579244.07 | 48310335.9 | 0 | 51042000
| 057 - State Bldgs. Const Acct |  | 152420.03 | 2579244.07 | 48310335.9 |  | 51042000 | E03
| XXX - Other State Funding | [5 empty] | 0
| Local Funds | [5 empty] | 0
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| Construction | 0 | 0 | 0 | 0 | 0 | 0
| 057 - State Bldgs. Const Acct | [5 empty] | 0
| XXX - Other State Funding | [5 empty] | 0
| Local Funds | [5 empty] | 0
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| TOTALS | 0 | 152420.03 | 2579244.07 | 48310335.9 | 0 | 51042000
Details
| Construction Type | College classroom facilities |  | Project Administered By |  | DES
| % of Bldgs. Area that is being remodeled | 0% |  | Art Requirement Applies |  | Yes
| Procurement Method | GCCM |  | Higher Ed Institution |  | Yes
Statistics
| Complete the table below with information from the cost estimate submitted with the predesign study, the cost estimate of the project as funded and the actual cost data to date or at completion. Explain any variances in the Notes column or below. |  |  | Estimate at Approved Predesign | Estimate of the Project as Currently Funded | Actuals to Date | Estimate as Currently Funded to Actuals Variance | Notes
| Gross Sq Ft (GSF) |  |  | 52000 | 52000 | 52076 | 76
| Usable Sq Ft (USF) |  |  | 35845 | 35845 | 33261 | -2584
| Space Efficiency (USF/GSF %): |  |  | 68.93% | 68.93% | 63.87% | -5.063%
| Site Work SF: | [5 empty] | 0
| Demolition SF (provide building names in comments): | [5 empty] | 0
| MACC/Bid Award COST/GSF |  |  | 671.3749 | 671.3749 | 0 | -671.3749
| Construction Subtotal COST/GSF (Includes change orders) |  |  | 768.4381 | 768.4381 | 0 | -768.4381
Milestone Dates
| Predesign Complete |  |  | 2025-12-01 | 2025-12-19 |  |  | Draft predesign completed and in review with WCC
| Start Design |  |  | 2025-12-01 | 2025-12-20
| Bid Due Date |  |  | 2027-06-30 | 2027-06-30
| Notice to Proceed |  |  | 2027-07-01 | 2027-07-01
| Substantial Completion |  |  | 2028-12-01 | 2028-12-01
Final Acceptance/Project Close-out Date
Project Costs
| Complete the table below with information from the cost estimate submitted with the predesign study, the cost estimate of the project as funded and the actual cost data to date or at completion. Explain any variances in the Notes column or below. |  |  | Cost Estimate at Approved Predesign | Cost Estimate of the Project as Currently Funded | Actual Costs to Date | Estimate as Currently Funded to Actuals Variance | Notes
Acquisition
|  |  | Acquisition Costs Total |  |  |  | 0
Consultant Services
| Pre-Schematic Design Services |  |  | 394364 | 394364 | 152981.28 | -241382.72
| AE Basic Service Fee - Construction Documents |  |  | 1769647 | 1769647 |  | -1769647
| Extra Services - Pre-Bid |  |  | 2204282 | 2204282 |  | -2204282
| AE Basic Service Fee - Bid/Construction/Closeout |  |  | 2159829 | 2159829 |  | -2159829
| Other Services - Post Bid | [5 empty] | 0
| Design Services Contingency |  |  | 337691 | 337691 |  | -337691
|  |  | Consultant Services Total | 6865813 | 6865813 | 152981.28 | -6712831.72
Construction
| Site Work |  |  | 1988777 | 1988777 |  | -1988777
| Related Project Costs |  |  | 0 | 0 |  | 0
| Facility Construction |  |  | 32922720 | 32922720 |  | -32922720
|  |  | Maximum Allowable Construction Cost (MACC) Subtotal | 34911497 | 34911497 | 0 | -34911497
| Construction Contingencies |  |  | 1747884 | 1747884 |  | -1747884
| Non-Taxable Items |  |  | 0 | 0 |  | 0
| Sales Tax |  |  | 3299402 | 3299402 |  | -3299402
| GCCM Costs | [5 empty] | 0
| GCCM Risk Contingency | [5 empty] | 0
|  |  | Construction Contracts Total | 39958783 | 39958783 | 0 | -39958783
Other Project Costs
| Equipment |  |  | 2945679 | 2945679 |  | -2945679
| Art Work |  |  | 253941 | 253941 |  | -253941
| Project Management |  |  | 449995 | 449995 |  | -449995
| Other Costs (describe) |  |  | 567789 | 567789 |  | -567789
|  |  | Other Project Costs Total | 4217404 | 4217404 | 0 | -4217404
| Total Project Costs |  |  | 51042000 | 51042000 | 152981.28 | -50889018.72
Additional comments:
The project is progressing on schedule with the draft pre-design document in review and the GC/CM selection process underway.
Wa Arts Commission - Dec 2025 - Meeting with committee chair in December. First committee meeting expected for January 2026.

## Photo Gallery
Photo Gallery
Right-click on picture above to change picture to photos of the project.
Right-click on picture above to change picture to photos of the project.
Updated Program Tabulation
Building Shape and Program Test Fits

## Lists (hidden)
Construction Type | Y/N | PM Admin |  |  | Date | Type of Report
Apartment | Yes | DES | 2003-05 | Design-Bid-Build | Select Date from Dropdown | WASHINGTON STATE MAJOR PROJECT STATUS REPORT
Archive building | No | Agency | 2004 | GCCM | January 2026 | WASHINGTON STATE MAJOR PROJECT FINAL CLOSE-OUT REPORT
Armories |  | Other (explain below) | 2005-07 | Design-Build | February 2026
Art galleries |  |  | 2006 | Other (explain below) | March 2026
Auditorium with stage |  |  | 2007-09 |  | April 2026
Auditorium without stage |  |  | 2008 |  | May 2026
Civil Construction | Estimate at PD to Estimate as Funded Variance |  | 2009-11 |  | June 2026
College classroom facilities | Estimate at PD to Actuals Variance |  | 2010 |  | July 2026
Communications Building | Estimate as Currently Funded to Actuals Variance |  | 2011-13 |  | August 2026
Computer rooms |  |  | 2012 |  | September 2026
Convention facilities |  |  | 2013-15 |  | October 2026
Courthouses |  |  | 2014 |  | November 2026
Day care facilities |  |  | 2015-17 |  | December 2026
Detention/correctional facilities - maximum |  |  | 2016 |  | January 2027
Detention/correctional facilities - min & max |  |  | 2017-19 |  | February 2027
Dining halls/institute |  |  | 2018 |  | March 2027
Dormatories |  |  | 2019-21 |  | April 2027
Emergency generator facilities |  |  | 2020 |  | May 2027
Exposition building |  |  | 2021-23 |  | June 2027
Extended care facilities |  |  | 2022 |  | July 2027
Farm structures |  |  | 2023-25 |  | August 2027
Fire and police stations |  |  | 2024 |  | September 2027
Fish hatcheries |  |  |  |  | October 2027
Greenhouses |  |  |  |  | November 2027
Guard towers |  |  |  |  | December 2027
Gymnasiums
Heating and power plants
Hospitals
Industrial buildings without special facilities
Laboratories (Research)
Laundry and cleaning facilities
Libraries
Medical office and clinics
Mental Institutions
Museums
Neighborhood centers and similar recreation facilities
Nursing homes
Observatories
Office buildings
Parking structures and garages
Printing plants
Prototype facilities
Recreational building
Research Facilities
Residence
Schools (primary and secondary)
Science labs (teaching)
Service garages
Sewer treatment plants
Shop and maintenance facilities
Simple loft-type structures (w/o special equipment)
Special schools for physically disadvantaged
Stadium-grandstand type
Stadiums multi-purpose
Storage-cold
Theaters and similar facilities
Transportation terminals
Veterinary hospitals
Vocational schools
Warehouses
Water treatment plants
Other Sch. A Projects
Other Sch. B Projects
Other Sch. C Projects
Formulas:
Date = TEXT(DATE(YEAR(TODAY()), MONTH(TODAY())+ROWS(M2:[Date])-1, DAY(1)), "MMMM YYYY")