## Major Project Report
OFFICE OF FINANCIAL MANAGEMENT
2025-27 Biennium
WASHINGTON STATE MAJOR PROJECT STATUS REPORT
December 2025
| Agency | 699
| Project Name | Bellevue College Center for Transdisciplinary Learning
| OFM Project Number(s) | 40000168
Contact Information
| Name | Christopher Butler
| Phone Number | 425-564-2473
| Email | christopher.butler@bellevuecollege.edu
Project Information
| Project Description: (Include a brief summary of the project and the programs it supports.) | The W Building brings together Arts, Digital Media Art, and aligned disciplines all designed around a common "maker space" that will enable the college to carry out its mission of innovation through transdisciplinary education that leads to excellence.
| Project Status: (Include scope or budget changes, phase updates, identified project delivery issues, discussion of critical path for construction and any potential for project cost overruns or claims.) | Bid set and specifications were complete November 4, 2024. Invitation to bid was published on November 14, 2024 with bids due January 14, 2025. Site walks with potential bidders were scheduled on December 4 and December 17, 2024. The building permit is expected to be received by mid-May 2025. Because the contractor will already be engaged, demolition would begin soon after the building permit is released. Ribbon-cutting is scheduled on May 15, 2025. UPDATE June 10,2025: Ground breaking ceremony held on May 15, 2025. Permits received and demolition of greenhouse completed and demolition of existing building started. UPDATE: December 22, 2025: Last concrete pour for NE 2nd floor roof happening early January. Building is being dried in with temporary roof to aid interior wall framing and HVAC & Electrical installation
Funding
All State & Local Sources, Project Transfers and Amounts
|  | Expenditures |  | Current Plan
| Phase & Fund Type | Prior Expended | 2025-27 Expended | 2025-27 Remaining | 2027-29 Plan | Future Plan | TOTAL | Notes
| Predesign | 0 | 0 | 0 | 0 | 0 | 0
| 057 - State Bldgs. Const Acct | [5 empty] | 0
| XXX - Other State Funding | [5 empty] | 0
| Local Funds | [5 empty] | 0
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| Design | 1476155 | 0 | 0 | 0 | 0 | 1476155
| 057 - State Bldgs. Const Acct | 1476155 |  |  |  |  | 1476155 | A11 moved bal to C14
| XXX - Other State Funding | [5 empty] | 0
| Local Funds | [5 empty] | 0
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| Construction | 10247460.47 | 7972352.5 | 35085031.64 | 0 | 0 | 53304844.61
| 057 - State Bldgs. Const Acct | 5926618.25 | 7926074.36 | 27452152 |  |  | 41304844.61 | C14, incl. reapprop A11
| 26V - Other State Funding | 2000000 |  |  |  |  | 2000000 | D26
| 147 - Local Funds | 2320842.22 | 46278.14 | 7632879.64 |  |  | 10000000 | R641
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| TOTALS | 11723615.47 | 7972352.5 | 35085031.64 | 0 | 0 | 54780999.61
Details
| Construction Type | College classroom facilities |  | Project Administered By |  | DES
| % of Bldgs. Area that is being remodeled |  |  | Art Requirement Applies |  | Yes
| Procurement Method | Design-Bid-Build |  | Higher Ed Institution |  | Yes
Statistics
| Complete the table below with information from the cost estimate submitted with the predesign study, the cost estimate of the project as funded and the actual cost data to date or at completion. Explain any variances in the Notes column or below. |  |  | Estimate at Approved Predesign | Estimate of the Project as Currently Funded | Actuals to Date | Estimate as Currently Funded to Actuals Variance | Notes
| Gross Sq Ft (GSF) |  |  | 52187 | 57630 |  | -57630
| Usable Sq Ft (USF) |  |  | 44359 | 46588 |  | -46588
| Space Efficiency (USF/GSF %): |  |  | 85% | 80.84%
| Site Work SF: | [5 empty] | 0
| Demolition SF (provide building names in comments): |  |  | 2897 | 2897 |  | -2897 | F Building, & ??
| MACC/Bid Award COST/GSF |  |  | 584.5702 | 669.9209
| Construction Subtotal COST/GSF (Includes change orders) |  |  | 675.8308 | 780.2221
Milestone Dates
| Predesign Complete |  |  | 2020-09-01 | 2020-09-01 | 2020-09-01 | 0 mo.
| Start Design |  |  | 2021-07-01 | 2022-11-01 | 2022-11-01 | 0 mo.
| Bid Due Date |  |  | 2024-07-26 | 2025-01-14 | 2025-01-14 | 0 mo.
| Notice to Proceed |  |  | 2022-02-01 | 2025-02-12 | 2025-04-14 | 2 mo. | June 5, 2025 UPDATE: DES issued notice to proceed for April 14, 2025.
| Substantial Completion |  |  | 2023-06-01 | 2026-07-31 | 2026-10-01 | 2 mo. | June 5, 2025 UPDATE: Substantial completion anticipated October 2026 instead of 9/11/2026.
| Final Acceptance/Project Close-out Date |  |  | 2023-08-11 | 2026-09-11
Project Costs
| Complete the table below with information from the cost estimate submitted with the predesign study, the cost estimate of the project as funded and the actual cost data to date or at completion. Explain any variances in the Notes column or below. |  |  | Cost Estimate at Approved Predesign | Cost Estimate of the Project as Currently Funded | Actual Costs to Date | Estimate as Currently Funded to Actuals Variance | Notes
Acquisition
|  |  | Acquisition Costs Total |  |  |  | 0
Consultant Services
| Pre-Schematic Design Services |  |  | 434934 | 206392 | 439669 | 233277 | P&W Pre. Mithun Validation Study
| AE Basic Service Fee - Construction Documents |  |  | 1456061 | 2312301 | 4183164.69 | 1870863.69 | 1) Overage due to $774,783.45 paid to Clark/LMN when project was abandoned. 2) See Amendment #4 re. max basic service adjustment from the PDB
| Extra Services - Pre-Bid |  |  | 1130769 | 1357577 |  | -1357577 | ESR 1 -8
| AE Basic Service Fee - Bid/Construction/Closeout |  |  | 679029.63 | 1886155.3982 |  | -1886155.3982
| Other Services - Post Bid |  |  | 850770 |  | 363089 | 363089 | special inspections
| Design Services Contingency |  |  | 182429 | 787975.5398 |  | -787975.5398
|  |  | Consultant Services Total | 4733992.63 | 6550400.938 | 4985922.69 | -1564478.248
Construction
| Site Work |  |  | 1838007 | 2554458 | 2500000 | -54458
| Related Project Costs |  |  |  |  | 853037 | 853037 | DB Contractor (Clark Const)
| Facility Construction |  |  | 28668958 | 36053085 | 9584125.37 | -26468959.63
|  |  | Maximum Allowable Construction Cost (MACC) Subtotal | 30506965 | 38607543 | 12937162.37 | -25670380.63
| Construction Contingencies |  |  | 1527169 | 2995597.2435 |  | -2995597.2435
| Non-Taxable Items | [5 empty] | 0 | WSST in "Other"
| Sales Tax |  |  | 3235448 | 3361060.1072 | 1232580.79 | -2128479.3172
0
0
|  |  | Construction Contracts Total | 35269582 | 44964200.3507 | 14169743.16 | -30794457.1907
Other Project Costs
| Equipment |  |  | 1612045 | 1788183.442 |  | -1788183.442
| Art Work |  |  | 212840 | 212843 | 49526.45 | -163316.55
| Project Management |  |  | 88385 | 80716 | 175000 | 94284 | Onsite PM
| Other Costs (describe) |  |  | 1226971 | 1423849.8 | 345298 | -1078551.8 | Additional Comments
|  |  | Other Project Costs Total | 3140241 | 3505592.242 | 569824.45 | -2935767.792
| Total Project Costs |  |  | 43143815.63 | 55020193.5307 | 19725490.3 | -35294703.2307
Additional comments:
Other Costs include design and construction Sales Tax, Owner Contingency, PDB Honorarium, Permitting and City Transportation impact fee.
WA Arts Commission December 2025. Artist selected (Arnette Jannotta) project in fabrication.
Additional Other Cost of Forma Construction Utility potholing inspection of below-ground infrastructure layout and routing and building move out JOC $345,299
Note on C52: Susan Locke: Partial renovation of A02990.
Note on E61: Susan Locke: demolish A06673 and A20104.
Note on I61: Susan Locke: demolish A06673 and A20104.

## Photo Gallery (early demo)
Photo Gallery

## Photo Gallery (Summer25)
Photo Gallery

## Photo Gallery (Fall25)
Photo Gallery

## Photo Gallery (Winter25)
Photo Gallery
Note: Add alternative text to the photos after the stock photo is changed:
1. Right click with mouse on photo, 2. Select "View Alternative Text" from menu, 3. Write brief description of photo details (white field in right Alt Text pane). 4. Repeat for each photo.
Arial View 11/03/2025
New Concrete slab poured
New second floor PT (Post Tensioned) Slab
Interior of second floor with roof slab supports
Exterior Framing being installed
First Floor interior framing and ductwork being installed

## Lists (hidden)
Construction Type | Y/N | PM Admin |  |  | Date | Type of Report
Apartment | Yes | DES | 2003-05 | Design-Bid-Build | Select Date from Dropdown | WASHINGTON STATE MAJOR PROJECT STATUS REPORT
Archive building | No | Agency | 2004 | GCCM | January 2026 | WASHINGTON STATE MAJOR PROJECT FINAL CLOSE-OUT REPORT
Armories |  | Other (explain below) | 2005-07 | Design-Build | February 2026
Art galleries |  |  | 2006 | Other (explain below) | March 2026
Auditorium with stage |  |  | 2007-09 |  | April 2026
Auditorium without stage |  |  | 2008 |  | May 2026
Civil Construction | Estimate at PD to Estimate as Funded Variance |  | 2009-11 |  | June 2026
College classroom facilities | Estimate at PD to Actuals Variance |  | 2010 |  | July 2026
Communications Building | Estimate as Currently Funded to Actuals Variance |  | 2011-13 |  | August 2026
Computer rooms |  |  | 2012 |  | September 2026
Convention facilities |  |  | 2013-15 |  | October 2026
Courthouses |  |  | 2014 |  | November 2026
Day care facilities |  |  | 2015-17 |  | December 2026
Detention/correctional facilities - maximum |  |  | 2016 |  | January 2027
Detention/correctional facilities - min & max |  |  | 2017-19 |  | February 2027
Dining halls/institute |  |  | 2018 |  | March 2027
Dormatories |  |  | 2019-21 |  | April 2027
Emergency generator facilities |  |  | 2020 |  | May 2027
Exposition building |  |  | 2021-23 |  | June 2027
Extended care facilities |  |  | 2022 |  | July 2027
Farm structures |  |  | 2023-25 |  | August 2027
Fire and police stations |  |  | 2024 |  | September 2027
Fish hatcheries |  |  |  |  | October 2027
Greenhouses |  |  |  |  | November 2027
Guard towers |  |  |  |  | December 2027
Gymnasiums
Heating and power plants
Hospitals
Industrial buildings without special facilities
Laboratories (Research)
Laundry and cleaning facilities
Libraries
Medical office and clinics
Mental Institutions
Museums
Neighborhood centers and similar recreation facilities
Nursing homes
Observatories
Office buildings
Parking structures and garages
Printing plants
Prototype facilities
Recreational building
Research Facilities
Residence
Schools (primary and secondary)
Science labs (teaching)
Service garages
Sewer treatment plants
Shop and maintenance facilities
Simple loft-type structures (w/o special equipment)
Special schools for physically disadvantaged
Stadium-grandstand type
Stadiums multi-purpose
Storage-cold
Theaters and similar facilities
Transportation terminals
Veterinary hospitals
Vocational schools
Warehouses
Water treatment plants
Other Sch. A Projects
Other Sch. B Projects
Other Sch. C Projects
Formulas:
Date = TEXT(DATE(YEAR(TODAY()), MONTH(TODAY())+ROWS(M2:[Date])-1, DAY(1)), "MMMM YYYY")