## Major Project Report
OFFICE OF FINANCIAL MANAGEMENT
2025-27 Biennium
WASHINGTON STATE MAJOR PROJECT STATUS REPORT
December 2025
| Agency | 699
| Project Name | Wenatchee Valley College Center for Technical Education and Innovation
| OFM Project Number(s) | 40000198
Contact Information
| Name | Rich Peters
| Phone Number | 509-682-6465
| Email | rpeters@wvc.edu
Project Information
| Project Description: (Include a brief summary of the project and the programs it supports.) | This project is for the engineering and design of a new 70,000 sq ft building to replace portions of Batjer (Automotive, Ag, Natural Resources, Machine, Mechatronics), Industrial Technology/Welding and Refrigeration with a modern state-of-the-art technical education learning facility.
| Project Status: (Include scope or budget changes, phase updates, identified project delivery issues, discussion of critical path for construction and any potential for project cost overruns or claims.) | The CMU block work is scheduled to be complete the first full week in January. Over ninety percent of the structural steel has been installed. The remaining exterior pre-cast panels will be installed at the Automotive area early in January. Roofing materials are on site and roofing work has begun on the north side of the building. Excessive rain and wind have made work difficult. If extreme weather conditions continue, the Contractor may be requesting some additional time to complete the project. There were some CMU prism breaks that did not meet the specified requirements. Additional testing is being done to ensure that the CMU walls meet the specifications.
Funding
All State & Local Sources, Project Transfers and Amounts
|  | Expenditures |  | Current Plan
| Phase & Fund Type | Prior Expended | 2025-27 Expended | 2025-27 Remaining | 2027-29 Plan | Future Plan | TOTAL | Notes
| Predesign | 0 | 0 | 0 | 0 | 0 | 0
| 057 - State Bldgs. Const Acct | [5 empty] | 0
| XXX - Other State Funding | [5 empty] | 0
| Local Funds | [5 empty] | 0
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| Design | 3243696.31 | 0 | 0 | 0 | 0 | 3243696.31
| 057 - State Bldgs. Const Acct | 3243696.31 |  |  |  |  | 3243696.31 | C07, remain w/D04 in BI2527
| XXX - Other State Funding | [5 empty] | 0
| Local Funds | [5 empty] | 0
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| Construction | 4437556.37 | 12910362.89 | 28440674.74 | 2420365 | 4000000 | 52208959
| 057 - State Bldgs. Const Acct | 4437556.37 | 12910362.89 | 28440674.74 | 2420365 |  | 48208959 | D04, incl. C07 reapprop in BI2527
| XXX - Other State Funding | [5 empty] | 0
| 147 - Local Funds |  |  |  |  | 700000 | 700000 | R772
| 147 - Local Funds |  |  |  |  | 3300000 | 3300000 | R870
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| TOTALS | 7681252.68 | 12910362.89 | 28440674.74 | 2420365 | 4000000 | 55452655.31
Details
| Construction Type | Vocational schools |  | Project Administered By |  | DES
| % of Bldgs. Area that is being remodeled | 0% |  | Art Requirement Applies |  | Yes
| Procurement Method | Design-Bid-Build |  | Higher Ed Institution |  | Yes
Statistics
| Complete the table below with information from the cost estimate submitted with the predesign study, the cost estimate of the project as funded and the actual cost data to date or at completion. Explain any variances in the Notes column or below. |  |  | Estimate at Approved Predesign | Estimate of the Project as Currently Funded | Actuals to Date | Estimate as Currently Funded to Actuals Variance | Notes
| Gross Sq Ft (GSF) |  |  | 69980 | 61085 |  | -61085
| Usable Sq Ft (USF) |  |  | 54190 | 44722 |  | -44722
| Space Efficiency (USF/GSF %): |  |  | 77.44% | 73.21%
| Site Work SF: | [5 empty] | 0
| Demolition SF (provide building names in comments): |  |  | 53596 | 53596 |  | -53596 | See Comments
| MACC/Bid Award COST/GSF |  |  | 499.2172 | 730.8854
| Construction Subtotal COST/GSF (Includes change orders) |  |  | 569.3137 | 825.596
Milestone Dates
| Predesign Complete |  |  | 2022-06-01 | 2022-06-01 | 2022-08-11 | 2.5 mo.
| Start Design |  |  | 2022-07-01 | 2022-07-01 | 2025-08-18 | 37.5 mo.
| Bid Due Date |  |  | 2024-04-30 | 2024-04-30 | 2024-10-29 | 6 mo.
| Notice to Proceed |  |  |  | 2025-03-03 | 2025-03-03 | 0 mo.
| Substantial Completion |  |  |  | 2027-06-24
| Final Acceptance/Project Close-out Date |  |  |  | 2027-07-27
Project Costs
| Complete the table below with information from the cost estimate submitted with the predesign study, the cost estimate of the project as funded and the actual cost data to date or at completion. Explain any variances in the Notes column or below. |  |  | Cost Estimate at Approved Predesign | Cost Estimate of the Project as Currently Funded | Actual Costs to Date | Estimate as Currently Funded to Actuals Variance | Notes
Acquisition
|  |  | Acquisition Costs Total |  |  |  | 0
Consultant Services
| Pre-Schematic Design Services |  |  | 428647 | 306710 | 306709.68 | -0.32 | RGU Architect.
| AE Basic Service Fee - Construction Documents |  |  | 1847717 | 2126551 | 1742933.42 | -383617.58 | RGU Architect.
| Extra Services - Pre-Bid |  |  | 1160115 | 1416470 | 1498166.06 | 81696.06 | Multiple
| AE Basic Service Fee - Bid/Construction/Closeout |  |  | 758906.9312 | 912450 | 316376.31 | -596073.69
| Other Services - Post Bid |  |  | 331231 |  | 92581.3 | 92581.3
| Design Services Contingency |  |  | 232917 |  |  | 0
|  |  | Consultant Services Total | 4759533.9312 | 4762181 | 3956766.77 | -805414.23
Construction
| Site Work |  |  | 3234398 |  | 1281170.28 | 1281170.28
| Related Project Costs |  |  | 436874 |  |  | 0
| Facility Construction |  |  | 31263951 | 44646135 | 13892969.85 | -30753165.15
|  |  | Maximum Allowable Construction Cost (MACC) Subtotal | 34935223 | 44646135 | 15174140.13 | -29471994.87
| Construction Contingencies |  |  | 1750384 | 1706376 |  | -1706376
| Non-Taxable Items | [5 empty] | 0
| Sales Tax |  |  | 3154963 | 4079021 | 1318998.76 | -2760022.24
0
0
|  |  | Construction Contracts Total | 39840570 | 50431532 | 16493138.89 | -33938393.11
Other Project Costs
| Equipment |  |  | 0 | 0 |  | 0
| Art Work |  |  | 223001 | 247446 | 0 | -247446
| Project Management |  |  |  | 0 |  | 0
| Other Costs (describe) |  |  |  | 11800 | 141709.91 | 129909.91 | Permits, RFP adv
|  |  | Other Project Costs Total | 223001 | 259246 | 141709.91 | -117536.09
| Total Project Costs |  |  | 44823104.9312 | 55452959 | 20591615.57 | -34861343.43
Additional comments:
Wa Arts Commission: Dec 2025 - initiation stage.
Note on I82: Maxwell, Debra: Hazardous Materials Survey, Geotechnical Engineering, Commissioning / Building Envelope Testing; RGU additional services

## Photo Gallery (2)
Photo Gallery
CTEI project - rendering 6-23
June 2025
June 2025
December 2025

## Lists (hidden)
Construction Type | Y/N | PM Admin |  |  | Date | Type of Report
Apartment | Yes | DES | 2003-05 | Design-Bid-Build | Select Date from Dropdown | WASHINGTON STATE MAJOR PROJECT STATUS REPORT
Archive building | No | Agency | 2004 | GCCM | January 2026 | WASHINGTON STATE MAJOR PROJECT FINAL CLOSE-OUT REPORT
Armories |  | Other (explain below) | 2005-07 | Design-Build | February 2026
Art galleries |  |  | 2006 | Other (explain below) | March 2026
Auditorium with stage |  |  | 2007-09 |  | April 2026
Auditorium without stage |  |  | 2008 |  | May 2026
Civil Construction | Estimate at PD to Estimate as Funded Variance |  | 2009-11 |  | June 2026
College classroom facilities | Estimate at PD to Actuals Variance |  | 2010 |  | July 2026
Communications Building | Estimate as Currently Funded to Actuals Variance |  | 2011-13 |  | August 2026
Computer rooms |  |  | 2012 |  | September 2026
Convention facilities |  |  | 2013-15 |  | October 2026
Courthouses |  |  | 2014 |  | November 2026
Day care facilities |  |  | 2015-17 |  | December 2026
Detention/correctional facilities - maximum |  |  | 2016 |  | January 2027
Detention/correctional facilities - min & max |  |  | 2017-19 |  | February 2027
Dining halls/institute |  |  | 2018 |  | March 2027
Dormatories |  |  | 2019-21 |  | April 2027
Emergency generator facilities |  |  | 2020 |  | May 2027
Exposition building |  |  | 2021-23 |  | June 2027
Extended care facilities |  |  | 2022 |  | July 2027
Farm structures |  |  | 2023-25 |  | August 2027
Fire and police stations |  |  | 2024 |  | September 2027
Fish hatcheries |  |  |  |  | October 2027
Greenhouses |  |  |  |  | November 2027
Guard towers |  |  |  |  | December 2027
Gymnasiums
Heating and power plants
Hospitals
Industrial buildings without special facilities
Laboratories (Research)
Laundry and cleaning facilities
Libraries
Medical office and clinics
Mental Institutions
Museums
Neighborhood centers and similar recreation facilities
Nursing homes
Observatories
Office buildings
Parking structures and garages
Printing plants
Prototype facilities
Recreational building
Research Facilities
Residence
Schools (primary and secondary)
Science labs (teaching)
Service garages
Sewer treatment plants
Shop and maintenance facilities
Simple loft-type structures (w/o special equipment)
Special schools for physically disadvantaged
Stadium-grandstand type
Stadiums multi-purpose
Storage-cold
Theaters and similar facilities
Transportation terminals
Veterinary hospitals
Vocational schools
Warehouses
Water treatment plants
Other Sch. A Projects
Other Sch. B Projects
Other Sch. C Projects
Formulas:
Date = TEXT(DATE(YEAR(TODAY()), MONTH(TODAY())+ROWS(M2:[Date])-1, DAY(1)), "MMMM YYYY")