## Major Project Report
OFFICE OF FINANCIAL MANAGEMENT
2025-27 Biennium
WASHINGTON STATE MAJOR PROJECT STATUS REPORT
December 2025
| Agency | 699
| Project Name | Shoreline Community College STEAM Education Center
| OFM Project Number(s) | 40000214
Contact Information
| Name | Kimberlee Clark
| Phone Number | 206-546-4514
| Email | kclark@shoreline.edu
Project Information
| Project Description: (Include a brief summary of the project and the programs it supports.) | The STEAM project includes Nursing, Science, Math and the college's music program. The project consists of a three story building on the footprint of existing building 2200. This buildings will be demolished prior to the start of grading/construction for STEAM with buildings 2300 and 800 being demolished after completion of STEAM. The project will also include an expansion of the stormwater pond in Greenwood lot and sidewalk improvements on Innis Arden way.
| Project Status: (Include scope or budget changes, phase updates, identified project delivery issues, discussion of critical path for construction and any potential for project cost overruns or claims.) | The STEAM building is nearing completion. We are scheduled for TCO by Spring break 2026. Bayley, is finishing up the building, working on the landscaping and pedestrian walk paths, and once they remove their trailers they will add in our EV charging stations. Once we receive TCO, we'll have 60 days to empty buildings 2300 and 800 for Bayley to start decommissioning. The stormwater pond expansion is complete. The Innis Arden project, under Harkness, is 80% complete. They should be completed by Spring 2026.
Funding
All State & Local Sources, Project Transfers and Amounts
|  | Expenditures |  | Current Plan
| Phase & Fund Type | Prior Expended | 2025-27 Expended | 2025-27 Remaining | 2027-29 Plan | Future Plan | TOTAL | Notes
| Predesign | 0 | 0 | 0 | 0 | 0 | 0
| 057 - State Bldgs. Const Acct | [5 empty] | 0
| XXX - Other State Funding | [5 empty] | 0
| Local Funds | [5 empty] | 0
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| Design | 3036441.99 | 0 | 0 | 0 | 0 | 3036441.99
| 057 - State Bldgs. Const Acct | 3036441.99 |  |  |  |  | 3036441.99 | C16, reapprop w/D05 in BI2527
| XXX - Other State Funding | [5 empty] | 0
| Local Funds | [5 empty] | 0
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| Construction | 19775435.5 | 6445450.75 | 13473671.76 | 0 | 0 | 39694558.01
| 057 - State Bldgs. Const Acct | 19775435.5 | 6445450.75 | 13473671.76 |  |  | 39694558.01 | D05, incl. C16 in BI2527
| XXX - Other State Funding | [5 empty] | 0
| Local Funds | [5 empty] | 0
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| TOTALS | 22811877.49 | 6445450.75 | 13473671.76 | 0 | 0 | 42731000
Details
| Construction Type | College classroom facilities |  | Project Administered By |  | DES
| % of Bldgs. Area that is being remodeled | 0% |  | Art Requirement Applies |  | Yes
| Procurement Method | Design-Bid-Build |  | Higher Ed Institution |  | Yes
Statistics
| Complete the table below with information from the cost estimate submitted with the predesign study, the cost estimate of the project as funded and the actual cost data to date or at completion. Explain any variances in the Notes column or below. |  |  | Estimate at Approved Predesign | Estimate of the Project as Currently Funded | Actuals to Date | Estimate as Currently Funded to Actuals Variance | Notes
| Gross Sq Ft (GSF) |  |  | 41500 | 40900 | 40500 | -400
| Usable Sq Ft (USF) |  |  | 26949 | 26549 | 26149 | -400
| Space Efficiency (USF/GSF %): |  |  | 64.94% | 64.91% | 64.57% | -0.3465%
| Site Work SF: | [5 empty] | 0
| Demolition SF (provide building names in comments): |  |  | 47681 | 47681 | 47681 | 0 | See Notes
| MACC/Bid Award COST/GSF |  |  | 543.356 | 670.9171 | 585.5589 | -85.3581
| Construction Subtotal COST/GSF (Includes change orders) |  |  | 629.3578 | 777.2324 | 655.2253 | -122.0071
Milestone Dates
| Predesign Complete |  |  | 2021-12-01 | 2021-12-01 | 2022-03-11 | 3.5 mo.
| Start Design |  |  | 2022-03-01 | 2022-03-01 | 2022-03-12 | 0.5 mo.
| Bid Due Date |  |  |  | 2023-06-01 | 2024-02-27 | 9 mo.
| Notice to Proceed |  |  | 2023-08-01 | 2023-08-01 | 2024-05-20 | 9.5 mo.
| Substantial Completion |  |  | 2025-12-01 | 2026-03-21
Final Acceptance/Project Close-out Date
Project Costs
| Complete the table below with information from the cost estimate submitted with the predesign study, the cost estimate of the project as funded and the actual cost data to date or at completion. Explain any variances in the Notes column or below. |  |  | Cost Estimate at Approved Predesign | Cost Estimate of the Project as Currently Funded | Actual Costs to Date | Estimate as Currently Funded to Actuals Variance | Notes
Acquisition
|  |  | Acquisition Costs Total |  |  |  | 0
Consultant Services
| Pre-Schematic Design Services |  |  | 201560 | 201560 | 163311 | -38249 | SWL
| AE Basic Service Fee - Construction Documents |  |  | 1116952 | 1266972 | 1385282 | 118310 | SWL
| Extra Services - Pre-Bid |  |  | 1548880 | 1563192 | 1064733 | -498459 | SWL, Geoengineers, PBS, Performance Validation, Roen, and Otto
| AE Basic Service Fee - Bid/Construction/Closeout |  |  | 525518.28 | 625185 | 718603 | 93418 | SWL
| Other Services - Post Bid |  |  | 639924 | 677345 | 164312 | -513033 | SSW
| Design Services Contingency |  |  | 208569 | 231818 |  | -231818
|  |  | Consultant Services Total | 4241403.28 | 4566072 | 3496241 | -1069831
Construction
| Site Work |  |  | 2271845 | 2706524 | 2371514 | -335010 | Bayley
| Related Project Costs | [5 empty] | 0
| Facility Construction |  |  | 20277428 | 24733984 | 21343623 | -3390361 | Bayley
|  |  | Maximum Allowable Construction Cost (MACC) Subtotal | 22549273 | 27440508 | 23715137 | -3725371
| Construction Contingencies |  |  | 1130101 | 1379807 | 321906 | -1057901 | Bayley
| Non-Taxable Items | [5 empty] | 0
| Sales Tax |  |  | 2438976 | 2968492 | 2499582 | -468910 | Bayley
0
0
|  |  | Construction Contracts Total | 26118350 | 31788807 | 26536625 | -5252182
Other Project Costs
| Equipment |  |  | 2261146 | 2393378 | 619098 | -1774280
| Art Work |  |  | 172488 | 206239 | 30936 | -175303
| Project Management |  |  | 374850 | 396771 | 288675 | -108096 | Project Mngmt
| Other Costs (describe) |  |  | 3285251 | 3379733 | 81547 | -3298186 | Permit Intake Fee
|  |  | Other Project Costs Total | 6093735 | 6376121 | 1020256 | -5355865
| Total Project Costs |  |  | 36453488.28 | 42731000 | 31053122 | -11677878
Additional comments:
Demolish: UFI A05615 Music = 23,822 gsf / UFI A07524 NursEd = 17,589 gsf / UFI A07428 RegCla = 6,270 gsf
Wa Arts Commission: Dec 2025 - artist William & Karma Simmons, artwork proposal phase

## Photo Gallery (2)
Photo Gallery
STEAM Building Site Plan
STEAM Building Rendering - View from North
STEAM Building Rendering - View from North
STEAM Building Rendering - Interior
STEAM Building - Steel Erection Underway
STEAM Building - Foundation Walls Complete
STEAM Building - Stormwater Structures Being Installed
STEAM Building - Preparation for Slab Pours

## Lists (hidden)
Construction Type | Y/N | PM Admin |  |  | Date | Type of Report
Apartment | Yes | DES | 2003-05 | Design-Bid-Build | Select Date from Dropdown | WASHINGTON STATE MAJOR PROJECT STATUS REPORT
Archive building | No | Agency | 2004 | GCCM | January 2026 | WASHINGTON STATE MAJOR PROJECT FINAL CLOSE-OUT REPORT
Armories |  | Other (explain below) | 2005-07 | Design-Build | February 2026
Art galleries |  |  | 2006 | Other (explain below) | March 2026
Auditorium with stage |  |  | 2007-09 |  | April 2026
Auditorium without stage |  |  | 2008 |  | May 2026
Civil Construction | Estimate at PD to Estimate as Funded Variance |  | 2009-11 |  | June 2026
College classroom facilities | Estimate at PD to Actuals Variance |  | 2010 |  | July 2026
Communications Building | Estimate as Currently Funded to Actuals Variance |  | 2011-13 |  | August 2026
Computer rooms |  |  | 2012 |  | September 2026
Convention facilities |  |  | 2013-15 |  | October 2026
Courthouses |  |  | 2014 |  | November 2026
Day care facilities |  |  | 2015-17 |  | December 2026
Detention/correctional facilities - maximum |  |  | 2016 |  | January 2027
Detention/correctional facilities - min & max |  |  | 2017-19 |  | February 2027
Dining halls/institute |  |  | 2018 |  | March 2027
Dormatories |  |  | 2019-21 |  | April 2027
Emergency generator facilities |  |  | 2020 |  | May 2027
Exposition building |  |  | 2021-23 |  | June 2027
Extended care facilities |  |  | 2022 |  | July 2027
Farm structures |  |  | 2023-25 |  | August 2027
Fire and police stations |  |  | 2024 |  | September 2027
Fish hatcheries |  |  |  |  | October 2027
Greenhouses |  |  |  |  | November 2027
Guard towers |  |  |  |  | December 2027
Gymnasiums
Heating and power plants
Hospitals
Industrial buildings without special facilities
Laboratories (Research)
Laundry and cleaning facilities
Libraries
Medical office and clinics
Mental Institutions
Museums
Neighborhood centers and similar recreation facilities
Nursing homes
Observatories
Office buildings
Parking structures and garages
Printing plants
Prototype facilities
Recreational building
Research Facilities
Residence
Schools (primary and secondary)
Science labs (teaching)
Service garages
Sewer treatment plants
Shop and maintenance facilities
Simple loft-type structures (w/o special equipment)
Special schools for physically disadvantaged
Stadium-grandstand type
Stadiums multi-purpose
Storage-cold
Theaters and similar facilities
Transportation terminals
Veterinary hospitals
Vocational schools
Warehouses
Water treatment plants
Other Sch. A Projects
Other Sch. B Projects
Other Sch. C Projects
Formulas:
Date = TEXT(DATE(YEAR(TODAY()), MONTH(TODAY())+ROWS(M2:[Date])-1, DAY(1)), "MMMM YYYY")