## Major Project Report
OFFICE OF FINANCIAL MANAGEMENT
2025-27 Biennium
WASHINGTON STATE MAJOR PROJECT FINAL CLOSE-OUT REPORT
December 2025
| Agency | 699
| Project Name | Pierce College Puyallup STEM building
| OFM Project Number(s) | 40000293
Contact Information
| Name | Kristen Curiale
| Phone Number | 253-964-6729
| Email | KCuriale@pierce.ctc.edu
Project Information
| Project Description: (Include a brief summary of the project and the programs it supports.) | A new Science, Technology, Engineering and Math (STEM) Building on the Puyallup campus. The project includes a new facility with specialized lab spaces such as organic and general chemistry, a "fablab" for physics, engineering and robotics , earth sciences, biology; and flexible spaces for support classes and student study spaces which will enable the expansion of critical support services in vacated space in existing buildings. Additionally, the project will enable the development of several new programs and capabilities. This project is authorized to exceed 70,000 gsf and includes infrastructure improvements and additional surface parking.
| Project Status: (Include scope or budget changes, phase updates, identified project delivery issues, discussion of critical path for construction and any potential for project cost overruns or claims.) | The building is complete and occupied. All Change Orders are complete and processed. DES is currently working with the General Contractor, Absher, to complete close out, including filing of Affadavits and follow up items from Auditor. Once complete, a FInal Pay Application will be reviewed and processed. All these items are being tracked and reviewed every 2 weeks to continue the close-out process. With the capital funds re-appropriated, there are a few items being considered to be added via Job Order Contract (so that Absher Contract can continue towards Close-Out). A site meeting was held with the JOC to review the scope items and we are awaiting pricing to confirm available budget.
Funding
All State & Local Sources, Project Transfers and Amounts
|  | Expenditures |  | Current Plan
| Phase & Fund Type | Prior Expended | 2025-27 Expended | 2025-27 Remaining | 2027-29 Plan | Future Plan | TOTAL | Notes
| Predesign | 0 | 0 | 0 | 0 | 0 | 0
| 057 - State Bldgs. Const Acct | [5 empty] | 0
| XXX - Other State Funding | [5 empty] | 0
| Local Funds | [5 empty] | 0
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| Design | 3368994.14 | 0 | 0 | 0 | 0 | 3368994.14
| 057 - State Bldgs. Const Acct | 3368994.14 |  |  |  |  | 3368994.14 | A17
| XXX - Other State Funding | [5 empty] | 0
| Local Funds | [5 empty] | 0
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| Construction | 46494836 | 374216.73 | 1355952.86 | 0 | 0 | 48225005.59
| 057 - State Bldgs. Const Acct | 37484679 | 91108.3 | 1024218.29 |  |  | 38600005.59 | C18
| XXX - Other State Funding | [5 empty] | 0
| 147 - Local Funds | 9010157 | 283108.43 | 331734.57 |  |  | 9625000 | Q617
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| TOTALS | 49863830.14 | 374216.73 | 1355952.86 | 0 | 0 | 51593999.73
Details
| Construction Type | Science labs (teaching) |  | Project Administered By |  | DES
| % of Bldgs. Area that is being remodeled | 0% |  | Art Requirement Applies |  | Yes
| Procurement Method | Design-Build |  | Higher Ed Institution |  | Yes
Statistics
| Complete the table below with information from the cost estimate submitted with the predesign study, the cost estimate of the project as funded and the actual cost data to date or at completion. Explain any variances in the Notes column or below. |  |  | Estimate at Approved Predesign | Estimate of the Project as Currently Funded | Actuals at Final Completion | Estimate as Currently Funded to Actuals Variance | Notes
| Gross Sq Ft (GSF) |  |  | 54400 | 66500 | 54000 | -12500
| Usable Sq Ft (USF) |  |  | 40825 | 45220 | 40000 | -5220
| Space Efficiency (USF/GSF %): |  |  | 75.05% | 68% | 74.07% | 6.074%
| Site Work SF: |  |  |  |  | 54000 | 54000
| Demolition SF (provide building names in comments): |  |  |  |  | 0 | 0
| MACC/Bid Award COST/GSF |  |  | 473.7982 | 521.7478 | 672.6968 | 150.949
| Construction Subtotal COST/GSF (Includes change orders) |  |  | 643.9712 | 600.2279 | 785.0723 | 184.8444
Milestone Dates
| Predesign Complete |  |  | 2020-07-01 | 2021-05-01 | 2020-09-23
| Start Design |  |  | 2021-07-01 | 2021-07-01 | 2020-09-24
Bid Due Date
| Notice to Proceed |  |  | 2022-04-01 | 2021-07-01 | 2021-12-06 | 5 mo.
| Substantial Completion |  |  | 2023-09-01 | 2024-08-14 | 2024-09-11 | 1 mo.
| Final Acceptance/Project Close-out Date |  |  |  | 2025-03-15
Project Costs
| Complete the table below with information from the cost estimate submitted with the predesign study, the cost estimate of the project as funded and the actual cost data to date or at completion. Explain any variances in the Notes column or below. |  |  | Cost Estimate at Approved Predesign | Cost Estimate of the Project as Currently Funded | Actual Cost Data at Final Completion | Estimate as Currently Funded to Actuals Variance | Notes
Acquisition
|  |  | Acquisition Costs Total |  |  |  | 0
Consultant Services
| Pre-Schematic Design Services |  |  | 296929 | 254680 | 283625.7 | 28945.7
| AE Basic Service Fee - Construction Documents |  |  | 0 | 1499322 | 1438369.72 | -60952.28
| Extra Services - Pre-Bid |  |  | 290332 | 1602677 | 20224.64 | -1582452.36
| AE Basic Service Fee - Bid/Construction/Closeout |  |  | 0 | 745512 | 2097784.19 | 1352272.19
| Other Services - Post Bid |  |  | 212320 | 226768 | 337646.14 | 110878.14
| Design Services Contingency |  |  | 40843 | 216676 |  | -216676
|  |  | Consultant Services Total | 840424 | 4545635 | 4177650.39 | -367984.61
Construction
| Site Work |  |  | 2289738 | 4379418 | 5524117.24 | 1144699.24
| Related Project Costs |  |  | 0 | 996572 |  | -996572
| Facility Construction |  |  | 23484882 | 29320238 | 30801509.65 | 1481271.65
|  |  | Maximum Allowable Construction Cost (MACC) Subtotal | 25774620 | 34696228 | 36325626.89 | 1629398.89
| Construction Contingencies |  |  | 2417908 | 1590277 | 213314.33 | -1376962.67
| Non-Taxable Items | [5 empty] | 0
| Sales Tax |  |  | 3155752 | 3628651 | 4200480.71 | 571829.71
| Design-Build Costs |  |  | 3683752 |  | 1654481.7 | 1654481.7
0
|  |  | Construction Contracts Total | 35032032 | 39915156 | 42393903.63 | 2478747.63
Other Project Costs
| Equipment |  |  | 2896608 | 2851451 | 1936430.87 | -915020.13
| Art Work |  |  | 201985 | 208801 | 187920 | -20881
| Project Management |  |  | 265400 | 125235 | 663216.43 | 537981.43
| Other Costs (describe) |  |  | 1362551 | 647771 | 1002639.17 | 354868.17
|  |  | Other Project Costs Total | 4726544 | 3833258 | 3790206.47 | -43051.53
| Total Project Costs |  |  | 40599000 | 48294049 | 50361760.49 | 2067711.49
Close-Out Information
NOTES
| Number of Change Orders | 39
| Total Value of Change Orders | 1972164.43
Outstanding Liabilities
Unsettled Claims
Additional comments:
WaArts - June 2025 - installed

## Photo Gallery-Dec2024
Photo Gallery
Completed Johnson Science Building - from Parking Lot
2 Story Entry Lobby viewed from second level
2-Story Space for Student Experimentation
Sun Lodge - by Preston Singletaryngletary (Arts WA)rts WA)
Completed Johnson Science Building - from Quad
Sun Lodge - by Preston Sngletary (Arts WA)
Feature Stairwell at Main Entry
Nature Trail for Hands-On Learning Opportunities

## Photo Gallery-jun2024
Photo Gallery
Front Entry Siding Mostly Complete - May '24
East Entry Siding Nearing Completion - May '24
Lab Casework Installation Underway - May '24
Fab Lab Equipment Storage - May '23
Lab Prep Room Equipment- May '24
Mechanical Room Equipment Installation- May '24

## Photo Gallery-dec2023
Photo Gallery
MEP rough-in underway - Oct '23
Structural Steel nearing completion - Oct '23
Closing in framing & exterior sheathing - Nov '23
View at entry off parking lot (east) - Nov '23
2-Story entry lobby - Nov '23
CHW piping rough-in - Nov '23

## Photo Gallery-jun2023
Photo Gallery
Wide-angle view of completed slab on grade
Installation of a site Fire Hydrant
New parking lot site, at grade and ready for final subgrade,
curbs and asphalt
Gravity lab view from grade-this will be a 2-story space for experimentation

## Lists (hidden)
Construction Type | Y/N | PM Admin |  |  | Date | Type of Report
Apartment | Yes | DES | 2003-05 | Design-Bid-Build | Select Date from Dropdown | WASHINGTON STATE MAJOR PROJECT STATUS REPORT
Archive building | No | Agency | 2004 | GCCM | January 2026 | WASHINGTON STATE MAJOR PROJECT FINAL CLOSE-OUT REPORT
Armories |  | Other (explain below) | 2005-07 | Design-Build | February 2026
Art galleries |  |  | 2006 | Other (explain below) | March 2026
Auditorium with stage |  |  | 2007-09 |  | April 2026
Auditorium without stage |  |  | 2008 |  | May 2026
Civil Construction | Estimate at PD to Estimate as Funded Variance |  | 2009-11 |  | June 2026
College classroom facilities | Estimate at PD to Actuals Variance |  | 2010 |  | July 2026
Communications Building | Estimate as Currently Funded to Actuals Variance |  | 2011-13 |  | August 2026
Computer rooms |  |  | 2012 |  | September 2026
Convention facilities |  |  | 2013-15 |  | October 2026
Courthouses |  |  | 2014 |  | November 2026
Day care facilities |  |  | 2015-17 |  | December 2026
Detention/correctional facilities - maximum |  |  | 2016 |  | January 2027
Detention/correctional facilities - min & max |  |  | 2017-19 |  | February 2027
Dining halls/institute |  |  | 2018 |  | March 2027
Dormatories |  |  | 2019-21 |  | April 2027
Emergency generator facilities |  |  | 2020 |  | May 2027
Exposition building |  |  | 2021-23 |  | June 2027
Extended care facilities |  |  | 2022 |  | July 2027
Farm structures |  |  | 2023-25 |  | August 2027
Fire and police stations |  |  | 2024 |  | September 2027
Fish hatcheries |  |  |  |  | October 2027
Greenhouses |  |  |  |  | November 2027
Guard towers |  |  |  |  | December 2027
Gymnasiums
Heating and power plants
Hospitals
Industrial buildings without special facilities
Laboratories (Research)
Laundry and cleaning facilities
Libraries
Medical office and clinics
Mental Institutions
Museums
Neighborhood centers and similar recreation facilities
Nursing homes
Observatories
Office buildings
Parking structures and garages
Printing plants
Prototype facilities
Recreational building
Research Facilities
Residence
Schools (primary and secondary)
Science labs (teaching)
Service garages
Sewer treatment plants
Shop and maintenance facilities
Simple loft-type structures (w/o special equipment)
Special schools for physically disadvantaged
Stadium-grandstand type
Stadiums multi-purpose
Storage-cold
Theaters and similar facilities
Transportation terminals
Veterinary hospitals
Vocational schools
Warehouses
Water treatment plants
Other Sch. A Projects
Other Sch. B Projects
Other Sch. C Projects
Formulas:
Date = TEXT(DATE(YEAR(TODAY()), MONTH(TODAY())+ROWS(M2:[Date])-1, DAY(1)), "MMMM YYYY")