## Major Project Report
OFFICE OF FINANCIAL MANAGEMENT
2025-27 Biennium
WASHINGTON STATE MAJOR PROJECT FINAL CLOSE-OUT REPORT
December 2025
| Agency | 699
| Project Name | Pierce College - Fort Steilacoom Olympic South Asbestos Abatement
| OFM Project Number(s) | 40000516
Contact Information
| Name | Kristen Curiale
| Phone Number | 253-964-6729
| Email | KCuriale@pierce.ctc.edu
Project Information
| Project Description: (Include a brief summary of the project and the programs it supports.) | In March of 2021 asbestos contamination was found in surface dust in the Olympic South building. Asbestos was discovered in the dust of the HVAC and electrical systems throughout levels 1, 2 and 3. Asbestos contamination was found on contents of Levels 1 and 2, however no significant asbestos was discovered on contents on level 3. The project is declared an emergency. The programs that are now displaced by this project include Early Childhood Education, Visual Art, Music, and Central Washington University's Pierce County satellite.
| Project Status: (Include scope or budget changes, phase updates, identified project delivery issues, discussion of critical path for construction and any potential for project cost overruns or claims.) | The building was re-occupied at the start of Spring Quarter 2025. The building is open for business and is well received. The progressive design build delivery method was perfect for this project. The entire team notes this project as one of the highlights of our collective careers. The project has equipment that is long-lead and still on order and expected to arrive after July 1, 2025. Additional abatement may be required to replace a security camera that was removed as part of the first phase of asbestos abatement but was overlooked in the reconstruction phase.
Funding
All State & Local Sources, Project Transfers and Amounts
|  | Expenditures |  | Current Plan
| Phase & Fund Type | Prior Expended | 2025-27 Expended | 2025-27 Remaining | 2027-29 Plan | Future Plan | TOTAL | Notes
| Predesign | 0 | 0 | 0 | 0 | 0 | 0
| 057 - State Bldgs. Const Acct | [5 empty] | 0
| XXX - Other State Funding | [5 empty] | 0
| Local Funds | [5 empty] | 0
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| Design | 0 | 0 | 0 | 0 | 0 | 0
| 057 - State Bldgs. Const Acct | [5 empty] | 0
| XXX - Other State Funding | [5 empty] | 0
| Local Funds | [5 empty] | 0
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| Construction | 25037108.01 | 186573.13 | 1080811.28 | 0 | 0 | 26304492.42
| 057 - State Bldg. Const Acct | 11933177.5 | 171937.63 | 1053884.37 |  |  | 13158999.5 | C28-Q618/Q650
| 060 - Hazmat/Emergency Pool | 1000000 |  |  |  |  | 1000000 | C21-Q585/Q559
| 147 - Local Funds | 10921437.6 | 14635.5 | 26926.91 |  |  | 10963000.01 | P612
| 057- Minor Works Program | 639526.44 |  |  |  |  | 639526.44 | A09-Q572
| 060-MW 21-23 URF fund | 542966.47 |  |  |  |  | 542966.47 | C21-Q363
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| TOTALS | 25037108.01 | 186573.13 | 1080811.28 | 0 | 0 | 26304492.42
Details
| Construction Type | College classroom facilities |  | Project Administered By |  | DES
| % of Bldgs. Area that is being remodeled | 100% |  | Art Requirement Applies |  | Yes
| Procurement Method | Design-Build |  | Higher Ed Institution |  | Yes
Statistics
| Complete the table below with information from the cost estimate submitted with the predesign study, the cost estimate of the project as funded and the actual cost data to date or at completion. Explain any variances in the Notes column or below. |  |  | Estimate at Approved Predesign | Estimate of the Project as Currently Funded | Actuals at Final Completion | Estimate as Currently Funded to Actuals Variance | Notes
| Gross Sq Ft (GSF) |  |  |  | 38800 | 38800 | 0
| Usable Sq Ft (USF) |  |  |  | 24761 | 24761 | 0
| Space Efficiency (USF/GSF %): |  |  |  | 63.82% | 63.82% | 0%
| Site Work SF: |  |  |  |  | 38800 | 38800
| Demolition SF (provide building names in comments): |  |  |  |  | 0 | 0
| MACC/Bid Award COST/GSF |  |  |  | 477.1514 | 489.441 | 12.2896
| Construction Subtotal COST/GSF (Includes change orders) |  |  |  | 562.3247 | 594.8832 | 32.5585
Milestone Dates
| Predesign Complete |  |  |  | 2022-07-15 | 2022-07-15 | 0 mo.
| Start Design |  |  |  | 2023-02-01 | 2023-02-01 | 0 mo.
Bid Due Date
| Notice to Proceed |  |  |  | 2023-01-19 | 2023-01-19 | 0 mo.
| Substantial Completion |  |  |  | 2024-09-30 | 2025-01-06 | 3 mo. | Now 01/06/25
| Final Acceptance/Project Close-out Date |  |  |  | 2025-03-01 | 2025-11-04 | 8 mo.
Project Costs
| Complete the table below with information from the cost estimate submitted with the predesign study, the cost estimate of the project as funded and the actual cost data to date or at completion. Explain any variances in the Notes column or below. |  |  | Cost Estimate at Approved Predesign | Cost Estimate of the Project as Currently Funded | Actual Cost Data at Final Completion | Estimate as Currently Funded to Actuals Variance | Notes
Acquisition
|  |  | Acquisition Costs Total |  |  |  | 0
Consultant Services
| Pre-Schematic Design Services |  |  |  | 136807 | 136321.54 | -485.46
| AE Basic Service Fee - Construction Documents |  |  |  | -2 | 586366.57 | 586368.57
| Extra Services - Pre-Bid |  |  |  | 1863245 | 1394899.22 | -468345.78
| AE Basic Service Fee - Bid/Construction/Closeout |  |  |  | -1 | 1394899.22 | 1394900.22
| Other Services - Post Bid |  |  |  | -1 | 631392.98 | 631393.98
| Design Services Contingency |  |  |  | 0 | 498170.82 | 498170.82
|  |  | Consultant Services Total | 0 | 2000048 | 4642050.35 | 2642002.35
Construction
| Site Work |  |  |  | 310651 | 1254889 | 944238
| Related Project Costs |  |  |  | 5228247 | 5594190.84 | 365943.84
| Facility Construction |  |  |  | 12974576 | 12141229.3 | -833346.7
|  |  | Maximum Allowable Construction Cost (MACC) Subtotal | 0 | 18513474 | 18990309.14 | 476835.14
| Construction Contingencies |  |  |  | 1303237 | 1196264.32 | -106972.68
| Non-Taxable Items |  |  |  | 0 |  | 0
| Sales Tax |  |  |  | 2001488 | 2284777.93 | 283289.93
| Design-Build Costs |  |  |  |  | 610116.5 | 610116.5
0
|  |  | Construction Contracts Total | 0 | 21818199 | 23081467.89 | 1263268.89
Other Project Costs
| Equipment |  |  |  | 1439227 | 631478.99 | -807748.01
| Art Work |  |  |  | 87121 | 15418 | -71703
| Project Management |  |  |  | 417546 | 403606.25 | -13939.75
| Other Costs (describe) |  |  |  | 212296 | 348837.93 | 136541.93 | Ads, Moving & Storage, Honorarium
|  |  | Other Project Costs Total | 0 | 2156190 | 1399341.17 | -756848.83
| Total Project Costs |  |  | 0 | 25974437 | 29122859.41 | 3148422.41
Close-Out Information
NOTES
| Number of Change Orders | 41
| Total Value of Change Orders | 16478149.88
Outstanding Liabilities
Unsettled Claims
Additional comments:
Wa Arts Commission Dec. 2025: artist Dionne Bonner in design phase

## Photo Gallery (2)
Photo Gallery
ECE Level 1 Lab School
Level 2 Gallery
Level 3 CWU Reception Area
ECE Outdoor Sheds
Exterior New Entry Approach
Outdoor Learning Environment from Level 3

## Lists (hidden)
Construction Type | Y/N | PM Admin |  |  | Date | Type of Report
Apartment | Yes | DES | 2003-05 | Design-Bid-Build | Select Date from Dropdown | WASHINGTON STATE MAJOR PROJECT STATUS REPORT
Archive building | No | Agency | 2004 | GCCM | January 2026 | WASHINGTON STATE MAJOR PROJECT FINAL CLOSE-OUT REPORT
Armories |  | Other (explain below) | 2005-07 | Design-Build | February 2026
Art galleries |  |  | 2006 | Other (explain below) | March 2026
Auditorium with stage |  |  | 2007-09 |  | April 2026
Auditorium without stage |  |  | 2008 |  | May 2026
Civil Construction | Estimate at PD to Estimate as Funded Variance |  | 2009-11 |  | June 2026
College classroom facilities | Estimate at PD to Actuals Variance |  | 2010 |  | July 2026
Communications Building | Estimate as Currently Funded to Actuals Variance |  | 2011-13 |  | August 2026
Computer rooms |  |  | 2012 |  | September 2026
Convention facilities |  |  | 2013-15 |  | October 2026
Courthouses |  |  | 2014 |  | November 2026
Day care facilities |  |  | 2015-17 |  | December 2026
Detention/correctional facilities - maximum |  |  | 2016 |  | January 2027
Detention/correctional facilities - min & max |  |  | 2017-19 |  | February 2027
Dining halls/institute |  |  | 2018 |  | March 2027
Dormatories |  |  | 2019-21 |  | April 2027
Emergency generator facilities |  |  | 2020 |  | May 2027
Exposition building |  |  | 2021-23 |  | June 2027
Extended care facilities |  |  | 2022 |  | July 2027
Farm structures |  |  | 2023-25 |  | August 2027
Fire and police stations |  |  | 2024 |  | September 2027
Fish hatcheries |  |  |  |  | October 2027
Greenhouses |  |  |  |  | November 2027
Guard towers |  |  |  |  | December 2027
Gymnasiums
Heating and power plants
Hospitals
Industrial buildings without special facilities
Laboratories (Research)
Laundry and cleaning facilities
Libraries
Medical office and clinics
Mental Institutions
Museums
Neighborhood centers and similar recreation facilities
Nursing homes
Observatories
Office buildings
Parking structures and garages
Printing plants
Prototype facilities
Recreational building
Research Facilities
Residence
Schools (primary and secondary)
Science labs (teaching)
Service garages
Sewer treatment plants
Shop and maintenance facilities
Simple loft-type structures (w/o special equipment)
Special schools for physically disadvantaged
Stadium-grandstand type
Stadiums multi-purpose
Storage-cold
Theaters and similar facilities
Transportation terminals
Veterinary hospitals
Vocational schools
Warehouses
Water treatment plants
Other Sch. A Projects
Other Sch. B Projects
Other Sch. C Projects
Formulas:
Date = TEXT(DATE(YEAR(TODAY()), MONTH(TODAY())+ROWS(M2:[Date])-1, DAY(1)), "MMMM YYYY")