## Major Project Report
OFFICE OF FINANCIAL MANAGEMENT
2025-27 Biennium
WASHINGTON STATE MAJOR PROJECT STATUS REPORT
June 2026
| Agency | 699
| Project Name | Olympic College Innovation and Technology Learning
| OFM Project Number(s) | 40000103
Contact Information
| Name | Brent Palmason
| Phone Number | 360-475-7121
| Email | bpalmason@olympic.edu
Project Information
| Project Description: (Include a brief summary of the project and the programs it supports.) | The plan is for a 31,864 square foot innovation and technology center. A two story building designed to support 23 faculty/staff and 258 students at peak occupancy. The ITLC building will provide state of the art labs for computer information systems, computer science, cybersecurity, digital media arts and water flow research engineering programs. Included will be classrooms, labs, offices and support areas for students.
| Project Status: (Include scope or budget changes, phase updates, identified project delivery issues, discussion of critical path for construction and any potential for project cost overruns or claims.) | The project is in permit review with the city of Bremerton. The site development permit review is nearing completion. The city has imposed additional right-of-way improvement requirements which have increased costs. To off-set these costs the project team has eliminated off-site parking improvements that do not affect the permit or program of the project. The permit review process is moving slower than expected and we now do not anticipate the project will bid in 2026. The design team continues to refine the design package for bidding/construction. The project would bid and construction start in early 2027 . Construction is estimated at 18 months with occupancy in fall 2028.
Funding
All State & Local Sources, Project Transfers and Amounts
|  | Expenditures |  | Current Plan
| Phase & Fund Type | Prior Expended | 2025-27 Expended | 2025-27 Remaining | 2027-29 Plan | Future Plan | TOTAL | Notes
| Predesign | 0 | 0 | 0 | 0 | 0 | 0
| 057 - State Bldgs. Const Acct | [5 empty] | 0
| XXX - Other State Funding | [5 empty] | 0
| Local Funds | [5 empty] | 0
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| Design | 1095568.11 | 991281.14 | 465150.75 | 0 | 0 | 2552000
| 057 - State Bldgs. Const Acct | 1095568.11 | 991281.14 | 465150.75 |  |  | 2552000 | A08
| XXX - Other State Funding | [5 empty] | 0
| Local Funds | [5 empty] | 0
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| Construction | 0 | 0 | 21792821 | 9261179 | 0 | 31054000
| 057 - State Bldgs. Const Acct |  | 0 | 21792821 | 9261179 |  | 31054000 | E00
| XXX - Other State Funding | [5 empty] | 0
| Local Funds | [5 empty] | 0
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| TOTALS | 1095568.11 | 991281.14 | 22257971.75 | 9261179 | 0 | 33606000
Details
| Construction Type | College classroom facilities |  | Project Administered By |  | DES
| % of Bldgs. Area that is being remodeled | 0% |  | Art Requirement Applies |  | Yes
| Procurement Method | Design-Bid-Build |  | Higher Ed Institution |  | Yes
Statistics
| Complete the table below with information from the cost estimate submitted with the predesign study, the cost estimate of the project as funded and the actual cost data to date or at completion. Explain any variances in the Notes column or below. |  |  | Estimate at Approved Predesign | Estimate of the Project as Currently Funded | Actuals to Date | Estimate as Currently Funded to Actuals Variance | Notes
| Gross Sq Ft (GSF) |  |  | 31864 | 31864 | 31864 | 0
| Usable Sq Ft (USF) |  |  | 20162 | 20162 | 20162 | 0
| Space Efficiency (USF/GSF %): |  |  | 63.28% | 63.28% | 63.28% | 0%
| Site Work SF: | [5 empty] | 0
| Demolition SF (provide building names in comments): | [5 empty] | 0
| MACC/Bid Award COST/GSF |  |  | 738.0319 | 738.0319 | 0 | -738.0319
| Construction Subtotal COST/GSF (Includes change orders) |  |  | 738.0319 | 738.0319 | 0 | -738.0319
Milestone Dates
| Predesign Complete |  |  | 2022-07-01 | 2022-07-01 | 2024-06-28 | 24 mo. | Variance due to hiring new architect and having to amend the original pre-design
| Start Design |  |  | 2022-11-01 | 2023-02-01 | 2023-02-01 | 0 mo.
| Bid Due Date |  |  |  | 2027-02-03
| Notice to Proceed |  |  | 2026-04-01 | 2027-03-01
| Substantial Completion |  |  | 2027-12-01 | 2028-09-01
| Final Acceptance/Project Close-out Date |  |  |  | 2028-11-01
Project Costs
| Complete the table below with information from the cost estimate submitted with the predesign study, the cost estimate of the project as funded and the actual cost data to date or at completion. Explain any variances in the Notes column or below. |  |  | Cost Estimate at Approved Predesign | Cost Estimate of the Project as Currently Funded | Actual Costs to Date | Estimate as Currently Funded to Actuals Variance | Notes
Acquisition
|  |  | Acquisition Costs Total |  |  |  | 0
Consultant Services
| Pre-Schematic Design Services |  |  | 211995 | 211995 | 193095 | -18900 | Miller Hull PDR
| AE Basic Service Fee - Construction Documents |  |  | 1192642 | 1192642 | 1063050 | -129592 | Actual SWL billing
| Extra Services - Pre-Bid |  |  | 1900328 | 1900328 | 742075 | -1158253 | Actual SWL billing+McKinstry OPR+Roen & Associates VE, Meng Analysis, PBS, DES ELCCA
| AE Basic Service Fee - Bid/Construction/Closeout |  |  | 584745 | 584744.7 | 0 | -584744.7
| Other Services - Post Bid |  |  | 551107 | 551107.3 |  | -551107.3
| Design Services Contingency |  |  | 237128 | 237128 |  | -237128
|  |  | Consultant Services Total | 4677945 | 4677945 | 1998220 | -2679725
Construction
| Site Work |  |  | 3244262 | 3244262 |  | -3244262
| Related Project Costs |  |  | 0 | 0 |  | 0
| Facility Construction |  |  | 20272386 | 20272386 |  | -20272386
|  |  | Maximum Allowable Construction Cost (MACC) Subtotal | 23516648 | 23516648 | 0 | -23516648
| Construction Contingencies | [5 empty] | 0
| Non-Taxable Items | [5 empty] | 0
| Sales Tax | [5 empty] | 0
0
0
|  |  | Construction Contracts Total | 23516648 | 23516648 | 0 | -23516648
Other Project Costs
| Equipment |  |  | 2008872 | 2008872 |  | -2008872
| Art Work |  |  | 172060 | 171172 | 0 | -171172
| Project Management |  |  | 272825 | 272825 |  | -272825
| Other Costs (describe) |  |  | 483165 | 483165 | 1453 | -481712 | Permit fee
|  |  | Other Project Costs Total | 2936922 | 2936034 | 1453 | -2934581
| Total Project Costs |  |  | 31131515 | 31130627 | 1999673 | -29130954
Additional comments:
WA Arts Commission - led the art committee to select an artist for the ITLC project. The artist accepted the commission and an on-site artist meeting was
held in April 2026. Preliminary concepts to be reviewed by September 2026.

## Photo Gallery
Photo Gallery
Construction document rendering from 15th & Lincoln
Aerial Perspective
1st floor plan
Maker space concept
South Elevation
2nd Floor Corridor
2nd Floor Plan

## Lists (hidden)
Construction Type | Y/N | PM Admin |  |  | Date | Type of Report
Apartment | Yes | DES | 2003-05 | Design-Bid-Build | Select Date from Dropdown | WASHINGTON STATE MAJOR PROJECT STATUS REPORT
Archive building | No | Agency | 2004 | GCCM | July 2026 | WASHINGTON STATE MAJOR PROJECT FINAL CLOSE-OUT REPORT
Armories |  | Other (explain below) | 2005-07 | Design-Build | August 2026
Art galleries |  |  | 2006 | Other (explain below) | September 2026
Auditorium with stage |  |  | 2007-09 |  | October 2026
Auditorium without stage |  |  | 2008 |  | November 2026
Civil Construction | Estimate at PD to Estimate as Funded Variance |  | 2009-11 |  | December 2026
College classroom facilities | Estimate at PD to Actuals Variance |  | 2010 |  | January 2027
Communications Building | Estimate as Currently Funded to Actuals Variance |  | 2011-13 |  | February 2027
Computer rooms |  |  | 2012 |  | March 2027
Convention facilities |  |  | 2013-15 |  | April 2027
Courthouses |  |  | 2014 |  | May 2027
Day care facilities |  |  | 2015-17 |  | June 2027
Detention/correctional facilities - maximum |  |  | 2016 |  | July 2027
Detention/correctional facilities - min & max |  |  | 2017-19 |  | August 2027
Dining halls/institute |  |  | 2018 |  | September 2027
Dormatories |  |  | 2019-21 |  | October 2027
Emergency generator facilities |  |  | 2020 |  | November 2027
Exposition building |  |  | 2021-23 |  | December 2027
Extended care facilities |  |  | 2022 |  | January 2028
Farm structures |  |  | 2023-25 |  | February 2028
Fire and police stations |  |  | 2024 |  | March 2028
Fish hatcheries |  |  |  |  | April 2028
Greenhouses |  |  |  |  | May 2028
Guard towers |  |  |  |  | June 2028
Gymnasiums
Heating and power plants
Hospitals
Industrial buildings without special facilities
Laboratories (Research)
Laundry and cleaning facilities
Libraries
Medical office and clinics
Mental Institutions
Museums
Neighborhood centers and similar recreation facilities
Nursing homes
Observatories
Office buildings
Parking structures and garages
Printing plants
Prototype facilities
Recreational building
Research Facilities
Residence
Schools (primary and secondary)
Science labs (teaching)
Service garages
Sewer treatment plants
Shop and maintenance facilities
Simple loft-type structures (w/o special equipment)
Special schools for physically disadvantaged
Stadium-grandstand type
Stadiums multi-purpose
Storage-cold
Theaters and similar facilities
Transportation terminals
Veterinary hospitals
Vocational schools
Warehouses
Water treatment plants
Other Sch. A Projects
Other Sch. B Projects
Other Sch. C Projects
Formulas:
Date = TEXT(DATE(YEAR(TODAY()), MONTH(TODAY())+ROWS(M2:[Date])-1, DAY(1)), "MMMM YYYY")