## QuickStartGuide
Major Project Report
Quick Start Guide
BACKGROUND INFORMATION
The Final Project Close-out Report requirement was implemented in the 2013-15 biennium as part of the recommendations in the 2009 JLARC report, “Evaluation of the Accuracy of Capital Project Cost Estimates.” This requirement is for agencies to submit the report to OFM at project completion to compare the scope and estimate from the predesign stage with the final scope and actual cost after construction as well as the estimate as the project was funded.
RCW 43.88.160 requires OFM to submit an annual report to the Legislature on the status of all appropriated capital projects (including transportation projects) that show significant cost overruns or underruns. As these projects are completed, agencies must provide OFM with a final summary showing estimated start and completion dates of each project phase compared to actual dates, as well as estimated costs of each phase compared to actual costs. OFM uses the information collected in the Final Project Close-out Report to make its annual report to the Legislature.
Agencies administering a major capital project or projects specifically identified for this reporting requirement by OFM or the Legislature must submit a detailed Major Project Status Report to OFM and the legislative fiscal committees each December 31 and July 1.
GENERAL INFORMATION
This comprehensive reporting tool merges the Major Project Status Report and the Final Project Close-Out Report. This is to generate consistency in reported data as required by OFM, the Legislature, and state statute; especially as it pertains to comparing cost estimates at predesign approval, cost estimates as projects are currently funded, and the actual costs at project completion.
Please contact your assigned OFM Capital Budget Analyst if you have any questions regarding this tool.
INSTRUCTIONS
1) | Blue cells are available for data entry.
2) | Select the type of report you will be submitting in cell B2. Select "Major Project Status Report" if your report is to fulfill the semi-annual requirement to update OFM and the Legislature on the status of your project. Select "Final Project Close-Out Report" if your project is complete.
3) | In the funding section, please include all funding sources for the project by phase. Identify the fund number and name (for example: "06X - Building and Tuition Acct"). Identify all local and alternative funding sources and all OFM authorized transfers from other projects. Insert rows where necessary.
4) | Cost and other variances can be compared three ways: 1) Estimates at Approved Predesign to Estimates as Currently Funded. 2) Estimates at Approved Predesign to Actuals. 3) Estimates as Currently Funded to Actuals). Click on cell H55 to select your variance comparison.
5) | Additional information, such as number and value of change orders, is required for the Final Project Close-Out Report. Those cells will be made available when that report type is selected in cell B2.
6) | If available, photos can be added to the Photo Gallery tab for a visual representation of the status of the project. Pictures can sometimes provide a better understanding of the status of a construction project than one can get from just the schedule or expenses to date. Right-click on the stock photos and select "Change Picture" to insert your photo from a file. Captions of the photo can be made in the text box below the photo.

## Major Project Report
OFFICE OF FINANCIAL MANAGEMENT
2023-25 Biennium
WASHINGTON STATE MAJOR PROJECT STATUS REPORT
June 2025
| Agency | 699
| Project Name | Lower Columbia College Center for Vocational & Transitional Studies
| OFM Project Number(s) | 40000106
Contact Information
| Name | Nolan Wheeler
| Phone Number | 360-442-2201
| Email | nwheeler@lowercolumbia.edu
Project Information
| Project Description: | The Vocational Education & Classroom Building will provide labs, classrooms, informal student study spaces and offices to serve the College's programs in machine trades, manufacturing, welding, information technology and transitional studies.
(Include a brief summary of the project and the programs it supports.)
| Project Status: | Pre-design - Engineering agreement signed 11/10/21. Pre-design report approved by OFM on 4/26/22. Architect selection for design completed on 5/19/22 (firm MSGS selected). Design team completed SD on 12/16/22 and starting on DD phase. A community leader share out of the schematic design was held on 12/13/22 and was very well attended. Project design work delayed pending future state funding. The City of Longview notified LCC on 5/22/2023 that they are requiring LCC to replace the 20-inch watermain that bisects campus from north to south with a new watermain in the 15th Avenue corridor. During the Project Request and Pre-design phase, LCC had been told that the city would only require protection of the existing watermain. This new requirement increases the cost of the project by approximately $3.4MM. Meetings are ongoing to be ready in July 2025. Art in Public Places reached out to start the artwork process.
(Include scope or budget changes, phase updates, identified project delivery issues, discussion of critical path for construction and any potential for project cost overruns or claims.)
Funding
All State & Local Sources, Project Transfers and Amounts
|  | Expenditures |  | Current Plan |  |  | TOTAL | Notes
| Phase & Fund Type | Prior Expended | 2023-25 Expended | 2023-25 Remaining | 2025-27 Plan | Future Plan
| Predesign | 0 | 0 | 0 | 0 | 0 | 0
| 057 - State Bldg Const Acct | [5 empty] | 0
| XXX - Other State Funding | [5 empty] | 0
| Local Funds | [5 empty] | 0
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| Design | 1401147 | 1098682.81 | 706170.19 | 0 | 0 | 3206000
| 057 - State Bldg Const Acct | 1401147 | 1098682.81 | 706170.19 |  |  | 3206000 | C09
| XXX - Other State Funding | [5 empty] | 0
| Local Funds | [5 empty] | 0
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| Construction | 0 | 0 | 0 | 0 | 34005000 | 34005000
| 057 - State Bldg Const Acct |  |  |  |  | 31805000 | 31805000 | Future
| XXX - Other State Funding | [5 empty] | 0
| Local Funds |  |  |  |  | 2200000 | 2200000 | Future if needed
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| TOTALS | 1401147 | 1098682.81 | 706170.19 | 0 | 34005000 | 37211000
Details
| Construction Type | College classroom facilities |  | Project Administered By |  | DES
| % of Bldg Area that is being remodeled | 0% |  | Art Requirement Applies |  | Yes
| Procurement Method | Design-Bid-Build |  | Higher Ed Institution |  | Yes
Statistics
| Complete the table below with information from the cost estimate submitted with the predesign study, the cost estimate of the project as funded and the actual cost data to date or at completion. Explain any variances in the Notes column or below. |  |  | Estimate at Approved Predesign | Estimate of the Project as Currently Funded | Actuals to Date | Estimate as Currently Funded to Actuals Variance | Notes
| Gross Sq Ft (GSF) |  |  | 46267 | 50694 |  | -50694
| Usable Sq Ft (USF) |  |  | 32590 | 35689 |  | -35689
| Space Efficiency (USF/GSF %): |  |  | 70.44% | 70.4%
| Site Work SF: | [5 empty] | 0
| Demolition SF (provide building names in comments): |  |  | 48795 | 48795 |  | -48795
| MACC/Bid Award COST/GSF |  |  | 593.1364 | 682.1686
| Construction Subtotal COST/GSF (Includes change orders) |  |  | 673.3506 | 722.1117
Milestone Dates
| Predesign Complete |  |  | 2022-04-26 | 2021-10-01 | 2022-04-26 | 7 mo.
| Start Design |  |  | 2022-04-26 | 2022-01-01 | 2025-06-01 | 41 mo.
Bid Due Date
| Notice to Proceed |  |  | 2023-09-01 | 2025-07-01
| Substantial Completion |  |  | 2025-09-01 | 2027-07-01
Final Acceptance/Project Close-out Date
Project Costs
| Complete the table below with information from the cost estimate submitted with the predesign study, the cost estimate of the project as funded and the actual cost data to date or at completion. Explain any variances in the Notes column or below. |  |  | Cost Estimate at Approved Predesign | Cost Estimate of the Project as Currently Funded | Actual Costs to Date | Estimate as Currently Funded to Actuals Variance | Notes
Acquisition
| Acquisition Costs Total | [5 empty] | 0
Consultant Services
| Pre-Schematic Design Services |  |  | 220836 | 220836 | 217079.44 | -3756.56 | McGranahan & BCE
| AE Basic Service Fee - Construction Documents |  |  | 1321049 | 1771357.0058 | 1580256.34 | -191100.6658 | MSGS Architects Inc
| Extra Services - Pre-Bid |  |  | 1264428 | 1249672 | 63526.6 | -1186145.4 | Daily Journal of Commerce, PBS, PUD, City of Longview
| AE Basic Service Fee - Bid/Construction/Closeout |  |  | 618484.2048 | 625676 | 498593.09 | -127082.91 | MSGS Architects Inc
| Other Services - Post Bid |  |  | 480295.7952 | 625677 | 142098 | -483579 | Sazan Envirn
| Design Services Contingency |  |  | 201341 | 224661 |  | -224661
| Consultant Services Total |  |  | 4106434 | 4717879.0058 | 2501553.47 | -2216325.5358
Construction
| Site Work |  |  | 3996993 | 7615501.8144 |  | -7615501.8144
| Related Project Costs |  |  |  | 0 |  | 0
| Facility Construction |  |  | 23445649 | 26966354 |  | -26966354
| Maximum Allowable Construction Cost (MACC) Subtotal |  |  | 27442642 | 34581855.8144 | 0 | -34581855.8144
| Construction Contingencies |  |  | 1376889 | 1729092.7907 |  | -1729092.7907
| Non-Taxable Items |  |  | 0 |  |  | 0
| Sales Tax |  |  | 2334383 | 2941242.0927 |  | -2941242.0927
0
0
| Construction Contracts Total |  |  | 31153914 | 39252190.6978 | 0 | -39252190.6978
Other Project Costs
| Equipment |  |  | 1580917 | 1499385.916 |  | -1499385.916
| Art Work |  |  | 185128 | 240805.6145 | 0 | -240805.6145
| Project Management |  |  | 0 | 0 |  | 0
| Other Costs (describe) |  |  | 184300 | 184300 |  | -184300
| Other Project Costs Total |  |  | 1950345 | 178956 | 0 | -178956
| Total Project Costs |  |  | 37210693 | 44149025.7036 | 2501553.47 | -41647472.2336
Additional comments:
Demolish: UFI A09213 Science = 6,994 gsf / UFI A03581 Vocational = 32,250 gsf / UFI A01344 Physical Science = 9,551 gsf Wa Arts Commission: June 2025 in conversation - no start date scheduled

## Photo Gallery (2)
Photo Gallery
Pre-design Concept Sketch 01 2/22/22
Pre-design Concept Sketch 02 2/22/22
Pre-design Concept Sketch 03 2/22/22
SD Concept Sketch 12/13/22
SD Concept Sketch 12/13/22
SDSD Concept Sketch 12/13/22

## Photo Gallery (hidden)
Photo Gallery
Right-click on picture above to change picture to photos of the project.
Triple-click on this text to change the caption.
Picture caption here.
Picture caption here.
Picture caption here.
Picture caption here.
Picture caption here.
image credit: www.bownegroup.com

## Lists (hidden)
Construction Type | Y/N | PM Admin |  |  | Date | Type of Report
Apartment | Yes | DES | 2003-05 | Design-Bid-Build | Select Date from Dropdown | WASHINGTON STATE MAJOR PROJECT STATUS REPORT
Archive building | No | Agency | 2004 | GCCM | July 2025 | WASHINGTON STATE MAJOR PROJECT FINAL CLOSE-OUT REPORT
Armories |  | Other (explain below) | 2005-07 | Design-Build | August 2025
Art galleries |  |  | 2006 | Other (explain below) | September 2025
Auditorium with stage |  |  | 2007-09 |  | October 2025
Auditorium without stage |  |  | 2008 |  | November 2025
Civil Construction | Estimate at PD to Estimate as Funded Variance |  | 2009-11 |  | December 2025
College classroom facilities | Estimate at PD to Actuals Variance |  | 2010 |  | January 2026
Communications Building | Estimate as Currently Funded to Actuals Variance |  | 2011-13 |  | February 2026
Computer rooms |  |  | 2012 |  | March 2026
Convention facilities |  |  | 2013-15 |  | April 2026
Courthouses |  |  | 2014 |  | May 2026
Day care facilities |  |  | 2015-17 |  | June 2026
Detention/correctional facilities - maximum |  |  | 2016 |  | July 2026
Detention/correctional facilities - min & max |  |  | 2017-19 |  | August 2026
Dining halls/institute |  |  | 2018 |  | September 2026
Dormatories |  |  | 2019-21 |  | October 2026
Emergency generator facilities |  |  | 2020 |  | November 2026
Exposition building |  |  | 2021-23 |  | December 2026
Extended care facilities |  |  | 2022 |  | January 2027
Farm structures |  |  | 2023-25 |  | February 2027
Fire and police stations |  |  | 2024 |  | March 2027
Fish hatcheries |  |  |  |  | April 2027
Greenhouses |  |  |  |  | May 2027
Guard towers |  |  |  |  | June 2027
Gymnasiums
Heating and power plants
Hospitals
Industrial buildings without special facilities
Laboratories (Research)
Laundry and cleaning facilities
Libraries
Medical office and clinics
Mental Institutions
Museums
Neighborhood centers and similar recreation facilities
Nursing homes
Observatories
Office buildings
Parking structures and garages
Printing plants
Prototype facilities
Recreational building
Research Facilities
Residence
Schools (primary and secondary)
Science labs (teaching)
Service garages
Sewer treatment plants
Shop and maintenance facilities
Simple loft-type structures (w/o special equipment)
Special schools for physically disadvantaged
Stadium-grandstand type
Stadiums multi-purpose
Storage-cold
Theaters and similar facilities
Transportation terminals
Veterinary hospitals
Vocational schools
Warehouses
Water treatment plants
Other Sch. A Projects
Other Sch. B Projects
Other Sch. C Projects
Formulas:
Date = TEXT(DATE(YEAR(TODAY()), MONTH(TODAY())+ROWS(M2:[Date])-1, DAY(1)), "MMMM YYYY")