## Major Project Report
OFFICE OF FINANCIAL MANAGEMENT
2025-27 Biennium
WASHINGTON STATE MAJOR PROJECT STATUS REPORT
June 2026
| Agency | 699
| Project Name | Lower Columbia College Center for Vocational & Transitional Studies
| OFM Project Number(s) | 40000106
Contact Information
| Name | Nolan Wheeler
| Phone Number | 360-442-2201
| Email | nwheeler@lowercolumbia.edu
Project Information
| Project Description: (Include a brief summary of the project and the programs it supports.) | The Vocational Education & Classroom Building will provide labs, classrooms, informal student study spaces and offices to serve the College's programs in machine trades, manufacturing, welding, information technology and transitional studies.
| Project Status: (Include scope or budget changes, phase updates, identified project delivery issues, discussion of critical path for construction and any potential for project cost overruns or claims.) | Pre-design - Engineering agreement signed 11/10/21. Pre-design report approved by OFM on 4/26/22. Architect selection for design completed on 5/19/22 (firm MSGS selected). Design team completed SD on 12/16/22 and starting on DD phase. A community leader share out of the schematic design was held on 12/13/22 and was very well attended. Project design work delayed pending future state funding. The City of Longview notified LCC on 5/22/2023 that they are requiring LCC to replace the 20-inch watermain that bisects campus from north to south with a new watermain in the 15th Avenue corridor. During the Project Request and Pre-design phase, LCC had been told that the city would only require protection of the existing watermain. This new requirement increases the cost of the project by approximately $3.4MM. Meetings are ongoing to be ready in July 2025. Art in Public Places reached out to start the artwork process. June 2026: Construction activities commenced with utilities relocation and site mobilization. Geopiers, footings, and slab placement were completed. Demolition of the Steam Plant was completed, and demolition of the Physical Science Building was nearing completion. Temporary work at Mark Morris High School, implemented to minimize disruption to school operations during construction, was removed and completed as part of the permanent water main reroute.
Funding
All State & Local Sources, Project Transfers and Amounts
|  | Expenditures |  | Current Plan
| Phase & Fund Type | Prior Expended | 2025-27 Expended | 2025-27 Remaining | 2027-29 Plan | Future Plan | TOTAL | Notes
| Predesign | 0 | 0 | 0 | 0 | 0 | 0
| 057 - State Bldgs. Const Acct | [5 empty] | 0
| XXX - Other State Funding | [5 empty] | 0
| Local Funds | [5 empty] | 0
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| Design | 2585060 | 620940 | 0 | 0 | 0 | 3206000
| 057 - State Bldgs. Const Acct | 2585060 | 620940 |  |  |  | 3206000 | C09
| XXX - Other State Funding | [5 empty] | 0
| Local Funds | [5 empty] | 0
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| Construction | 0 | 8586416.15 | 29781018.85 | 6828565 | 0 | 45196000
| 057 - State Bldgs. Const Acct |  | 8586416.15 | 29781018.85 | 6828565 |  | 45196000 | E01
| XXX - Other State Funding | [5 empty] | 0
| Local Funds | [5 empty] | 0
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| TOTALS | 2585060 | 9207356.15 | 29781018.85 | 6828565 | 0 | 48402000
Details
| Construction Type | College classroom facilities |  | Project Administered By |  | DES
| % of Bldgs. Area that is being remodeled | 0% |  | Art Requirement Applies |  | Yes
| Procurement Method | Design-Bid-Build |  | Higher Ed Institution |  | Yes
Statistics
| Complete the table below with information from the cost estimate submitted with the predesign study, the cost estimate of the project as funded and the actual cost data to date or at completion. Explain any variances in the Notes column or below. |  |  | Estimate at Approved Predesign | Estimate of the Project as Currently Funded | Actuals to Date | Estimate as Currently Funded to Actuals Variance | Notes
| Gross Sq Ft (GSF) |  |  | 46267 | 50694 |  | -50694
| Usable Sq Ft (USF) |  |  | 32590 | 35689 |  | -35689
| Space Efficiency (USF/GSF %): |  |  | 70.44% | 70.4%
| Site Work SF: | [5 empty] | 0
| Demolition SF (provide building names in comments): |  |  | 48795 | 48795 |  | -48795
| MACC/Bid Award COST/GSF |  |  | 593.1364 | 682.1686
| Construction Subtotal COST/GSF (Includes change orders) |  |  | 673.3506 | 774.2966
Milestone Dates
| Predesign Complete |  |  | 2022-04-26 | 2021-10-01 | 2022-04-26 | 7 mo.
| Start Design |  |  | 2022-04-26 | 2022-01-01 | 2025-06-01 | 41 mo.
Bid Due Date
| Notice to Proceed |  |  | 2023-09-01 | 2025-07-01
| Substantial Completion |  |  | 2025-09-01 | 2027-07-01
Final Acceptance/Project Close-out Date
Project Costs
| Complete the table below with information from the cost estimate submitted with the predesign study, the cost estimate of the project as funded and the actual cost data to date or at completion. Explain any variances in the Notes column or below. |  |  | Cost Estimate at Approved Predesign | Cost Estimate of the Project as Currently Funded | Actual Costs to Date | Estimate as Currently Funded to Actuals Variance | Notes
Acquisition
|  |  | Acquisition Costs Total |  |  |  | 0
Consultant Services
| Pre-Schematic Design Services |  |  | 220836 | 220836 | 217079.44 | -3756.56 | McGranahan & BCE
| AE Basic Service Fee - Construction Documents |  |  | 1321049 | 1771357.0058 | 2910865.67 | 1139508.6642 | MSGS Architects Inc, Neely Construction Co
| Extra Services - Pre-Bid |  |  | 1264428 | 1249672 | 766545.06 | -483126.94 | Daily Journal of Commerce, PBS, PUD, City of Longview, Green Business Cert
| AE Basic Service Fee - Bid/Construction/Closeout |  |  | 618484.2048 | 625676 | 498593.09 | -127082.91 | MSGS Architects Inc
| Other Services - Post Bid |  |  | 480295.7952 | 625677 | 188575.5 | -437101.5 | Sazan Envirn, Certerra NW
| Design Services Contingency |  |  | 201341 | 224661 |  | -224661
|  |  | Consultant Services Total | 4106434 | 4717879.0058 | 4581658.76 | -136220.2458
Construction
| Site Work |  |  | 3996993 | 7615501.8144 | 6926497.01 | -689004.8044 | Neeley Construction Co
| Related Project Costs |  |  |  | 0 |  | 0
| Facility Construction |  |  | 23445649 | 26966354 |  | -26966354
|  |  | Maximum Allowable Construction Cost (MACC) Subtotal | 27442642 | 34581855.8144 | 6926497.01 | -27655358.8044
| Construction Contingencies |  |  | 1376889 | 1729092.7907 | 19033.38 | -1710059.4107 | Fire Watch
| Non-Taxable Items |  |  | 0 |  |  | 0
| Sales Tax |  |  | 2334383 | 2941242.0927 |  | -2941242.0927
0
0
|  |  | Construction Contracts Total | 31153914 | 39252190.6978 | 6945530.39 | -32306660.3078
Other Project Costs
| Equipment |  |  | 1580917 | 1499385.916 | 114583.8 | -1384802.116 | Computers/related hardware
| Art Work |  |  | 185128 | 240805.6145 | 42974.32 | -197831.2945
| Project Management |  |  | 0 | 0 |  | 0
| Other Costs (describe) |  |  | 184300 | 184300 |  | -184300
|  |  | Other Project Costs Total | 1950345 | 1924491.5305 | 157558.12 | -1766933.4105
| Total Project Costs |  |  | 37210693 | 45894561.2341 | 11684747.27 | -34209813.9641
Additional comments:
Demolish: UFI A09213 Science = 6,994 gsf / UFI A03581 Vocational = 32,250 gsf / UFI A01344 Physical Science = 9,551 gsf
Wa Arts Commission: June 2026 in conversation - Artist selected, Mary Coss, In design.

## Photo Gallery June 2026
Photo Gallery

## Photo Gallery December 2025
Photo Gallery

## Photo Gallery Design
Photo Gallery
Pre-design Concept Sketch 01 2/22/22
Pre-design Concept Sketch 02 2/22/22
Pre-design Concept Sketch 03 2/22/22
SD Concept Sketch 12/13/22
SD Concept Sketch 12/13/22
SDSD Concept Sketch 12/13/22

## Lists (hidden)
Construction Type | Y/N | PM Admin |  |  | Date | Type of Report
Apartment | Yes | DES | 2003-05 | Design-Bid-Build | Select Date from Dropdown | WASHINGTON STATE MAJOR PROJECT STATUS REPORT
Archive building | No | Agency | 2004 | GCCM | July 2026 | WASHINGTON STATE MAJOR PROJECT FINAL CLOSE-OUT REPORT
Armories |  | Other (explain below) | 2005-07 | Design-Build | August 2026
Art galleries |  |  | 2006 | Other (explain below) | September 2026
Auditorium with stage |  |  | 2007-09 |  | October 2026
Auditorium without stage |  |  | 2008 |  | November 2026
Civil Construction | Estimate at PD to Estimate as Funded Variance |  | 2009-11 |  | December 2026
College classroom facilities | Estimate at PD to Actuals Variance |  | 2010 |  | January 2027
Communications Building | Estimate as Currently Funded to Actuals Variance |  | 2011-13 |  | February 2027
Computer rooms |  |  | 2012 |  | March 2027
Convention facilities |  |  | 2013-15 |  | April 2027
Courthouses |  |  | 2014 |  | May 2027
Day care facilities |  |  | 2015-17 |  | June 2027
Detention/correctional facilities - maximum |  |  | 2016 |  | July 2027
Detention/correctional facilities - min & max |  |  | 2017-19 |  | August 2027
Dining halls/institute |  |  | 2018 |  | September 2027
Dormatories |  |  | 2019-21 |  | October 2027
Emergency generator facilities |  |  | 2020 |  | November 2027
Exposition building |  |  | 2021-23 |  | December 2027
Extended care facilities |  |  | 2022 |  | January 2028
Farm structures |  |  | 2023-25 |  | February 2028
Fire and police stations |  |  | 2024 |  | March 2028
Fish hatcheries |  |  |  |  | April 2028
Greenhouses |  |  |  |  | May 2028
Guard towers |  |  |  |  | June 2028
Gymnasiums
Heating and power plants
Hospitals
Industrial buildings without special facilities
Laboratories (Research)
Laundry and cleaning facilities
Libraries
Medical office and clinics
Mental Institutions
Museums
Neighborhood centers and similar recreation facilities
Nursing homes
Observatories
Office buildings
Parking structures and garages
Printing plants
Prototype facilities
Recreational building
Research Facilities
Residence
Schools (primary and secondary)
Science labs (teaching)
Service garages
Sewer treatment plants
Shop and maintenance facilities
Simple loft-type structures (w/o special equipment)
Special schools for physically disadvantaged
Stadium-grandstand type
Stadiums multi-purpose
Storage-cold
Theaters and similar facilities
Transportation terminals
Veterinary hospitals
Vocational schools
Warehouses
Water treatment plants
Other Sch. A Projects
Other Sch. B Projects
Other Sch. C Projects
Formulas:
Date = TEXT(DATE(YEAR(TODAY()), MONTH(TODAY())+ROWS(M2:[Date])-1, DAY(1)), "MMMM YYYY")