## Major Project Report
OFFICE OF FINANCIAL MANAGEMENT
2025-27 Biennium
WASHINGTON STATE MAJOR PROJECT STATUS REPORT
June 2026
| Agency | 699
| Project Name | Spokane Community College Apprenticeship Center
| OFM Project Number(s) | 40000107
Contact Information
| Name | Clinton Brown
| Phone Number | 509-533-4899
| Email | clinton.brown@ccs.spokane.edu
Project Information
| Project Description: (Include a brief summary of the project and the programs it supports.) | New building construction to support regional Apprenticeship instruction and certification for numerous trades including carpentry, masonry & concrete, electrical, and roofing as well as finishing, flooring, insulating, laborer training, et al. The facility will be flexible to meet rising and changing industry needs for skilled labor demand.
| Project Status: (Include scope or budget changes, phase updates, identified project delivery issues, discussion of critical path for construction and any potential for project cost overruns or claims.) | Project design has been postponed, waiting for confirmation of Construction Funding. The schedule below is based on the most recent information placing funding appropriation in July 2029. As of May 2026, nothing has changed from the previous update.
Funding
All State & Local Sources, Project Transfers and Amounts
|  | Expenditures |  | Current Plan
| Phase & Fund Type | Prior Expended | 2025-27 Expended | 2025-27 Remaining | 2027-29 Plan | Future Plan | TOTAL | Notes
| Predesign | 0 | 0 | 0 | 0 | 0 | 0
| 057 - State Bldgs. Const Acct | [5 empty] | 0
| XXX - Other State Funding | [5 empty] | 0
| Local Funds | [5 empty] | 0
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| Design | 373000 | 0 | 2995000 | 0 | 0 | 3368000
| 057 - State Bldgs. Const Acct | 373000 |  | 2995000 |  |  | 3368000 | C10
| XXX - Other State Funding | [5 empty] | 0
| Local Funds | [5 empty] | 0
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| Construction | 0 | 0 | 0 | 0 | 0 | 0
| 057 - State Bldgs. Const Acct | [5 empty] | 0 | Future
| XXX - Other State Funding | [5 empty] | 0
| Local Funds | [5 empty] | 0
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| TOTALS | 373000 | 0 | 2995000 | 0 | 0 | 3368000
Details
| Construction Type | Vocational schools |  | Project Administered By |  | DES
| % of Bldgs. Area that is being remodeled | 0% |  | Art Requirement Applies |  | Yes
| Procurement Method | GCCM |  | Higher Ed Institution |  | Yes
Statistics
| Complete the table below with information from the cost estimate submitted with the predesign study, the cost estimate of the project as funded and the actual cost data to date or at completion. Explain any variances in the Notes column or below. |  |  | Estimate at Approved Predesign | Estimate of the Project as Currently Funded | Actuals to Date | Estimate as Currently Funded to Actuals Variance | Notes
| Gross Sq Ft (GSF) |  |  | 59683 | 59683 |  | -59683
| Usable Sq Ft (USF) |  |  | 45695 | 45695 |  | -45695
| Space Efficiency (USF/GSF %): |  |  | 76.56% | 76.56%
| Site Work SF: | [5 empty] | 0
| Demolition SF (provide building names in comments): |  |  | 46565 | 46565 |  | -46565
| MACC/Bid Award COST/GSF |  |  | 434.3115 | 579.1185
| Construction Subtotal COST/GSF (Includes change orders) |  |  | 498.8218 | 666.0452
Milestone Dates
| Predesign Complete |  |  | 2022-06-01 | 2022-06-01 | 2022-09-27 | 4 mo.
| Start Design |  |  | 2022-07-01 | 2028-01-15 |  |  | const fndg delay
| Bid Due Date |  |  |  | 2029-07-01 |  |  | const fndg delay
| Notice to Proceed |  |  | 2023-06-01 | 2029-08-15 |  |  | const fndg delay
| Substantial Completion |  |  | 2024-06-01 | 2031-06-30 |  |  | const fndg delay
| Final Acceptance/Project Close-out Date |  |  |  | 2031-09-30
Project Costs
| Complete the table below with information from the cost estimate submitted with the predesign study, the cost estimate of the project as funded and the actual cost data to date or at completion. Explain any variances in the Notes column or below. |  |  | Cost Estimate at Approved Predesign | Cost Estimate of the Project as Currently Funded | Actual Costs to Date | Estimate as Currently Funded to Actuals Variance | Notes
Acquisition
|  |  | Acquisition Costs Total |  |  |  | 0
Consultant Services
| Pre-Schematic Design Services |  |  | 204468 | 203917 | 201640.2 | -2276.8
| AE Basic Service Fee - Construction Documents |  |  | 1276066 | 1718424 | 0 | -1718424
| Extra Services - Pre-Bid |  |  | 668455 | 1092437 | 33919 | -1058518
| AE Basic Service Fee - Bid/Construction/Closeout |  |  | 586380.5181 | 1301762 | 0 | -1301762
| Other Services - Post Bid |  |  | 61997 |  | 0 | 0
| Design Services Contingency |  |  | 142433 | 221973 | 0 | -221973
|  |  | Consultant Services Total | 2939799.5181 | 4538513 | 235559.2 | -4302953.8
Construction
| Site Work |  |  | 3118736 | 3764219 | 0 | -3764219
| Related Project Costs |  |  |  |  | 0 | 0
| Facility Construction |  |  | 22802280 | 30799309 | 0 | -30799309
|  |  | Maximum Allowable Construction Cost (MACC) Subtotal | 25921016 | 34563528 | 0 | -34563528
| Construction Contingencies |  |  | 1297894 | 1732507 | 0 | -1732507
| Non-Taxable Items |  |  | 129790 | 173251 |  | -173251
| Sales Tax |  |  | 2422483 | 3282288 | 0 | -3282288
| GCCM Costs | [5 empty] | 0
| GCCM Risk Contingency | [5 empty] | 0
|  |  | Construction Contracts Total | 29771183 | 39751574 | 0 | -39751574
Other Project Costs
| Equipment |  |  | 834722 | 1178177 | 0 | -1178177
| Art Work |  |  | 169361 | 230347 | 0 | -230347
| Project Management |  |  | 326516 | 601161 | 136508.82 | -464652.18
| Other Costs (describe) |  |  |  | 0 | 161.65 | 161.65 | advertising
|  |  | Other Project Costs Total | 1330599 | 2009685 | 136670.47 | -1873014.53
| Total Project Costs |  |  | 34041581.5181 | 46299772 | 372229.67 | -45927542.33
Additional comments:
Demolish: UFI A00226 = 19,497 gsf / UFI A10412 = 24,063 gsf / UFI A21469 = 1,505 gsf / UFI A25178 = 1,500 gsf
Wa Arts Commission: June 2026 not started, building in design.

## Photo Gallery
Photo Gallery
Schematic Floor Plan - Pre-Design
Schematic Sketch - Pre-Design ("Gaining Momemtum" plan)-Selected
Schematic Sketch - Pre-Design ("Gallery of Trades" plan)
Schematic Sketch - Pre-Design ("The Line Up" plan)

## Lists (hidden)
Construction Type | Y/N | PM Admin |  |  | Date | Type of Report
Apartment | Yes | DES | 2003-05 | Design-Bid-Build | Select Date from Dropdown | WASHINGTON STATE MAJOR PROJECT STATUS REPORT
Archive building | No | Agency | 2004 | GCCM | June 2026 | WASHINGTON STATE MAJOR PROJECT FINAL CLOSE-OUT REPORT
Armories |  | Other (explain below) | 2005-07 | Design-Build | July 2026
Art galleries |  |  | 2006 | Other (explain below) | August 2026
Auditorium with stage |  |  | 2007-09 |  | September 2026
Auditorium without stage |  |  | 2008 |  | October 2026
Civil Construction | Estimate at PD to Estimate as Funded Variance |  | 2009-11 |  | November 2026
College classroom facilities | Estimate at PD to Actuals Variance |  | 2010 |  | December 2026
Communications Building | Estimate as Currently Funded to Actuals Variance |  | 2011-13 |  | January 2027
Computer rooms |  |  | 2012 |  | February 2027
Convention facilities |  |  | 2013-15 |  | March 2027
Courthouses |  |  | 2014 |  | April 2027
Day care facilities |  |  | 2015-17 |  | May 2027
Detention/correctional facilities - maximum |  |  | 2016 |  | June 2027
Detention/correctional facilities - min & max |  |  | 2017-19 |  | July 2027
Dining halls/institute |  |  | 2018 |  | August 2027
Dormatories |  |  | 2019-21 |  | September 2027
Emergency generator facilities |  |  | 2020 |  | October 2027
Exposition building |  |  | 2021-23 |  | November 2027
Extended care facilities |  |  | 2022 |  | December 2027
Farm structures |  |  | 2023-25 |  | January 2028
Fire and police stations |  |  | 2024 |  | February 2028
Fish hatcheries |  |  |  |  | March 2028
Greenhouses |  |  |  |  | April 2028
Guard towers |  |  |  |  | May 2028
Gymnasiums
Heating and power plants
Hospitals
Industrial buildings without special facilities
Laboratories (Research)
Laundry and cleaning facilities
Libraries
Medical office and clinics
Mental Institutions
Museums
Neighborhood centers and similar recreation facilities
Nursing homes
Observatories
Office buildings
Parking structures and garages
Printing plants
Prototype facilities
Recreational building
Research Facilities
Residence
Schools (primary and secondary)
Science labs (teaching)
Service garages
Sewer treatment plants
Shop and maintenance facilities
Simple loft-type structures (w/o special equipment)
Special schools for physically disadvantaged
Stadium-grandstand type
Stadiums multi-purpose
Storage-cold
Theaters and similar facilities
Transportation terminals
Veterinary hospitals
Vocational schools
Warehouses
Water treatment plants
Other Sch. A Projects
Other Sch. B Projects
Other Sch. C Projects
Formulas:
Date = TEXT(DATE(YEAR(TODAY()), MONTH(TODAY())+ROWS(M2:[Date])-1, DAY(1)), "MMMM YYYY")