## Major Project Report
OFFICE OF FINANCIAL MANAGEMENT
2025-27 Biennium
WASHINGTON STATE MAJOR PROJECT STATUS REPORT
June 2026
| Agency | 699
| Project Name | Columbia Basin: Performing Arts Building
| OFM Project Number(s) | 40000108
Contact Information
| Name | Performing Arts Building Replacement
| Phone Number | 509-542-4727
| Email | bdexter@columbiabasin.edu
Project Information
| Project Description: (Include a brief summary of the project and the programs it supports.) | Columbia Basin College proposes to replace the existing Performing Arts Center (P Building) with a new 58,668 GSF facility to address significant structural, functional, and programmatic deficiencies that limit instructional effectiveness and student access. The project will support Visual Arts, Performing Arts (Theater and Music), Multimedia, and Innovation Center programs by providing modern, flexible, and interdisciplinary learning environments aligned with current educational and workforce needs.
| Project Status: (Include scope or budget changes, phase updates, identified project delivery issues, discussion of critical path for construction and any potential for project cost overruns or claims.) | The project was funded in the 2025–27 capital budget and is currently in the predesign phase, with submission to OFM pending approval. The scope includes full replacement of the existing P Building with an expanded facility to address program deficiencies and support modern, interdisciplinary arts instruction, with the total project budget aligned at this stage with legislative assumptions. Advancement beyond predesign and timely OFM approval will be critical to maintaining schedule, and while major delivery issues have not yet been identified, risks of cost escalation or refinement of scope may emerge as design progresses and detailed cost estimates are developed.
Funding
All State & Local Sources, Project Transfers and Amounts
|  | Expenditures |  | Current Plan
| Phase & Fund Type | Prior Expended | 2025-27 Expended | 2025-27 Remaining | 2027-29 Plan | Future Plan | TOTAL | Notes
| Predesign | 0 | 0 | 0 | 0 | 0 | 0
| 057 - State Bldg. Const Acct | 0 |  |  |  |  | 0
| XXX - Other State Funding | [5 empty] | 0
| Local Funds | [5 empty] | 0
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| Design | 0 | 0 | 0 | 0 | 0 | 0
| 057 - State Bldg. Const Acct | [5 empty] | 0
| XXX - Other State Funding | [5 empty] | 0
| Local Funds | [5 empty] | 0
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| Design & Construction | 0 | 250491 | 45355045 | 8942464 | 8000000 | 62548000
| 057 - State Bldg. Const Acct |  | 250491 | 45355045 | 8942464 |  | 54548000 | E02
| XXX - Other State Funding | [5 empty] | 0
| 147 - Local Funds |  |  |  |  | 8000000 | 8000000 | S802
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| TOTALS | 0 | 250491 | 45355045 | 8942464 | 8000000 | 62548000
Details
| Construction Type | College classroom facilities |  | Project Administered By |  | DES
| % of Bldg. Area that is being remodeled | 100% |  | Art Requirement Applies |  | Yes
| Procurement Method | Design-Build |  | Higher Ed Institution |  | Yes
Statistics
| Complete the table below with information from the cost estimate submitted with the predesign study, the cost estimate of the project as funded and the actual cost data to date or at completion. Explain any variances in the Notes column or below. |  |  | Estimate at Approved Predesign | Estimate of the Project as Currently Funded | Actuals to Date | Estimate as Currently Funded to Actuals Variance | Notes
| Gross Sq Ft (GSF) |  |  | 58668 | 51285 | 51285 | 0
| Usable Sq Ft (USF) |  |  | 42924 | 31540 | 31540 | 0
| Space Efficiency (USF/GSF %): |  |  | 73.16% | 61.5% | 61.5% | 0%
| Site Work SF: | [5 empty] | 0
| Demolition SF (provide building names in comments): |  |  | 37170 | 37170 |  | -37170 | A08055 (P Building)
| MACC/Bid Award COST/GSF |  |  | 593.293 | 746.8222 | 0 | -746.8222
| Construction Subtotal COST/GSF (Includes change orders) |  |  | 678.4613 | 964.8225 | 0 | -964.8225
Milestone Dates
| Predesign Complete |  |  | 2026-02-01 | 2026-02-01 | 2026-06-01 | 4 mo.
| Start Design |  |  | 2027-02-01 | 2028-10-01
Bid Due Date
| Notice to Proceed |  |  | 2028-05-01 | 2030-05-01
| Substantial Completion |  |  | 2029-12-29 | 2030-05-30
| Final Acceptance/Project Close-out Date |  |  | 2028-01-01 | 2028-01-01 | 2030-05-30 | 29 mo.
Project Costs
| Complete the table below with information from the cost estimate submitted with the predesign study, the cost estimate of the project as funded and the actual cost data to date or at completion. Explain any variances in the Notes column or below. |  |  | Cost Estimate at Approved Predesign | Cost Estimate of the Project as Currently Funded | Actual Costs to Date | Estimate as Currently Funded to Actuals Variance | Notes
Acquisition
|  |  | Acquisition Costs Total | 0 | 0 | 0 | 0
Consultant Services
| Pre-Schematic Design Services |  |  | 359562 | 393338 |  | -393338
| AE Basic Service Fee - Construction Documents |  |  | 1808928 | 2264148 |  | -2264148
| Extra Services - Pre-Bid |  |  | 1686322 | 1633531 | 250491 | -1383040 | Auditor, Hazmat, Survey
| AE Basic Service Fee - Bid/Construction/Closeout |  |  | 1707667 | 1707667 |  | -1707667
| Other Services - Post Bid |  |  | 278636 | 344819 |  | -344819
| Design Services Contingency |  |  |  | 1026624 |  | -1026624
|  |  | Consultant Services Total | 5841115 | 7370127 | 250491 | -7119636
Construction
| Site Work |  |  | 2147707 | 1948208 |  | -1948208
| Related Project Costs |  |  | 106633 | 1833501 |  | -1833501
| Facility Construction |  |  | 32552976 | 34519065 |  | -34519065
|  |  | Maximum Allowable Construction Cost (MACC) Subtotal | 34807316 | 38300774 |  | -38300774
| Construction Contingencies |  |  | 1743572 | 3991307 |  | -3991307
| Non-Taxable Items |  |  | 0 | 3424845 |  | -3424845
| Sales Tax |  |  | 3253082 | 3763995 |  | -3763995
| Design-Build Costs | [5 empty] | 0
0
|  |  | Construction Contracts Total | 39803970 | 49480921 | 0 | -49480921
Other Project Costs
| Equipment |  |  | 8479073 | 2382642 |  | -2382642
| Art Work |  |  | 271382 | 271382 | 0 | -271382
| Project Management |  |  | 0 | 2714041 |  | -2714041
| Other Costs (describe) |  |  | 152316 | 306169 |  | -306169
|  |  | Other Project Costs Total | 8902771 | 5674234 | 0 | -5674234
| Total Project Costs |  |  | 54547856 | 62525282 | 250491 | -62274791
Additional comments:
Auditor, Hazmat, Survey are all under contract but have they have not yet billed for any services.
June 2026 - Wa Arts - pre-conversations, first meeting pending.

## Photo Gallery
Photo Gallery
Kickoff Faculty Discussion prior to Architect selection
Student Focus Group for Predesign study
Theater Faculty giving the consultants as tour of existing spaces
Brain storming session with Faculty and consultants.
Watching the concert band performance
Consultant going through a 3D model of some proposed ideas with Faculty and VPI

## Lists (hidden)
Construction Type | Y/N | PM Admin |  |  | Date | Type of Report
Apartment | Yes | DES | 2003-05 | Design-Bid-Build | Select Date from Dropdown | WASHINGTON STATE MAJOR PROJECT STATUS REPORT
Archive building | No | Agency | 2004 | GCCM | June 2026 | WASHINGTON STATE MAJOR PROJECT FINAL CLOSE-OUT REPORT
Armories |  | Other (explain below) | 2005-07 | Design-Build | July 2026
Art galleries |  |  | 2006 | Other (explain below) | August 2026
Auditorium with stage |  |  | 2007-09 |  | September 2026
Auditorium without stage |  |  | 2008 |  | October 2026
Civil Construction | Estimate at PD to Estimate as Funded Variance |  | 2009-11 |  | November 2026
College classroom facilities | Estimate at PD to Actuals Variance |  | 2010 |  | December 2026
Communications Building | Estimate as Currently Funded to Actuals Variance |  | 2011-13 |  | January 2027
Computer rooms |  |  | 2012 |  | February 2027
Convention facilities |  |  | 2013-15 |  | March 2027
Courthouses |  |  | 2014 |  | April 2027
Day care facilities |  |  | 2015-17 |  | May 2027
Detention/correctional facilities - maximum |  |  | 2016 |  | June 2027
Detention/correctional facilities - min & max |  |  | 2017-19 |  | July 2027
Dining halls/institute |  |  | 2018 |  | August 2027
Dormatories |  |  | 2019-21 |  | September 2027
Emergency generator facilities |  |  | 2020 |  | October 2027
Exposition building |  |  | 2021-23 |  | November 2027
Extended care facilities |  |  | 2022 |  | December 2027
Farm structures |  |  | 2023-25 |  | January 2028
Fire and police stations |  |  | 2024 |  | February 2028
Fish hatcheries |  |  |  |  | March 2028
Greenhouses |  |  |  |  | April 2028
Guard towers |  |  |  |  | May 2028
Gymnasiums
Heating and power plants
Hospitals
Industrial buildings without special facilities
Laboratories (Research)
Laundry and cleaning facilities
Libraries
Medical office and clinics
Mental Institutions
Museums
Neighborhood centers and similar recreation facilities
Nursing homes
Observatories
Office buildings
Parking structures and garages
Printing plants
Prototype facilities
Recreational building
Research Facilities
Residence
Schools (primary and secondary)
Science labs (teaching)
Service garages
Sewer treatment plants
Shop and maintenance facilities
Simple loft-type structures (w/o special equipment)
Special schools for physically disadvantaged
Stadium-grandstand type
Stadiums multi-purpose
Storage-cold
Theaters and similar facilities
Transportation terminals
Veterinary hospitals
Vocational schools
Warehouses
Water treatment plants
Other Sch. A Projects
Other Sch. B Projects
Other Sch. C Projects
Formulas:
Date = TEXT(DATE(YEAR(TODAY()), MONTH(TODAY())+ROWS(M2:[Date])-1, DAY(1)), "MMMM YYYY")