## Major Project Report
OFFICE OF FINANCIAL MANAGEMENT
2025-27 Biennium
WASHINGTON STATE MAJOR PROJECT STATUS REPORT
June 2026
| Agency | 699
| Project Name | Skagit Valley College Library and Culinary Arts
| OFM Project Number(s) | 40000110
Contact Information
| Name | Tim Wheeler
| Phone Number | 360-416-7751
| Email | tim.wheeler@skagit.edu
Project Information
| Project Description: (Include a brief summary of the project and the programs it supports.) | This project includes the demolition of the Norwood Cole Library building number (04070) and also the Administrative Annex building (04037). The programs supported by this project include, Library & Media/eLearning Services, Reference Help, Student On-line Services, Culinary Arts, Student Support Services, Math Labs, Tutoring and IT Help Desk Services.
| Project Status: (Include scope or budget changes, phase updates, identified project delivery issues, discussion of critical path for construction and any potential for project cost overruns or claims.) | 06-18-2026: This project is on hold and no change in status since our last Update in December of 2025. Our project team completed 90% construction documents in the 2023-2025 biennium, including $336,554.48. in local funding needed to complete design documents to a 90% complete bid ready status. I have attached a copy of the project Design Book to the email associated with this Status Update which summarizes our design team's work to date. For this status update, I have adjusted cells E/67, E/68, E/69 and E/70 to reflect projections for construction funding to be allocated to the College in the 2029-2031 biennium. In the upcoming summer of 2026 the college will begin displacing and relocation programs and personnel out of the Norwood Cole Library and the Administrative Annex buildings. We hope to have these buildings as ready for demolition as possible in preparation for construction funding to be approved July 1, 2029.
Funding
All State & Local Sources, Project Transfers and Amounts
|  | Expenditures |  | Current Plan
| Phase & Fund Type | Prior Expended | 2025-27 Expended | 2025-27 Remaining | 2027-29 Plan | Future Plan | TOTAL | Notes
| Predesign | 0 | 0 | 0 | 0 | 0 | 0
| 057 - State Bldgs. Const Acct | [5 empty] | 0
| XXX - Other State Funding | [5 empty] | 0
| Local Funds | [5 empty] | 0
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| Design | 2581109.48 | 0 | 3674890.52 | 0 | 0 | 6256000
| 057 - State Bldgs. Const Acct | 2244555 | 0 | 12445 |  |  | 2257000 | C12
| XXX - Other State Funding | [5 empty] | 0
| Local Funds | 336554.48 | 0 | 3662445.52 |  |  | 3999000 | Q690
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| Construction | 0 | 0 | 0 | 0 | 0 | 0
| 057 - State Bldgs. Const Acct | [5 empty] | 0 | Future
| XXX - Other State Funding | [5 empty] | 0
| 147 - Local Funds | [5 empty] | 0
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| TOTALS | 2581109.48 | 0 | 3674890.52 | 0 | 0 | 6256000
Details
| Construction Type | Libraries |  | Project Administered By |  | DES
| % of Bldgs. Area that is being remodeled | 0% |  | Art Requirement Applies |  | Yes
| Procurement Method | Design-Bid-Build |  | Higher Ed Institution |  | Yes
Statistics
| Complete the table below with information from the cost estimate submitted with the predesign study, the cost estimate of the project as funded and the actual cost data to date or at completion. Explain any variances in the Notes column or below. |  |  | Estimate at Approved Predesign | Estimate of the Project as Currently Funded | Actuals to Date | Estimate as Currently Funded to Actuals Variance | Notes
| Gross Sq Ft (GSF) |  |  | 43200 | 39366 |  | -39366
| Usable Sq Ft (USF) |  |  | 32180 | 30350 |  | -30350
| Space Efficiency (USF/GSF %): |  |  | 74.49% | 77.1%
| Site Work SF: | [5 empty] | 0
| Demolition SF (provide building names in comments): |  |  | 26730 | 26730 |  | -26730
| MACC/Bid Award COST/GSF |  |  | 556.0066 | 750.6265
| Construction Subtotal COST/GSF (Includes change orders) |  |  | 635.2921 | 857.8179
Milestone Dates
| Predesign Complete |  |  | 2022-04-01 | 2022-04-01 | 2022-08-01 | 4 mo.
| Start Design |  |  | 2022-07-01 | 2022-07-01 | 2023-07-30 | 13 mo.
| Bid Due Date |  |  | 2029-12-01 |  |  | 0 mo.
| Notice to Proceed |  |  | 2030-02-01 |  |  | 0 mo.
| Substantial Completion |  |  | 2031-09-01 |  |  | 0 mo.
| Final Acceptance/Project Close-out Date |  |  | 2031-11-01 |  |  | 0 mo.
Project Costs
| Complete the table below with information from the cost estimate submitted with the predesign study, the cost estimate of the project as funded and the actual cost data to date or at completion. Explain any variances in the Notes column or below. |  |  | Cost Estimate at Approved Predesign | Cost Estimate of the Project as Currently Funded | Actual Costs to Date | Estimate as Currently Funded to Actuals Variance | Notes
Acquisition
|  |  | Acquisition Costs Total |  |  |  | 0
Consultant Services
| Pre-Schematic Design Services |  |  | 206717 | 206778 | 204736.07 | -2041.93
| AE Basic Service Fee - Construction Documents |  |  | 1392091 | 1397339 | 1044205.6 | -353133.4
| Extra Services - Pre-Bid |  |  | 1337196 | 1315415 | 1184738.3 | -130676.7
| AE Basic Service Fee - Bid/Construction/Closeout |  |  | 553200.1536 | 658819 | 0 | -658819
| Other Services - Post Bid |  |  | 484069 | 1181171 | 0 | -1181171
| Design Services Contingency |  |  | 204273 | 249363 | 0 | -249363
|  |  | Consultant Services Total | 4177546.1536 | 5008885 | 2433679.97 | -2575205.03
Construction
| Site Work |  |  | 4909517 | 5794386 |  | -5794386
| Related Project Costs |  |  |  | 0 |  | 0
| Facility Construction |  |  | 19109967 | 23754775 |  | -23754775
|  |  | Maximum Allowable Construction Cost (MACC) Subtotal | 24019484 | 29549161 | 0 | -29549161
| Construction Contingencies |  |  | 1205347 | 1488333 |  | -1488333
| Non-Taxable Items | [5 empty] | 0
| Sales Tax |  |  | 2219786 | 2731366 |  | -2731366
0
0
|  |  | Construction Contracts Total | 27444617 | 33768860 | 0 | -33768860
Other Project Costs
| Equipment |  |  | 1678894 | 2860889 |  | -2860889
| Art Work |  |  | 125126 | 197172 | 0 | -197172
| Project Management |  |  | 386764 | 395513 |  | -395513
| Other Costs (describe) |  |  | 1137437 | 1399235 |  | -1399235
|  |  | Other Project Costs Total | 3328221 | 4852809 | 0 | -4852809
| Total Project Costs |  |  | 34950384.1536 | 43630554 | 2433679.97 | -41196874.03
Additional comments:
Demolish UFI A05680 = 26,730 gsf
Wa Arts Commission: June 2026 - initial meeting completed, no selection process yet.

## Photo Gallery (2)
Photo Gallery
Project Location

## Lists (hidden)
Construction Type | Y/N | PM Admin |  |  | Date | Type of Report
Apartment | Yes | DES | 2003-05 | Design-Bid-Build | Select Date from Dropdown | WASHINGTON STATE MAJOR PROJECT STATUS REPORT
Archive building | No | Agency | 2004 | GCCM | July 2026 | WASHINGTON STATE MAJOR PROJECT FINAL CLOSE-OUT REPORT
Armories |  | Other (explain below) | 2005-07 | Design-Build | August 2026
Art galleries |  |  | 2006 | Other (explain below) | September 2026
Auditorium with stage |  |  | 2007-09 |  | October 2026
Auditorium without stage |  |  | 2008 |  | November 2026
Civil Construction | Estimate at PD to Estimate as Funded Variance |  | 2009-11 |  | December 2026
College classroom facilities | Estimate at PD to Actuals Variance |  | 2010 |  | January 2027
Communications Building | Estimate as Currently Funded to Actuals Variance |  | 2011-13 |  | February 2027
Computer rooms |  |  | 2012 |  | March 2027
Convention facilities |  |  | 2013-15 |  | April 2027
Courthouses |  |  | 2014 |  | May 2027
Day care facilities |  |  | 2015-17 |  | June 2027
Detention/correctional facilities - maximum |  |  | 2016 |  | July 2027
Detention/correctional facilities - min & max |  |  | 2017-19 |  | August 2027
Dining halls/institute |  |  | 2018 |  | September 2027
Dormatories |  |  | 2019-21 |  | October 2027
Emergency generator facilities |  |  | 2020 |  | November 2027
Exposition building |  |  | 2021-23 |  | December 2027
Extended care facilities |  |  | 2022 |  | January 2028
Farm structures |  |  | 2023-25 |  | February 2028
Fire and police stations |  |  | 2024 |  | March 2028
Fish hatcheries |  |  |  |  | April 2028
Greenhouses |  |  |  |  | May 2028
Guard towers |  |  |  |  | June 2028
Gymnasiums
Heating and power plants
Hospitals
Industrial buildings without special facilities
Laboratories (Research)
Laundry and cleaning facilities
Libraries
Medical office and clinics
Mental Institutions
Museums
Neighborhood centers and similar recreation facilities
Nursing homes
Observatories
Office buildings
Parking structures and garages
Printing plants
Prototype facilities
Recreational building
Research Facilities
Residence
Schools (primary and secondary)
Science labs (teaching)
Service garages
Sewer treatment plants
Shop and maintenance facilities
Simple loft-type structures (w/o special equipment)
Special schools for physically disadvantaged
Stadium-grandstand type
Stadiums multi-purpose
Storage-cold
Theaters and similar facilities
Transportation terminals
Veterinary hospitals
Vocational schools
Warehouses
Water treatment plants
Other Sch. A Projects
Other Sch. B Projects
Other Sch. C Projects
Formulas:
Date = TEXT(DATE(YEAR(TODAY()), MONTH(TODAY())+ROWS(M2:[Date])-1, DAY(1)), "MMMM YYYY")