## Major Project Report
OFFICE OF FINANCIAL MANAGEMENT
2025-27 Biennium
WASHINGTON STATE MAJOR PROJECT STATUS REPORT
June 2026
| Agency | 699
| Project Name | Bates Technical College Fire Service Training Center
| OFM Project Number(s) | 40000130
Contact Information
| Name | Bob Roehl
| Phone Number | 206-276-0561
| Email | robert.roehl@batestech.edu
Project Information
| Project Description: (Include a brief summary of the project and the programs it supports.) | The Fire Service Training Center will be a ~45,000 GSF facility with one main building (classrooms, other functions) and one drill zone area that includes a training tower, located at the northwest corner of our South Campus. It will serve as the most prominent structure visible from the north campus entry. The Fire Service Training Center will support the multiple pathways and rich partnerships associated with fire service training education. It will include classrooms, break-out spaces for collaborative learning or small group instruction, a computer lab, a physical fitness room, fire station apparatus mock up facility including vehicle bays, hose and equipment maintenance and storage, fire station crew support mock-up facility, administrative support area and live fire training yard with drill towers, command training center and covered props/storage area.
| Project Status: (Include scope or budget changes, phase updates, identified project delivery issues, discussion of critical path for construction and any potential for project cost overruns or claims.) | The selected D-B Team (BNBuilders-Miller Hull-MW Studios) is now under contract with a November 9, 2023 Notice to Proceed date. Pre-design verification and Design Phase activities began in earnest. The project completed the 20% Schematic Design Phase, which included cost and scope review with the full Design-Build Team. The project then moved forward and has completed 100% Design Documents and Permit Review Documents, in anticipation of the Guaranteed Maximum Price (GMP) Phase, which has been completed. Site development started on April 28th, with all needed permits approved. The last six months has seen the Construction Phase moving forward and has remained on schedule for a mid-September Substantial Completion. The FF&E order is nearing completion for submittal/approval. The Design-Build Team members has used their trusting, positive working relationship to help move the project forward.
Funding
All State & Local Sources, Project Transfers and Amounts
|  | Expenditures |  | Current Plan
| Phase & Fund Type | Prior Expended | 2025-27 Expended | 2025-27 Remaining | 2027-29 Plan | Future Plan | TOTAL | Notes
| Predesign | 0 | 0 | 0 | 0 | 0 | 0
| 057 - State Bldgs. Const Acct | [5 empty] | 0
| XXX - Other State Funding | [5 empty] | 0
| Local Funds | [5 empty] | 0
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| Design | 2801999.93 | 0 | 0 | 0 | 0 | 2801999.93
| 057 - State Bldgs. Const Acct | 2801999.93 |  |  |  |  | 2801999.93 | A10
| XXX - Other State Funding | [5 empty] | 0
| Local Funds | [5 empty] | 0
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| Construction | 4089426.52 | 19383326.1 | 17661647.38 | 0 | 0 | 41134400
| 057 - State Bldgs. Const Acct | 4089426.52 | 19383326.1 | 14662247.38 |  |  | 38135000 | D02
| XXX - Other State Funding | [5 empty] | 0
| 147 - Local Funds |  | 0 | 2000000 |  |  | 2000000 | R865
| 145 - Local Funds |  | 0 | 999400 |  |  | 999400 | R864
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| TOTALS | 6891426.45 | 19383326.1 | 17661647.38 | 0 | 0 | 43936399.93
Details
| Construction Type | College classroom facilities |  | Project Administered By |  | DES
| % of Bldgs. Area that is being remodeled | 0% |  | Art Requirement Applies |  | Yes
| Procurement Method | Design-Build |  | Higher Ed Institution |  | Yes
Statistics
| Complete the table below with information from the cost estimate submitted with the predesign study, the cost estimate of the project as funded and the actual cost data to date or at completion. Explain any variances in the Notes column or below. |  |  | Estimate at Approved Predesign | Estimate of the Project as Currently Funded | Actuals to Date | Estimate as Currently Funded to Actuals Variance | Notes
| Gross Sq Ft (GSF) |  |  | 54500 | 43094 |  | -43094
| Usable Sq Ft (USF) |  |  | 45166 | 32173 |  | -32173
| Space Efficiency (USF/GSF %): |  |  | 82.87% | 74.66%
| Site Work SF: | [5 empty] | 0
| Demolition SF (provide building names in comments): | [5 empty] | 0
| MACC/Bid Award COST/GSF |  |  | 418.0336 | 686.7969
| Construction Subtotal COST/GSF (Includes change orders) |  |  | 479.3533 | 836.7626
Milestone Dates
| Predesign Complete |  |  | 2020-08-01 | 2020-08-01 | 2020-08-01 | 0 mo.
| Start Design |  |  | 2023-11-09 | 2023-07-01 | 2023-07-01 | 0 mo.
Bid Due Date
| Notice to Proceed |  |  | 2023-11-09 | 2023-11-09 | 2023-11-09 | 0 mo.
| Substantial Completion |  |  | TBD | 2026-09-15
| Final Acceptance/Project Close-out Date |  |  | TBD | 2026-12-31
Project Costs
| Complete the table below with information from the cost estimate submitted with the predesign study, the cost estimate of the project as funded and the actual cost data to date or at completion. Explain any variances in the Notes column or below. |  |  | Cost Estimate at Approved Predesign | Cost Estimate of the Project as Currently Funded | Actual Costs to Date | Estimate as Currently Funded to Actuals Variance | Notes
Acquisition
|  |  | Acquisition Costs Total |  |  |  | 0
Consultant Services
| Pre-Schematic Design Services |  |  | 215439 | 249302 | 1783936.19 | 1534634.19
| AE Basic Service Fee - Construction Documents |  |  | 0 | 0 |  | 0
| Extra Services - Pre-Bid |  |  | 618467 | 540278 | 6851 | -533427
| AE Basic Service Fee - Bid/Construction/Closeout |  |  | 0 | 0 |  | 0
| Other Services - Post Bid |  |  | 0 | 0 |  | 0
| Design Services Contingency |  |  | 44288 | 40971 |  | -40971
|  |  | Consultant Services Total | 878194 | 830551 | 1790787.19 | 960236.19
Construction
| Site Work |  |  | 2898071 | 4251166 |  | -4251166
| Related Project Costs |  |  | 157650 | 189867 |  | -189867
| Facility Construction |  |  | 19727112 | 25155794 | 21410204.13 | -3745589.87
|  |  | Maximum Allowable Construction Cost (MACC) Subtotal | 22782833 | 29596827 | 21410204.13 | -8186622.87
| Construction Contingencies |  |  | 1143998 | 1484326 |  | -1484326
| Non-Taxable Items |  |  | -2763594 | -2109619 |  | 2109619
| Sales Tax |  |  | 2767196 | 3367292 |  | -3367292
| Design-Build Costs |  |  | 2194323 | 3720620 | 2957782 | -762838
0
|  |  | Construction Contracts Total | 26124756 | 36059446 | 24367986.13 | -11691459.87
Other Project Costs
| Equipment |  |  | 2971200 | 2923435 |  | -2923435
| Art Work |  |  | 113914 | 203665 | 46849.75 | -156815.25
| Project Management |  |  | 1022568 | 293150 | 69097 | -224053
| Other Costs (describe) |  |  | 683150 | 626993 |  | -626993
|  |  | Other Project Costs Total | 4790832 | 4047243 | 115946.75 | -3931296.25
| Total Project Costs |  |  | 31793782 | 40937240 | 26274720.07 | -14662519.93
Additional comments:
The commercial driver's license (CDL) program at Bates is being reconfigured to align with standard industry practices for length of program and scope.
The CDL program has been moved. This change in the program has allowed for the Fire Services Bldgs. to shift to the second building location identified during
pre-design, and the preferred location. This shift will allow the activities of the fire services program to reside at one location on campus. The initial location
would have required the split of activities between the building and the SW corner of the campus (which was to serve as the exercise yard in initial pre-design).
Wa Arts Commission June 2026 has completed the selection process to identify the Artist. The Artist selected is Hooman Mehdizadehjafari.
The beautiful design was completed and approved by the Bates Technical Center Art Committee and College President. Art in fabrication.

## Photo Gallery (3)
Photo Gallery

## Photo Gallery (2)
Photo Gallery

## Photo Gallery
Photo Gallery
North Site Alternative B
South Site Alternative A - Preferred Alternative

## Lists (hidden)
Construction Type | Y/N | PM Admin |  |  | Date | Type of Report
Apartment | Yes | DES | 2003-05 | Design-Bid-Build | Select Date from Dropdown | WASHINGTON STATE MAJOR PROJECT STATUS REPORT
Archive building | No | Agency | 2004 | GCCM | July 2026 | WASHINGTON STATE MAJOR PROJECT FINAL CLOSE-OUT REPORT
Armories |  | Other (explain below) | 2005-07 | Design-Build | August 2026
Art galleries |  |  | 2006 | Other (explain below) | September 2026
Auditorium with stage |  |  | 2007-09 |  | October 2026
Auditorium without stage |  |  | 2008 |  | November 2026
Civil Construction | Estimate at PD to Estimate as Funded Variance |  | 2009-11 |  | December 2026
College classroom facilities | Estimate at PD to Actuals Variance |  | 2010 |  | January 2027
Communications Building | Estimate as Currently Funded to Actuals Variance |  | 2011-13 |  | February 2027
Computer rooms |  |  | 2012 |  | March 2027
Convention facilities |  |  | 2013-15 |  | April 2027
Courthouses |  |  | 2014 |  | May 2027
Day care facilities |  |  | 2015-17 |  | June 2027
Detention/correctional facilities - maximum |  |  | 2016 |  | July 2027
Detention/correctional facilities - min & max |  |  | 2017-19 |  | August 2027
Dining halls/institute |  |  | 2018 |  | September 2027
Dormatories |  |  | 2019-21 |  | October 2027
Emergency generator facilities |  |  | 2020 |  | November 2027
Exposition building |  |  | 2021-23 |  | December 2027
Extended care facilities |  |  | 2022 |  | January 2028
Farm structures |  |  | 2023-25 |  | February 2028
Fire and police stations |  |  | 2024 |  | March 2028
Fish hatcheries |  |  |  |  | April 2028
Greenhouses |  |  |  |  | May 2028
Guard towers |  |  |  |  | June 2028
Gymnasiums
Heating and power plants
Hospitals
Industrial buildings without special facilities
Laboratories (Research)
Laundry and cleaning facilities
Libraries
Medical office and clinics
Mental Institutions
Museums
Neighborhood centers and similar recreation facilities
Nursing homes
Observatories
Office buildings
Parking structures and garages
Printing plants
Prototype facilities
Recreational building
Research Facilities
Residence
Schools (primary and secondary)
Science labs (teaching)
Service garages
Sewer treatment plants
Shop and maintenance facilities
Simple loft-type structures (w/o special equipment)
Special schools for physically disadvantaged
Stadium-grandstand type
Stadiums multi-purpose
Storage-cold
Theaters and similar facilities
Transportation terminals
Veterinary hospitals
Vocational schools
Warehouses
Water treatment plants
Other Sch. A Projects
Other Sch. B Projects
Other Sch. C Projects
Formulas:
Date = TEXT(DATE(YEAR(TODAY()), MONTH(TODAY())+ROWS(M2:[Date])-1, DAY(1)), "MMMM YYYY")