## Major Project Report
OFFICE OF FINANCIAL MANAGEMENT
2025-27 Biennium
WASHINGTON STATE MAJOR PROJECT STATUS REPORT
June 2026
| Agency | 699
| Project Name | Whatcom Technology and Engineering Center
| OFM Project Number(s) | 40000137
Contact Information
| Name | Brian Keeley
| Phone Number | 360.383.3375
| Email | Bkeeley@shatcom.edu
Project Information
| Project Description: (Include a brief summary of the project and the programs it supports.) | The Technology and Engineering Center (TEC) will be a new building of approximately 52,000-gsf located on the north end of campus between Kulshan Hall and the Phyllis & Charles Self Learning Commons. The new TEC will provide programmed space for computer science, computer information systems, IT networking, cybersecurity, engineering, and tech-equipped instructional spaces to support community learning and basic education offerings. These will include program specific labs, technology rich classrooms, and general-purpose classrooms. The building will also include staff and faculty offices along with student-focused spaces such as collaborative learning labs and study locations. This project includes design and construction of a new building and related infrastructure using the GC/CM delivery method. The building programming may include purposefully designed lab spaces to meet the physical security requirements of a Sensitive Compartmentalized Information Facility (SCIF) as defined by National Security Agency (NSA).
| Project Status: (Include scope or budget changes, phase updates, identified project delivery issues, discussion of critical path for construction and any potential for project cost overruns or claims.) | The Technology & Engineering Center (TEC) is completing schematic design and will enter design development in June 2026 to further refine building programming and design. Dawson Construction was selected as the General Contractor/Construction Manager (GCCM) and will provide constructability and cost review services throughout design and construction.
Funding
All State & Local Sources, Project Transfers and Amounts
|  | Expenditures |  | Current Plan
| Phase & Fund Type | Prior Expended | 2025-27 Expended | 2025-27 Remaining | 2027-29 Plan | Future Plan | TOTAL | Notes
| Predesign | 0 | 0 | 0 | 0 | 0 | 0
| 057 - State Bldgs. Const Acct | [5 empty] | 0
| XXX - Other State Funding | [5 empty] | 0
| Local Funds | [5 empty] | 0
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| Design | 0 | 943455.28 | 9839405 | 40259140 | 0 | 51042000.28
| 057 - State Bldgs. Const Acct |  | 943455.28 | 9839405 | 40259140 |  | 51042000.28 | E03
| XXX - Other State Funding | [5 empty] | 0
| Local Funds | [5 empty] | 0
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| Construction | 0 | 0 | 0 | 0 | 0 | 0
| 057 - State Bldgs. Const Acct | [5 empty] | 0
| XXX - Other State Funding | [5 empty] | 0
| Local Funds | [5 empty] | 0
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| TOTALS | 0 | 943455.28 | 9839405 | 40259140 | 0 | 51042000.28
Details
| Construction Type | College classroom facilities |  | Project Administered By |  | DES
| % of Bldgs. Area that is being remodeled | 0% |  | Art Requirement Applies |  | Yes
| Procurement Method | GCCM |  | Higher Ed Institution |  | Yes
Statistics
| Complete the table below with information from the cost estimate submitted with the predesign study, the cost estimate of the project as funded and the actual cost data to date or at completion. Explain any variances in the Notes column or below. |  |  | Estimate at Approved Predesign | Estimate of the Project as Currently Funded | Actuals to Date | Estimate as Currently Funded to Actuals Variance | Notes
| Gross Sq Ft (GSF) |  |  | 46494 | 46494 |  | -46494 | See Addl. comments
| Usable Sq Ft (USF) |  |  | 25702 | 25702 |  | -25702 | Refinement will continue in DD to capture more USF.
| Space Efficiency (USF/GSF %): |  |  | 55.28% | 55.28%
| Site Work SF: | [5 empty] | 0
| Demolition SF (provide building names in comments): | [5 empty] | 0
| MACC/Bid Award COST/GSF |  |  | 673.15 | 673.15
| Construction Subtotal COST/GSF (Includes change orders) |  |  | 873.3103 | 873.3103
Milestone Dates
| Predesign Complete |  |  | 2026-03-04 | 2026-03-04 | 2026-03-04 | 0 mo. | Predesign report completed and approved by OFM.
| Start Design |  |  | 2026-03-05 | 2026-03-05 | 2026-03-05 | 0 mo.
| Bid Due Date |  |  | 2027-03-04 | 2027-03-04
| Notice to Proceed |  |  | 2027-03-22 | 2027-03-22
| Substantial Completion |  |  | 2028-07-10 | 2028-07-10
| Final Acceptance/Project Close-out Date |  |  | 2028-09-15 | 2028-09-15 |  |  | 2 months for close-out
Project Costs
| Complete the table below with information from the cost estimate submitted with the predesign study, the cost estimate of the project as funded and the actual cost data to date or at completion. Explain any variances in the Notes column or below. |  |  | Cost Estimate at Approved Predesign | Cost Estimate of the Project as Currently Funded | Actual Costs to Date | Estimate as Currently Funded to Actuals Variance | Notes
Acquisition
|  |  | Acquisition Costs Total |  |  |  | 0
Consultant Services
| Pre-Schematic Design Services |  |  | 290708 | 290708 | 290708 | 0
| AE Basic Service Fee - Construction Documents |  |  | 2908493 | 2908493 | 565236.02 | -2343256.98
| Extra Services - Pre-Bid |  |  | 1584698 | 1584698 | 44476.2 | -1540221.8
| AE Basic Service Fee - Bid/Construction/Closeout |  |  | 600816 | 600816 |  | -600816
| Other Services - Post Bid | [5 empty] | 0
| Design Services Contingency |  |  | 279032 | 279032 |  | -279032
|  |  | Consultant Services Total | 5663747 | 5663747 | 900420.22 | -4763326.78
Construction
| Site Work |  |  | 2533281 | 2533281 |  | -2533281
| Related Project Costs |  |  | 0 | 0 |  | 0
| Facility Construction |  |  | 28764156 | 28764156 |  | -28764156
|  |  | Maximum Allowable Construction Cost (MACC) Subtotal | 31297437 | 31297437 | 0 | -31297437
| Construction Contingencies |  |  | 1774447 | 1774447 |  | -1774447
| Non-Taxable Items |  |  | 0 | 0 |  | 0
| Sales Tax |  |  | 3386742 | 3386742 |  | -3386742
| GCCM Costs |  |  | 3099601 | 3099601 | 80589.48 | -3019011.52
| GCCM Risk Contingency |  |  | 1045464 | 1045464 |  | -1045464
|  |  | Construction Contracts Total | 40603691 | 40603691 | 80589.48 | -40523101.52
Other Project Costs
| Equipment |  |  | 3551724 | 3551724 |  | -3551724
| Art Work |  |  | 253938 | 253938 | 0 | -253938
| Project Management |  |  | 427019 | 427019 |  | -427019
| Other Costs (describe) |  |  | 541881 | 541881 | 539.85 | -541341.15 | Permitting fees, TIF, public trail development costs + $500 rounded escalation
|  |  | Other Project Costs Total | 4774562 | 4774562 | 539.85 | -4774022.15
| Total Project Costs |  |  | 51042000 | 51042000 | 981549.55 | -50060450.45
Additional comments:
A reduction in building GSF from 52,000 GSF to 46,000 GSF was required to align the design with the budget following the SD cost reconciliation between
the design cost estimator and the GCCM.
Changes included a reduced floor to floor height (16' to 14'-8"), loss of one shared active learning classroom, loss of 1 CIS general purpose teaching lab, removal
of the SCIF (other issues also factored into this decision), and loss of 3 faculty offices.
Wa Arts - June 2026 - Artist selection in process.

## Photo Gallery
Photo Gallery
Updated floor plan (level 1)
Updated floo plan (level 2)
Updated floor plan (level 3)
Rendored view of TEC south elevation from the quad.

## Lists (hidden)
Construction Type | Y/N | PM Admin |  |  | Date | Type of Report
Apartment | Yes | DES | 2003-05 | Design-Bid-Build | Select Date from Dropdown | WASHINGTON STATE MAJOR PROJECT STATUS REPORT
Archive building | No | Agency | 2004 | GCCM | July 2026 | WASHINGTON STATE MAJOR PROJECT FINAL CLOSE-OUT REPORT
Armories |  | Other (explain below) | 2005-07 | Design-Build | August 2026
Art galleries |  |  | 2006 | Other (explain below) | September 2026
Auditorium with stage |  |  | 2007-09 |  | October 2026
Auditorium without stage |  |  | 2008 |  | November 2026
Civil Construction | Estimate at PD to Estimate as Funded Variance |  | 2009-11 |  | December 2026
College classroom facilities | Estimate at PD to Actuals Variance |  | 2010 |  | January 2027
Communications Building | Estimate as Currently Funded to Actuals Variance |  | 2011-13 |  | February 2027
Computer rooms |  |  | 2012 |  | March 2027
Convention facilities |  |  | 2013-15 |  | April 2027
Courthouses |  |  | 2014 |  | May 2027
Day care facilities |  |  | 2015-17 |  | June 2027
Detention/correctional facilities - maximum |  |  | 2016 |  | July 2027
Detention/correctional facilities - min & max |  |  | 2017-19 |  | August 2027
Dining halls/institute |  |  | 2018 |  | September 2027
Dormatories |  |  | 2019-21 |  | October 2027
Emergency generator facilities |  |  | 2020 |  | November 2027
Exposition building |  |  | 2021-23 |  | December 2027
Extended care facilities |  |  | 2022 |  | January 2028
Farm structures |  |  | 2023-25 |  | February 2028
Fire and police stations |  |  | 2024 |  | March 2028
Fish hatcheries |  |  |  |  | April 2028
Greenhouses |  |  |  |  | May 2028
Guard towers |  |  |  |  | June 2028
Gymnasiums
Heating and power plants
Hospitals
Industrial buildings without special facilities
Laboratories (Research)
Laundry and cleaning facilities
Libraries
Medical office and clinics
Mental Institutions
Museums
Neighborhood centers and similar recreation facilities
Nursing homes
Observatories
Office buildings
Parking structures and garages
Printing plants
Prototype facilities
Recreational building
Research Facilities
Residence
Schools (primary and secondary)
Science labs (teaching)
Service garages
Sewer treatment plants
Shop and maintenance facilities
Simple loft-type structures (w/o special equipment)
Special schools for physically disadvantaged
Stadium-grandstand type
Stadiums multi-purpose
Storage-cold
Theaters and similar facilities
Transportation terminals
Veterinary hospitals
Vocational schools
Warehouses
Water treatment plants
Other Sch. A Projects
Other Sch. B Projects
Other Sch. C Projects
Formulas:
Date = TEXT(DATE(YEAR(TODAY()), MONTH(TODAY())+ROWS(M2:[Date])-1, DAY(1)), "MMMM YYYY")