## QuickStartGuide
Major Project Report
Quick Start Guide
BACKGROUND INFORMATION
The Final Project Close-out Report requirement was implemented in the 2013-15 biennium as part of the recommendations in the 2009 JLARC report, “Evaluation of the Accuracy of Capital Project Cost Estimates.” This requirement is for agencies to submit the report to OFM at project completion to compare the scope and estimate from the predesign stage with the final scope and actual cost after construction as well as the estimate as the project was funded.
RCW 43.88.160 requires OFM to submit an annual report to the Legislature on the status of all appropriated capital projects (including transportation projects) that show significant cost overruns or underruns. As these projects are completed, agencies must provide OFM with a final summary showing estimated start and completion dates of each project phase compared to actual dates, as well as estimated costs of each phase compared to actual costs. OFM uses the information collected in the Final Project Close-out Report to make its annual report to the Legislature.
Agencies administering a major capital project or projects specifically identified for this reporting requirement by OFM or the Legislature must submit a detailed Major Project Status Report to OFM and the legislative fiscal committees each December 31 and July 1.
GENERAL INFORMATION
This comprehensive reporting tool merges the Major Project Status Report and the Final Project Close-Out Report. This is to generate consistency in reported data as required by OFM, the Legislature, and state statute; especially as it pertains to comparing cost estimates at predesign approval, cost estimates as projects are currently funded, and the actual costs at project completion.
Please contact your assigned OFM Capital Budget Analyst if you have any questions regarding this tool.
INSTRUCTIONS
1) | Blue cells are available for data entry.
2) | Select the type of report you will be submitting in cell B2. Select "Major Project Status Report" if your report is to fulfill the semi-annual requirement to update OFM and the Legislature on the status of your project. Select "Final Project Close-Out Report" if your project is complete.
3) | In the funding section, please include all funding sources for the project by phase. Identify the fund number and name (for example: "06X - Building and Tuition Acct"). Identify all local and alternative funding sources and all OFM authorized transfers from other projects. Insert rows where necessary.
4) | Cost and other variances can be compared three ways: 1) Estimates at Approved Predesign to Estimates as Currently Funded. 2) Estimates at Approved Predesign to Actuals. 3) Estimates as Currently Funded to Actuals). Click on cell H55 to select your variance comparison.
5) | Additional information, such as number and value of change orders, is required for the Final Project Close-Out Report. Those cells will be made available when that report type is selected in cell B2.
6) | If available, photos can be added to the Photo Gallery tab for a visual representation of the status of the project. Pictures can sometimes provide a better understanding of the status of a construction project than one can get from just the schedule or expenses to date. Right-click on the stock photos and select "Change Picture" to insert your photo from a file. Captions of the photo can be made in the text box below the photo.

## Major Project Report
OFFICE OF FINANCIAL MANAGEMENT
2023-25 Biennium
WASHINGTON STATE MAJOR PROJECT STATUS REPORT
June 2025
| Agency | 699
| Project Name | Everett Community College Baker Hall Replacement
| OFM Project Number(s) | 40000190
Contact Information
| Name | Allen Flaa
| Phone Number | 425-388-9565
| Email | aflaa@everettcc.edu
Project Information
| Project Description: | This project replaces a facility built in 1962. The Baker Hall Replacement project will support the following programs: General Business, Accounting, Economics, Business Technology, Information Technology and Theatre. It will contain sixteen primary instructional classrooms, two Basic Skills labs, and instructional support spaces ranging from classroom break-out spaces to collaboration rooms to informal lounges. An auditorium convertible for use as a black-box theater will serve multiple roles, from instructional lab to instructional support to a campus event space.
(Include a brief summary of the project and the programs it supports.)
| Project Status: | This project received Design and Construction funding in the 2023-25 biennium. The method of the project was changed to GCCM in December of 2024. McGranahan PBK was selected as the architect in February of 2025 and Cornerstone Construction was selected as the contractor in May of 2025. The design phase is expected to last around 12-13 months with a construction start date of around April or May of 2026 and the demolition of the old Baker Hall to start in March of 2026. The State Project Manager and EvCC project team meet weekly; team has identified programming for the new building which will be the cosmetology program (currently residing in Marysville, WA) and blackbox theater on the 1st floor and basic, flexible classrooms on the 2nd floor.
(Include scope or budget changes, phase updates, identified project delivery issues, discussion of critical path for construction and any potential for project cost overruns or claims.)
Funding
All State & Local Sources, Project Transfers and Amounts
|  | Expenditures |  | Current Plan |  |  | TOTAL | Notes
| Phase & Fund Type | Prior Expended | 2023-25 Expended | 2023-25 Remaining | 2025-27 Plan | Future Plan
| Predesign | 139209 | 0 | 135000 | 0 | 0 | 274209
| 057 - State Bldg. Const Acct | 139209 | 0 | 135000 |  |  | 274209 | A21
| XXX - Other State Funding | [5 empty] | 0
| Local Funds | [5 empty] | 0
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| Design | 0 | 0 | 0 | 0 | 0 | 0
| 057 - State Bldg. Const Acct | [5 empty] | 0
| XXX - Other State Funding | [5 empty] | 0
| Local Funds | [5 empty] | 0
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| Construction | 0 | 145 | 37903855 | 0 | 0 | 37904000
| 057 - State Bldg. Const Acct | 0 | 145 | 37903855 |  |  | 37904000 | D03
| XXX - Other State Funding | [5 empty] | 0
| Local Funds | [5 empty] | 0
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| TOTALS | 139209 | 145 | 38038855 | 0 | 0 | 38178209
Details
| Construction Type | College classroom facilities |  | Project Administered By |  | DES
| % of Bldg. Area that is being remodeled | 0% |  | Art Requirement Applies |  | Yes
| Procurement Method | GCCM |  | Higher Ed Institution |  | Yes
Statistics
| Complete the table below with information from the cost estimate submitted with the predesign study, the cost estimate of the project as funded and the actual cost data to date or at completion. Explain any variances in the Notes column or below. |  |  | Estimate at Approved Predesign | Estimate of the Project as Currently Funded | Actuals to Date | Estimate as Currently Funded to Actuals Variance | Notes
| Gross Sq Ft (GSF) |  |  | 49000 | 50000 |  | -50000
| Usable Sq Ft (USF) |  |  | 29525 | 32180 |  | -32180
| Space Efficiency (USF/GSF %): |  |  | 60.26% | 64.36%
| Site Work SF: | [5 empty] | 0
| Demolition SF (provide building names in comments): |  |  | 23710 | 23710 |  | -23710 | UFI A10077
| MACC/Bid Award COST/GSF |  |  | 455.856 | 532.5067
| Construction Subtotal COST/GSF (Includes change orders) |  |  | 525.6194 | 614.6007
Milestone Dates
| Predesign Complete |  |  | 2020-12-01 | 2020-12-01 | 2021-04-06 | 4 mo. | OFM approved
| Start Design |  |  | 2021-07-01 | 2023-07-01 | 2025-04-01 | 21 mo.
Bid Due Date
| Notice to Proceed |  |  | 2021-07-01 | 2026-07-01
| Substantial Completion |  |  | 2023-01-01 | 2027-07-01
| Final Acceptance/Project Close-out Date |  |  |  | 2027-10-31
Project Costs
| Complete the table below with information from the cost estimate submitted with the predesign study, the cost estimate of the project as funded and the actual cost data to date or at completion. Explain any variances in the Notes column or below. |  |  | Cost Estimate at Approved Predesign | Cost Estimate of the Project as Currently Funded | Actual Costs to Date | Estimate as Currently Funded to Actuals Variance | Notes
Acquisition
| Acquisition Costs Total | [5 empty] | 0
Consultant Services
| Pre-Schematic Design Services |  |  | 249710 | 271067 | 123969 | -147098
| AE Basic Service Fee - Construction Documents |  |  | 1179794 | 1392569 |  | -1392569
| Extra Services - Pre-Bid |  |  | 1299689 | 1379881 | 15240.11 | -1364640.89
| AE Basic Service Fee - Bid/Construction/Closeout |  |  | 518975.1255 | 625647.1584 |  | -625647.1584
| Other Services - Post Bid |  |  | 293481.8745 | 311627 |  | -311627
| Design Services Contingency |  |  | 179419 | 199510 |  | -199510
| Consultant Services Total |  |  | 3721069 | 4180301.1584 | 139209.11 | -4041092.0484
Construction
| Site Work |  |  | 3151376 | 3006960 |  | -3006960
| Related Project Costs |  |  |  | 0 |  | 0
| Facility Construction |  |  | 19185570 | 23618376 |  | -23618376
| Maximum Allowable Construction Cost (MACC) Subtotal |  |  | 22336946 | 26625336 | 0 | -26625336
| Construction Contingencies |  |  | 1119659 | 1336479 |  | -1336479
| Non-Taxable Items |  |  |  | 0 |  | 0
| Sales Tax |  |  | 2298748 | 2768220 |  | -2768220
| GCCM Costs | [5 empty] | 0
| GCCM Risk Contingency | [5 empty] | 0
| Construction Contracts Total |  |  | 25755353 | 30730035 | 0 | -30730035
Other Project Costs
| Equipment |  |  | 2134639 | 2226070 |  | -2226070
| Art Work |  |  | 161959 | 189941 | 0 | -189941
| Project Management |  |  | 225924 | 249299 |  | -249299
| Other Costs (describe) |  |  | 554909 | 602366 |  | -602366
| Other Project Costs Total |  |  | 3077431 | 3267676 | 0 | -3267676
| Total Project Costs |  |  | 32553853 | 38178012.1584 | 139209.11 | -38038803.0484
Additional comments:
Demolish Baker Hall UFI A10077 Wa Arts Commission has reached out to initiate the formation of the Art Selection Committee; EvCC will meet with the committee in the next two weeks to affirm their participation, apprise them of the status of the Baker Hall project and then they will be connected with Claire Schectman of the WA Arts Commission.

## Photo Gallery (hidden)
Photo Gallery
Right-click on picture above to change picture to photos of the project.
Triple-click on this text to change the caption.
Picture caption here.
Picture caption here.
Picture caption here.
Picture caption here.
Picture caption here.
image credit: www.bownegroup.com

## Lists (hidden)
Construction Type | Y/N | PM Admin |  |  | Date | Type of Report
Apartment | Yes | DES | 2003-05 | Design-Bid-Build | Select Date from Dropdown | WASHINGTON STATE MAJOR PROJECT STATUS REPORT
Archive building | No | Agency | 2004 | GCCM | July 2025 | WASHINGTON STATE MAJOR PROJECT FINAL CLOSE-OUT REPORT
Armories |  | Other (explain below) | 2005-07 | Design-Build | August 2025
Art galleries |  |  | 2006 | Other (explain below) | September 2025
Auditorium with stage |  |  | 2007-09 |  | October 2025
Auditorium without stage |  |  | 2008 |  | November 2025
Civil Construction | Estimate at PD to Estimate as Funded Variance |  | 2009-11 |  | December 2025
College classroom facilities | Estimate at PD to Actuals Variance |  | 2010 |  | January 2026
Communications Building | Estimate as Currently Funded to Actuals Variance |  | 2011-13 |  | February 2026
Computer rooms |  |  | 2012 |  | March 2026
Convention facilities |  |  | 2013-15 |  | April 2026
Courthouses |  |  | 2014 |  | May 2026
Day care facilities |  |  | 2015-17 |  | June 2026
Detention/correctional facilities - maximum |  |  | 2016 |  | July 2026
Detention/correctional facilities - min & max |  |  | 2017-19 |  | August 2026
Dining halls/institute |  |  | 2018 |  | September 2026
Dormatories |  |  | 2019-21 |  | October 2026
Emergency generator facilities |  |  | 2020 |  | November 2026
Exposition building |  |  | 2021-23 |  | December 2026
Extended care facilities |  |  | 2022 |  | January 2027
Farm structures |  |  | 2023-25 |  | February 2027
Fire and police stations |  |  | 2024 |  | March 2027
Fish hatcheries |  |  |  |  | April 2027
Greenhouses |  |  |  |  | May 2027
Guard towers |  |  |  |  | June 2027
Gymnasiums
Heating and power plants
Hospitals
Industrial buildings without special facilities
Laboratories (Research)
Laundry and cleaning facilities
Libraries
Medical office and clinics
Mental Institutions
Museums
Neighborhood centers and similar recreation facilities
Nursing homes
Observatories
Office buildings
Parking structures and garages
Printing plants
Prototype facilities
Recreational building
Research Facilities
Residence
Schools (primary and secondary)
Science labs (teaching)
Service garages
Sewer treatment plants
Shop and maintenance facilities
Simple loft-type structures (w/o special equipment)
Special schools for physically disadvantaged
Stadium-grandstand type
Stadiums multi-purpose
Storage-cold
Theaters and similar facilities
Transportation terminals
Veterinary hospitals
Vocational schools
Warehouses
Water treatment plants
Other Sch. A Projects
Other Sch. B Projects
Other Sch. C Projects
Formulas:
Date = TEXT(DATE(YEAR(TODAY()), MONTH(TODAY())+ROWS(M2:[Date])-1, DAY(1)), "MMMM YYYY")