## Major Project Report
OFFICE OF FINANCIAL MANAGEMENT
2025-27 Biennium
WASHINGTON STATE MAJOR PROJECT STATUS REPORT
June 2026
| Agency | 699
| Project Name | Everett Community College Baker Hall Replacement
| OFM Project Number(s) | 40000190
Contact Information
| Name | Chris Carson
| Phone Number | 425-388-9516
| Email | ccarson@everettcc.edu
Project Information
| Project Description: (Include a brief summary of the project and the programs it supports.) | This project replaces a facility built in 1962. The Baker Hall Replacement project will house Cosmetology and Fine Arts, including Theater, with instructional flex space for Business, Accounting, Economics, Business Technology, Information Technology, and additional programs. It will contain three primary instructional classrooms, two Basic Skills labs, and instructional support spaces ranging from classroom break-out spaces to collaboration rooms to informal lounges. An auditorium convertible for use as a black-box theater will serve multiple roles, from instructional lab to instructional support to a campus event space.
| Project Status: (Include scope or budget changes, phase updates, identified project delivery issues, discussion of critical path for construction and any potential for project cost overruns or claims.) | This project received Design and Construction funding in the 2023-25 biennium. The method of the project was changed to GCCM in December of 2024. McGranahan PBK was selected as the architect in February of 2025 and Cornerstone Construction was selected as the contractor in May of 2025. The design phase is expected to last around 12-13 months with a construction start date of around September or October of 2026 and the demolition of the old Baker Hall to start in July of 2026. The State Project Manager and EvCC project team meet weekly; team has identified programming for the new building which will be the cosmetology program (currently residing in Marysville, WA) and Blackbox theater, as well a basic, flexible classroom.
Funding
All State & Local Sources, Project Transfers and Amounts
|  | Expenditures |  | Current Plan
| Phase & Fund Type | Prior Expended | 2025-27 Expended | 2025-27 Remaining | 2027-29 Plan | Future Plan | TOTAL | Notes
| Predesign | 275000 | 0 | 0 | 0 | 0 | 275000
| 057 - State Bldgs. Const Acct | 275000 |  |  |  |  | 275000 | A21
| XXX - Other State Funding | [5 empty] | 0
| Local Funds | [5 empty] | 0
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| Design | 0 | 0 | 0 | 0 | 0 | 0
| 057 - State Bldgs. Const Acct | [5 empty] | 0
| XXX - Other State Funding | [5 empty] | 0
| Local Funds | [5 empty] | 0
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| Design & Construction | 303122.37 | 1934220.2 | 1240587.8 | 34426070 | 0 | 37904000.37
| 057 - State Bldgs. Const Acct | 303122.37 | 1934220.2 | 1240587.8 | 34426070 |  | 37904000.37 | D03
| XXX - Other State Funding | [5 empty] | 0
| Local Funds | [5 empty] | 0
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| TOTALS | 578122.37 | 1934220.2 | 1240587.8 | 34426070 | 0 | 38179000.37
Details
| Construction Type | College classroom facilities |  | Project Administered By |  | DES
| % of Bldgs. Area that is being remodeled | 0% |  | Art Requirement Applies |  | Yes
| Procurement Method | GCCM |  | Higher Ed Institution |  | Yes
Statistics
| Complete the table below with information from the cost estimate submitted with the predesign study, the cost estimate of the project as funded and the actual cost data to date or at completion. Explain any variances in the Notes column or below. |  |  | Estimate at Approved Predesign | Estimate of the Project as Currently Funded | Actuals to Date | Estimate as Currently Funded to Actuals Variance | Notes
| Gross Sq Ft (GSF) |  |  | 49000 | 50000 | 31203 | -18797
| Usable Sq Ft (USF) |  |  | 29525 | 32180 | 27613 | -4567
| Space Efficiency (USF/GSF %): |  |  | 60.26% | 64.36% | 88.49% | 24.13%
| Site Work SF: | [5 empty] | 0
| Demolition SF (provide building names in comments): |  |  | 23710 | 23710 | 23710 | 0 | UFI A10077
| MACC/Bid Award COST/GSF |  |  | 455.856 | 532.5067 | 0 | -532.5067
| Construction Subtotal COST/GSF (Includes change orders) |  |  | 525.6194 | 614.6007 | 0 | -614.6007
Milestone Dates
| Predesign Complete |  |  | 2020-12-01 | 2020-12-01 | 2021-04-06 | 4 mo. | OFM approved
| Start Design |  |  | 2021-07-01 | 2023-07-01 | 2025-04-01 | 21 mo.
| Bid Due Date |  |  |  | 2026-08-07 |  |  | Bid closing date
| Notice to Proceed |  |  | 2021-07-01 | 2026-07-01
| Substantial Completion |  |  | 2023-01-01 | 2027-11-30 |  |  | Substantial completion date pushed back from 7/1/27
| Final Acceptance/Project Close-out Date |  |  |  | 2027-12-20 |  |  | Close out pushed back from 10/31/27
Project Costs
| Complete the table below with information from the cost estimate submitted with the predesign study, the cost estimate of the project as funded and the actual cost data to date or at completion. Explain any variances in the Notes column or below. |  |  | Cost Estimate at Approved Predesign | Cost Estimate of the Project as Currently Funded | Actual Costs to Date | Estimate as Currently Funded to Actuals Variance | Notes
Acquisition
|  |  | Acquisition Costs Total |  |  |  | 0
Consultant Services
| Pre-Schematic Design Services |  |  | 249710 | 271067 | 336776.58 | 65709.58
| AE Basic Service Fee - Construction Documents |  |  | 1179794 | 1392569 | 551003.9 | -841565.1
| Extra Services - Pre-Bid |  |  | 1299689 | 1379881 | 1101447.55 | -278433.45
| AE Basic Service Fee - Bid/Construction/Closeout |  |  | 518975.1255 | 625647.1584 | 1870.96 | -623776.1984
| Other Services - Post Bid |  |  | 293481.8745 | 311627 |  | -311627
| Design Services Contingency |  |  | 179419 | 199510 |  | -199510
|  |  | Consultant Services Total | 3721069 | 4180301.1584 | 1991098.99 | -2189202.1684
Construction
| Site Work |  |  | 3151376 | 3006960 |  | -3006960
| Related Project Costs |  |  |  | 0 |  | 0
| Facility Construction |  |  | 19185570 | 23618376 |  | -23618376
|  |  | Maximum Allowable Construction Cost (MACC) Subtotal | 22336946 | 26625336 | 0 | -26625336
| Construction Contingencies |  |  | 1119659 | 1336479 |  | -1336479
| Non-Taxable Items |  |  |  | 0 |  | 0
| Sales Tax |  |  | 2298748 | 2768220 |  | -2768220
| GCCM Costs | [5 empty] | 0
| GCCM Risk Contingency | [5 empty] | 0
|  |  | Construction Contracts Total | 25755353 | 30730035 | 0 | -30730035
Other Project Costs
| Equipment |  |  | 2134639 | 2226070 |  | -2226070
| Art Work |  |  | 161959 | 189941 | 33157.82 | -156783.18
| Project Management |  |  | 225924 | 249299 |  | -249299
| Other Costs (describe) |  |  | 554909 | 602366 |  | -602366
|  |  | Other Project Costs Total | 3077431 | 3267676 | 33157.82 | -3234518.18
| Total Project Costs |  |  | 32553853 | 38178012.1584 | 2024256.81 | -36153755.3484
Additional comments:
Demolish Baker Hall UFI A10077
Wa Arts Commission - June 2026 - Artist selected, Shan Shan Sheng, and initial design to be presented Spring 2026.
Baker Hall Demo bid opening scheduled for 6/9/26 with a building hand-off to the awarded contractor the week of 7/7/26

## Lists (hidden)
Construction Type | Y/N | PM Admin |  |  | Date | Type of Report
Apartment | Yes | DES | 2003-05 | Design-Bid-Build | Select Date from Dropdown | WASHINGTON STATE MAJOR PROJECT STATUS REPORT
Archive building | No | Agency | 2004 | GCCM | July 2026 | WASHINGTON STATE MAJOR PROJECT FINAL CLOSE-OUT REPORT
Armories |  | Other (explain below) | 2005-07 | Design-Build | August 2026
Art galleries |  |  | 2006 | Other (explain below) | September 2026
Auditorium with stage |  |  | 2007-09 |  | October 2026
Auditorium without stage |  |  | 2008 |  | November 2026
Civil Construction | Estimate at PD to Estimate as Funded Variance |  | 2009-11 |  | December 2026
College classroom facilities | Estimate at PD to Actuals Variance |  | 2010 |  | January 2027
Communications Building | Estimate as Currently Funded to Actuals Variance |  | 2011-13 |  | February 2027
Computer rooms |  |  | 2012 |  | March 2027
Convention facilities |  |  | 2013-15 |  | April 2027
Courthouses |  |  | 2014 |  | May 2027
Day care facilities |  |  | 2015-17 |  | June 2027
Detention/correctional facilities - maximum |  |  | 2016 |  | July 2027
Detention/correctional facilities - min & max |  |  | 2017-19 |  | August 2027
Dining halls/institute |  |  | 2018 |  | September 2027
Dormatories |  |  | 2019-21 |  | October 2027
Emergency generator facilities |  |  | 2020 |  | November 2027
Exposition building |  |  | 2021-23 |  | December 2027
Extended care facilities |  |  | 2022 |  | January 2028
Farm structures |  |  | 2023-25 |  | February 2028
Fire and police stations |  |  | 2024 |  | March 2028
Fish hatcheries |  |  |  |  | April 2028
Greenhouses |  |  |  |  | May 2028
Guard towers |  |  |  |  | June 2028
Gymnasiums
Heating and power plants
Hospitals
Industrial buildings without special facilities
Laboratories (Research)
Laundry and cleaning facilities
Libraries
Medical office and clinics
Mental Institutions
Museums
Neighborhood centers and similar recreation facilities
Nursing homes
Observatories
Office buildings
Parking structures and garages
Printing plants
Prototype facilities
Recreational building
Research Facilities
Residence
Schools (primary and secondary)
Science labs (teaching)
Service garages
Sewer treatment plants
Shop and maintenance facilities
Simple loft-type structures (w/o special equipment)
Special schools for physically disadvantaged
Stadium-grandstand type
Stadiums multi-purpose
Storage-cold
Theaters and similar facilities
Transportation terminals
Veterinary hospitals
Vocational schools
Warehouses
Water treatment plants
Other Sch. A Projects
Other Sch. B Projects
Other Sch. C Projects
Formulas:
Date = TEXT(DATE(YEAR(TODAY()), MONTH(TODAY())+ROWS(M2:[Date])-1, DAY(1)), "MMMM YYYY")