## Major Project Report
OFFICE OF FINANCIAL MANAGEMENT
2025-27 Biennium
WASHINGTON STATE MAJOR PROJECT STATUS REPORT
June 2026
| Agency | 699
| Project Name | Wenatchee Valley College Center for Technical Education and Innovation
| OFM Project Number(s) | 40000198
Contact Information
| Name | Rich Peters
| Phone Number | 509-682-6465
| Email | rpeters@wvc.edu
Project Information
| Project Description: (Include a brief summary of the project and the programs it supports.) | This project is for the engineering and design of a new 70,000 sq ft building to replace portions of Batjer (Automotive, Ag, Natural Resources, Machine, Mechatronics), Industrial Technology/Welding and Refrigeration with a modern state-of-the-art technical education learning facility.
| Project Status: (Include scope or budget changes, phase updates, identified project delivery issues, discussion of critical path for construction and any potential for project cost overruns or claims.) | The project is approximately 70% complete and is on schedule. The installation of exterior doors and windows is underway. The labs, classrooms and offices are currently being painted. Cabinets will begin to be installed on June 29th. The elevator is scheduled to arrive and be installed the week of June 15th. Grading work on the west and south sides of the building is taking place in preparation of curbs being poured on June 18th and asphalt paving on July 8th in these two areas. The installation of lab equipment will begin this August. The intent is to have classes in the new building starting in January 2027. The existing refrigeration and industrial technology buildings will be demolished in January 2027 to make way for an access road and parking on the east side of the building. Occupancy is planned to occur July 2027.
Funding
All State & Local Sources, Project Transfers and Amounts
|  | Expenditures |  | Current Plan
| Phase & Fund Type | Prior Expended | 2025-27 Expended | 2025-27 Remaining | 2027-29 Plan | Future Plan | TOTAL | Notes
| Predesign | 0 | 0 | 0 | 0 | 0 | 0
| 057 - State Bldgs. Const Acct | [5 empty] | 0
| XXX - Other State Funding | [5 empty] | 0
| Local Funds | [5 empty] | 0
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| Design | 3243696.31 | 0 | 0 | 0 | 0 | 3243696.31
| 057 - State Bldgs. Const Acct | 3243696.31 |  |  |  |  | 3243696.31 | C07, remain w/D04 in BI2527
| XXX - Other State Funding | [5 empty] | 0
| Local Funds | [5 empty] | 0
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| Construction | 4437556.37 | 31848645.49 | 9502391.51 | 2420365 | 4000000 | 52208958.37
| 057 - State Bldgs. Const Acct | 4437556.37 | 31848645.49 | 9502391.51 | 2420365 |  | 48208958.37 | D04, incl. C07 reapprop in BI2527
| XXX - Other State Funding | [5 empty] | 0
| 147 - Local Funds |  |  |  |  | 700000 | 700000 | R772
| 147 - Local Funds |  |  |  |  | 3300000 | 3300000 | R870
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| TOTALS | 7681252.68 | 31848645.49 | 9502391.51 | 2420365 | 4000000 | 55452654.68
Details
| Construction Type | Vocational schools |  | Project Administered By |  | DES
| % of Bldgs. Area that is being remodeled | 0% |  | Art Requirement Applies |  | Yes
| Procurement Method | Design-Bid-Build |  | Higher Ed Institution |  | Yes
Statistics
| Complete the table below with information from the cost estimate submitted with the predesign study, the cost estimate of the project as funded and the actual cost data to date or at completion. Explain any variances in the Notes column or below. |  |  | Estimate at Approved Predesign | Estimate of the Project as Currently Funded | Actuals to Date | Estimate as Currently Funded to Actuals Variance | Notes
| Gross Sq Ft (GSF) |  |  | 69980 | 61085 |  | -61085
| Usable Sq Ft (USF) |  |  | 54190 | 44722 |  | -44722
| Space Efficiency (USF/GSF %): |  |  | 77.44% | 73.21%
| Site Work SF: | [5 empty] | 0
| Demolition SF (provide building names in comments): |  |  | 53596 | 53596 |  | -53596 | See Comments
| MACC/Bid Award COST/GSF |  |  | 499.2172 | 730.8854
| Construction Subtotal COST/GSF (Includes change orders) |  |  | 569.3137 | 825.596
Milestone Dates
| Predesign Complete |  |  | 2022-06-01 | 2022-06-01 | 2022-08-11 | 2.5 mo.
| Start Design |  |  | 2022-07-01 | 2022-07-01 | 2025-08-18 | 37.5 mo.
| Bid Due Date |  |  | 2024-04-30 | 2024-04-30 | 2024-10-29 | 6 mo.
| Notice to Proceed |  |  |  | 2025-03-03 | 2025-03-03 | 0 mo.
| Substantial Completion |  |  |  | 2027-06-24
| Final Acceptance/Project Close-out Date |  |  |  | 2027-07-27
Project Costs
| Complete the table below with information from the cost estimate submitted with the predesign study, the cost estimate of the project as funded and the actual cost data to date or at completion. Explain any variances in the Notes column or below. |  |  | Cost Estimate at Approved Predesign | Cost Estimate of the Project as Currently Funded | Actual Costs to Date | Estimate as Currently Funded to Actuals Variance | Notes
Acquisition
|  |  | Acquisition Costs Total |  |  |  | 0
Consultant Services
| Pre-Schematic Design Services |  |  | 428647 | 306710 | 306709.68 | -0.32 | RGU Architect.
| AE Basic Service Fee - Construction Documents |  |  | 1847717 | 2126551 | 1793432.43 | -333118.57 | RGU Architect.
| Extra Services - Pre-Bid |  |  | 1160115 | 1416470 | 1529647.46 | 113177.46 | Multiple
| AE Basic Service Fee - Bid/Construction/Closeout |  |  | 758906.9312 | 912450 | 477215.67 | -435234.33
| Other Services - Post Bid |  |  | 331231 |  | 177026.34 | 177026.34
| Design Services Contingency |  |  | 232917 |  |  | 0
|  |  | Consultant Services Total | 4759533.9312 | 4762181 | 4284031.58 | -478149.42
Construction
| Site Work |  |  | 3234398 |  | 1608294.6 | 1608294.6
| Related Project Costs |  |  | 436874 |  |  | 0
| Facility Construction |  |  | 31263951 | 44646135 | 30638945 | -14007190
|  |  | Maximum Allowable Construction Cost (MACC) Subtotal | 34935223 | 44646135 | 32247239.6 | -12398895.4
| Construction Contingencies |  |  | 1750384 | 1706376 |  | -1706376
| Non-Taxable Items | [5 empty] | 0
| Sales Tax |  |  | 3154963 | 4079021 | 2811912 | -1267109
0
0
|  |  | Construction Contracts Total | 39840570 | 50431532 | 35059151.6 | -15372380.4
Other Project Costs
| Equipment |  |  | 0 | 0 |  | 0
| Art Work |  |  | 223001 | 247446 | 37116.9 | -210329.1
| Project Management |  |  |  | 0 |  | 0
| Other Costs (describe) |  |  |  | 11800 | 149598.09 | 137798.09 | Permits, RFP adv
|  |  | Other Project Costs Total | 223001 | 259246 | 186714.99 | -72531.01
| Total Project Costs |  |  | 44823104.9312 | 55452959 | 39529898.17 | -15923060.83
Additional comments:
Wa Arts Commission - June 2026: The Artist has been selected
Note on I82: Maxwell, Debra: Hazardous Materials Survey, Geotechnical Engineering, Commissioning / Building Envelope Testing; RGU additional services

## Photo Gallery (2)
Photo Gallery
CTEI project - rendering 6-23
June 2025
June 2025
December 2025
June 2026

## Lists (hidden)
Construction Type | Y/N | PM Admin |  |  | Date | Type of Report
Apartment | Yes | DES | 2003-05 | Design-Bid-Build | Select Date from Dropdown | WASHINGTON STATE MAJOR PROJECT STATUS REPORT
Archive building | No | Agency | 2004 | GCCM | August 2026 | WASHINGTON STATE MAJOR PROJECT FINAL CLOSE-OUT REPORT
Armories |  | Other (explain below) | 2005-07 | Design-Build | September 2026
Art galleries |  |  | 2006 | Other (explain below) | October 2026
Auditorium with stage |  |  | 2007-09 |  | November 2026
Auditorium without stage |  |  | 2008 |  | December 2026
Civil Construction | Estimate at PD to Estimate as Funded Variance |  | 2009-11 |  | January 2027
College classroom facilities | Estimate at PD to Actuals Variance |  | 2010 |  | February 2027
Communications Building | Estimate as Currently Funded to Actuals Variance |  | 2011-13 |  | March 2027
Computer rooms |  |  | 2012 |  | April 2027
Convention facilities |  |  | 2013-15 |  | May 2027
Courthouses |  |  | 2014 |  | June 2027
Day care facilities |  |  | 2015-17 |  | July 2027
Detention/correctional facilities - maximum |  |  | 2016 |  | August 2027
Detention/correctional facilities - min & max |  |  | 2017-19 |  | September 2027
Dining halls/institute |  |  | 2018 |  | October 2027
Dormatories |  |  | 2019-21 |  | November 2027
Emergency generator facilities |  |  | 2020 |  | December 2027
Exposition building |  |  | 2021-23 |  | January 2028
Extended care facilities |  |  | 2022 |  | February 2028
Farm structures |  |  | 2023-25 |  | March 2028
Fire and police stations |  |  | 2024 |  | April 2028
Fish hatcheries |  |  |  |  | May 2028
Greenhouses |  |  |  |  | June 2028
Guard towers |  |  |  |  | July 2028
Gymnasiums
Heating and power plants
Hospitals
Industrial buildings without special facilities
Laboratories (Research)
Laundry and cleaning facilities
Libraries
Medical office and clinics
Mental Institutions
Museums
Neighborhood centers and similar recreation facilities
Nursing homes
Observatories
Office buildings
Parking structures and garages
Printing plants
Prototype facilities
Recreational building
Research Facilities
Residence
Schools (primary and secondary)
Science labs (teaching)
Service garages
Sewer treatment plants
Shop and maintenance facilities
Simple loft-type structures (w/o special equipment)
Special schools for physically disadvantaged
Stadium-grandstand type
Stadiums multi-purpose
Storage-cold
Theaters and similar facilities
Transportation terminals
Veterinary hospitals
Vocational schools
Warehouses
Water treatment plants
Other Sch. A Projects
Other Sch. B Projects
Other Sch. C Projects
Formulas:
Date = TEXT(DATE(YEAR(TODAY()), MONTH(TODAY())+ROWS(M2:[Date])-1, DAY(1)), "MMMM YYYY")