## Major Project Report
OFFICE OF FINANCIAL MANAGEMENT
2025-27 Biennium
WASHINGTON STATE MAJOR PROJECT STATUS REPORT
June 2026
| Agency | 699
| Project Name | Cascadia Community College CC5 Gateway building
| OFM Project Number(s) | 40000222
Contact Information
| Name | Shawna Pitts
| Phone Number | 425-352-8513
| Email | Spitts@Cascadia.edu
Project Information
| Project Description: (Include a brief summary of the project and the programs it supports.) | The Gateway building will consolidate all student services in one place to support equity, student retention, and student success. It will support Guided Pathways by physically replicating the steps of the student lifecycle process via layout and signage; allow for learning outside formal instructional environment through the inclusion of break-out rooms, collaborative workspaces, and a Learning Commons. It's location on campus will serve as a symbolic entry to Cascadia College.
| Project Status: (Include scope or budget changes, phase updates, identified project delivery issues, discussion of critical path for construction and any potential for project cost overruns or claims.) | The CC5 project was put on hold without receiving funding for the 2025-2027 biennium. The City of Bothell approved our building permit however the project did not have funding to purchase the permit. Cascadia College submitted and requested $5m from the supplemental budget and has received the allocation. This allows Cascadia to continue the project, purchase the building permits and begin utility and minor site work prior to full funding in July 2027. Currently the team is reviewing the upcoming construction schedule for site and utility work.
Funding
All State & Local Sources, Project Transfers and Amounts
|  | Expenditures |  | Current Plan
| Phase & Fund Type | Prior Expended | 2025-27 Expended | 2025-27 Remaining | 2027-29 Plan | Future Plan | TOTAL | Notes
| Predesign | 0 | 0 | 0 | 0 | 0 | 0
| 057 - State Bldgs. Const Acct | [5 empty] | 0
| XXX - Other State Funding | [5 empty] | 0
| Local Funds | [5 empty] | 0
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| Design | 2667327.68 | 305315.81 | 123356.51 | 0 | 0 | 3096000
| 057 - State Bldgs. Const Acct | 2667327.68 | 305315.81 | 123356.51 |  |  | 3096000 | C17
| 057 - State Bldgs. Const. Acct. | [5 empty] | 5000000 | E10
| Local Funds | [5 empty] | 0
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| Construction | 0 | 0 | 0 | 0 | 0 | 0
| 057 - State Bldgs. Const Acct | [5 empty] | 0 | Future
| XXX - Other State Funding | [5 empty] | 0
| Local Funds | [5 empty] | 0
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| TOTALS | 2667327.68 | 305315.81 | 123356.51 | 0 | 0 | 3096000
Details
| Construction Type | College classroom facilities |  | Project Administered By |  | DES
| % of Bldgs. Area that is being remodeled | 0% |  | Art Requirement Applies |  | Yes
| Procurement Method | GCCM |  | Higher Ed Institution |  | Yes
Statistics
| Complete the table below with information from the cost estimate submitted with the predesign study, the cost estimate of the project as funded and the actual cost data to date or at completion. Explain any variances in the Notes column or below. |  |  | Estimate at Approved Predesign | Estimate of the Project as Currently Funded | Actuals to Date | Estimate as Currently Funded to Actuals Variance | Notes
| Gross Sq Ft (GSF) |  |  | 37200 | 37200 | 37203 | 3
| Usable Sq Ft (USF) |  |  | 24230 | 24230 | 22968 | -1262
| Space Efficiency (USF/GSF %): |  |  | 65.13% | 65.13% | 61.74% | -3.397%
| Site Work SF: | [5 empty] | 0
| Demolition SF (provide building names in comments): | [5 empty] | 0
| MACC/Bid Award COST/GSF |  |  | 653.9093 | 653.9093 | 0 | -653.9093
| Construction Subtotal COST/GSF (Includes change orders) |  |  | 829.1588 | 829.1588 | 6.3167 | -822.8421
Milestone Dates
| Predesign Complete |  |  | 2022-07-01 | 2022-07-01 | 2022-08-11 | 1.5 mo. | Project not
| Start Design |  |  | 2022-09-01 | 2022-09-01 | 2025-04-30 | 32 mo. | currently
| Bid Due Date | [6 empty] | approved for
| Notice to Proceed |  |  | 2027-08-01 |  |  | 0 mo. | funding until
| Substantial Completion |  |  | 2029-03-01 |  |  | 0 mo. | 2027-07-01
| Final Acceptance/Project Close-out Date |  |  | 2029-05-01 |  |  | 0 mo.
Project Costs
| Complete the table below with information from the cost estimate submitted with the predesign study, the cost estimate of the project as funded and the actual cost data to date or at completion. Explain any variances in the Notes column or below. |  |  | Cost Estimate at Approved Predesign | Cost Estimate of the Project as Currently Funded | Actual Costs to Date | Estimate as Currently Funded to Actuals Variance | Notes
Acquisition
|  |  | Acquisition Costs Total |  |  |  | 0
Consultant Services
| Pre-Schematic Design Services |  |  | 250975 | 250975 | 247771.03 | -3203.97
| AE Basic Service Fee - Construction Documents |  |  | 1257932 | 1257932 | 1440898 | 182966
| Extra Services - Pre-Bid |  |  | 1055392 | 1055392 | 820608 | -234784
| AE Basic Service Fee - Bid/Construction/Closeout |  |  | 557160.228 | 557160.228 |  | -557160.228
| Other Services - Post Bid |  |  | 416529 | 416529 |  | -416529 | includes Basic Services
| Design Services Contingency |  |  | 181260 | 181260 | 181260 | 0
|  |  | Consultant Services Total | 3719248.228 | 3719248.228 | 2690537.03 | -1028711.198
Construction
| Site Work |  |  | 1302527 | 1302527 |  | -1302527
| Related Project Costs | [5 empty] | 0
| Facility Construction |  |  | 23022898 | 23022898 |  | -23022898
|  |  | Maximum Allowable Construction Cost (MACC) Subtotal | 24325425 | 24325425 | 0 | -24325425
| Construction Contingencies |  |  | 1217429 | 1217429 |  | -1217429
| Non-Taxable Items | [5 empty] | 0
| Sales Tax |  |  | 2829533 | 2829533 |  | -2829533
| GCCM Costs |  |  | 1826451 | 1826451 | 235000 | -1591451
| GCCM Risk Contingency |  |  | 645869 | 645869 |  | -645869
|  |  | Construction Contracts Total | 30844707 | 30844707 | 235000 | -30609707
Other Project Costs
| Equipment |  |  | 1165484 | 1165484 |  | -1165484
| Art Work |  |  | 183341 | 183341 |  | -183341
| Project Management |  |  | 297689 | 297689 | 47105.6 | -250583.4
| Other Costs (describe) |  |  | 641171 | 641171 |  | -641171 | permit & connect fees
|  |  | Other Project Costs Total | 2287685 | 2287685 | 47105.6 | -2240579.4
| Total Project Costs |  |  | 36851640.228 | 36851640.228 | 2972642.63 | -33878997.598
Additional comments:
C-100's (building and infrastructure) for the 2021-23 budget request total $36,852,000. A transposed entry was made in CBS for $36,582,000.
2021-23 Capital Request assumed Design Bid Build; current draft Predesign recommends GC/CM delivery method
2023-2025- Capital Request was not approved. Building will be designed and then wait for the next biennium
June 2026-initial meeting in October 2024 with WA Arts Commission.
March 2024- Cascadia/Mahlum team proposed to both State and DES to remain GC/CM delivery method, all parties agreed due to complexity.
The RFQ was drafted and posted for contractors to submit SOQs.
June 2024- Currently in process of interviewing contractors to assist with the complexity of the project and involvement in the construction documents.
Contractor to be secured by July 1, 2024.
December 2025-The CC5 project was submitted for review with the supplemental budget. The construction documents are completed and the building permit
with the City of Bothell is pending final review.
June 2026- Additional funding of $5M is allowing us to purchase the approved building permit, early utility and site work.

## Photo Gallery (2)
Photo Gallery
View of Gateway Building from the North along the Promenade
View of Gateway Building from the SW along the Promenade
View of Gateway Building from the SE along Campus Way
Site Plan
Level U1 Plan
Level 1 Plan
Level 2 Plan
Level 3 Plan

## Lists (hidden)
Construction Type | Y/N | PM Admin |  |  | Date | Type of Report
Apartment | Yes | DES | 2003-05 | Design-Bid-Build | Select Date from Dropdown | WASHINGTON STATE MAJOR PROJECT STATUS REPORT
Archive building | No | Agency | 2004 | GCCM | June 2026 | WASHINGTON STATE MAJOR PROJECT FINAL CLOSE-OUT REPORT
Armories |  | Other (explain below) | 2005-07 | Design-Build | July 2026
Art galleries |  |  | 2006 | Other (explain below) | August 2026
Auditorium with stage |  |  | 2007-09 |  | September 2026
Auditorium without stage |  |  | 2008 |  | October 2026
Civil Construction | Estimate at PD to Estimate as Funded Variance |  | 2009-11 |  | November 2026
College classroom facilities | Estimate at PD to Actuals Variance |  | 2010 |  | December 2026
Communications Building | Estimate as Currently Funded to Actuals Variance |  | 2011-13 |  | January 2027
Computer rooms |  |  | 2012 |  | February 2027
Convention facilities |  |  | 2013-15 |  | March 2027
Courthouses |  |  | 2014 |  | April 2027
Day care facilities |  |  | 2015-17 |  | May 2027
Detention/correctional facilities - maximum |  |  | 2016 |  | June 2027
Detention/correctional facilities - min & max |  |  | 2017-19 |  | July 2027
Dining halls/institute |  |  | 2018 |  | August 2027
Dormatories |  |  | 2019-21 |  | September 2027
Emergency generator facilities |  |  | 2020 |  | October 2027
Exposition building |  |  | 2021-23 |  | November 2027
Extended care facilities |  |  | 2022 |  | December 2027
Farm structures |  |  | 2023-25 |  | January 2028
Fire and police stations |  |  | 2024 |  | February 2028
Fish hatcheries |  |  |  |  | March 2028
Greenhouses |  |  |  |  | April 2028
Guard towers |  |  |  |  | May 2028
Gymnasiums
Heating and power plants
Hospitals
Industrial buildings without special facilities
Laboratories (Research)
Laundry and cleaning facilities
Libraries
Medical office and clinics
Mental Institutions
Museums
Neighborhood centers and similar recreation facilities
Nursing homes
Observatories
Office buildings
Parking structures and garages
Printing plants
Prototype facilities
Recreational building
Research Facilities
Residence
Schools (primary and secondary)
Science labs (teaching)
Service garages
Sewer treatment plants
Shop and maintenance facilities
Simple loft-type structures (w/o special equipment)
Special schools for physically disadvantaged
Stadium-grandstand type
Stadiums multi-purpose
Storage-cold
Theaters and similar facilities
Transportation terminals
Veterinary hospitals
Vocational schools
Warehouses
Water treatment plants
Other Sch. A Projects
Other Sch. B Projects
Other Sch. C Projects
Formulas:
Date = TEXT(DATE(YEAR(TODAY()), MONTH(TODAY())+ROWS(M2:[Date])-1, DAY(1)), "MMMM YYYY")