## Major Project Report
OFFICE OF FINANCIAL MANAGEMENT
2025-27 Biennium
WASHINGTON STATE MAJOR PROJECT STATUS REPORT
June 2026
| Agency | Bellingham Technical College
| Project Name | Campus Center Emergency
| OFM Project Number(s) | 40000916
Contact Information
| Name | Dave Jungkuntz
| Phone Number | 360-752-8355
| Email | djungkuntz@btc.edu
Project Information
| Project Description: (Include a brief summary of the project and the programs it supports.) | A major structural failure on a 3-story truss was discovered in Fall 2022. Emergency repairs followed and additional structural investigations found more design and construction issues related to both gravity load and seismic integrity. Building occupants were relocated to other areas on campus until construction is completed. The 70,000 square foot building houses campus Library & e-Learning, Associated Student Body space, Campus Tutoring, Trio-support, Computer Networking program, Business Computing program, Culinary Program, & Campus Store. Major project was approved by Legislature in Spring 2024. Building has been unoccupied since Summer 2023.
| Project Status: (Include scope or budget changes, phase updates, identified project delivery issues, discussion of critical path for construction and any potential for project cost overruns or claims.) | Since the December 2025 status update: From January 2026 through May 2026, Contractor work continued on finishes and project punch list items throughout the building and around the exterior of building. Substantial completion of project was achieved in May 2026. BTC Facilities and Moving teams continued the fixture resets and user re-occupancy throughout the building. Phased occupancy-step 2 for classrooms and the majority of the building was being used during Winter Quarter 2026. Third floor uses of Library, Associated Student Body space, and Tutoring were completed throughout Winter Quarter and over Spring Break (March/April 2026). Temporary portable buildings were removed from Campus as of May 1st. Settlemyer Hall meeting space within Campus Center was re-occupied in May and BTC Campus Store is planned for relocation back into Campus Center by July 2026. BTC Arts Committee & WA Arts have selected an Artist for the Public Art. Final project budget and schedule are under review.
Funding
All State & Local Sources, Project Transfers and Amounts
|  | Expenditures |  | Current Plan
| Phase & Fund Type | Prior Expended | 2025-27 Expended | 2025-27 Remaining | 2027-29 Plan | Future Plan | TOTAL | Notes
| Predesign | 0 | 0 | 0 | 0 | 0 | 0
| 057 - State Bldgs. Const Acct | [5 empty] | 0
| XXX - Other State Funding | [5 empty] | 0
| Local Funds | [5 empty] | 0
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| Design | 0 | 0 | 0 | 0 | 0 | 0
| 057 - State Bldgs. Const Acct | [5 empty] | 0
| XXX - Other State Funding | [5 empty] | 0
| Local Funds | [5 empty] | 0
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| Construction | 13169694.95 | 8964734.3 | 1643570.34 | 0 | 0 | 23777999.59
| 057 - State Bldg. Const Acct | 7972927 | 6236627.55 | 174445.04 |  |  | 14383999.59 | D25-R709 & R722
| 057 - State Bldg. Const Acct | 500000 |  |  |  |  | 500000 | D09-R551
| 057 - State Bldg. Const Acct | 229000 |  |  |  |  | 229000 | D07-R609
| 057 - State Bldg. Const Acct | 70000 |  |  |  |  | 70000 | D13-R611
| 057 - State Bldg. Const Acct | 1231000 |  |  |  |  | 1231000 | D15-R615
| 057 - State Bldg. Const Acct | 1164000 |  |  |  |  | 1164000 | D17-R616
| 060 - Other State Funding | 2002767.95 | 2728106.75 | 269125.3 |  |  | 5000000 | D24-R676
| 147 - Local Funds | 0 | 0 | 1200000 |  |  | 1200000 | R10-R601
0
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| TOTALS | 13169694.95 | 8964734.3 | 1643570.34 | 0 | 0 | 23777999.59
Details
| Construction Type | College classroom facilities |  | Project Administered By |  | DES
| % of Bldgs. Area that is being remodeled | 100% |  | Art Requirement Applies |  | Yes
| Procurement Method | GCCM |  | Higher Ed Institution |  | Yes
Statistics
| Complete the table below with information from the cost estimate submitted with the predesign study, the cost estimate of the project as funded and the actual cost data to date or at completion. Explain any variances in the Notes column or below. |  |  | Estimate at Approved Predesign | Estimate of the Project as Currently Funded | Actuals to Date | Estimate as Currently Funded to Actuals Variance | Notes
| Gross Sq Ft (GSF) |  |  |  | 68093 | 68093 | 0
| Usable Sq Ft (USF) |  |  |  | 63258 | 63258 | 0
| Space Efficiency (USF/GSF %): |  |  |  | 92.9% | 92.9% | 0%
| Site Work SF: | [5 empty] | 0
| Demolition SF (provide building names in comments): | [5 empty] | 0
| MACC/Bid Award COST/GSF |  |  |  | 175.4272 | 258.5603 | 83.133
| Construction Subtotal COST/GSF (Includes change orders) |  |  |  | 276.9618 | 294.1694 | 17.2077
Milestone Dates
Predesign Complete
| Start Design |  |  |  | 2023-03-01 | 2023-03-01 | 0 mo.
| Bid Due Date |  |  |  | 2024-06-01 | 2024-06-01 | 0 mo.
| Notice to Proceed |  |  |  | 2024-07-01 | 2024-07-01 | 0 mo.
| Substantial Completion |  |  |  | 2026-06-01 | 2026-05-21
Final Acceptance/Project Close-out Date
Project Costs
| Complete the table below with information from the cost estimate submitted with the predesign study, the cost estimate of the project as funded and the actual cost data to date or at completion. Explain any variances in the Notes column or below. |  |  | Cost Estimate at Approved Predesign | Cost Estimate of the Project as Currently Funded | Actual Costs to Date | Estimate as Currently Funded to Actuals Variance | Notes
Acquisition
|  |  | Acquisition Costs Total |  |  |  | 0
Consultant Services
| Pre-Schematic Design Services |  |  |  | 15030 | 6500 | -8530 | 23-077: A&E | AHBL
| AE Basic Service Fee - Construction Documents |  |  |  | 1249317 | 567440.96 | -681876.04 | 24-049: A&E | Coffman (50%); KPFF (100%); Zervas (50%)
| Extra Services - Pre-Bid |  |  |  | 712505 | 328803.65 | -383701.35 | 3rd Party Testing | RMA-GeoTest (100%)
| AE Basic Service Fee - Bid/Construction/Closeout |  |  |  | 475028.9066 | 512956.72 | 37927.8134 | 24-049: A&E | Coffman (50%); Zervas (50%)
| Other Services - Post Bid |  |  |  | 226309.0934 | 25380.5 | -200928.5934 |  | Commissioning; 3rd party Audit-Ankura (100%)
| Design Services Contingency |  |  |  | 139109 |  | -139109
|  |  | Consultant Services Total | 0 | 2817299 | 1441081.83 | -1376217.17
Construction
| Site Work | [5 empty] | 0
| Related Project Costs | [5 empty] | 0
| Facility Construction |  |  |  | 11945366 | 17606144.45 | 5660778.45 | 23-077; 24-049: E & H | Exxel & Dawson - Emergency & H Contracts
|  |  | Maximum Allowable Construction Cost (MACC) Subtotal | 0 | 11945366 | 17606144.45 | 5660778.45
| Construction Contingencies |  |  |  | 2389074 |  | -2389074
| Non-Taxable Items | [5 empty] | 0
| Sales Tax |  |  |  | 1525373 | 1722401.46 | 197028.46 | 24-049: E | Exxel & Dawson - Emergency & H Contracts
| GCCM Costs |  |  |  | 2402075 | 702334 | -1699741 | 24-049: G | Dawson - G Contract
| GCCM Risk Contingency |  |  |  | 597269 |  | -597269
|  |  | Construction Contracts Total | 0 | 18859157 | 20030879.91 | 1171722.91
Other Project Costs
| Equipment |  |  |  | 883199 | 643830.3 | -239368.7 | Prtbles; Eqmt; | King Cty; PacMobile; Diversification; Technology
| Art Work |  |  |  | 106912 | 18636.8 | -88275.2
| Project Management |  |  |  | 22737 |  | -22737
| Other Costs (describe) | [5 empty] | 0
|  |  | Other Project Costs Total | 0 | 1012848 | 662467.1 | -350380.9
| Total Project Costs |  |  | 0 | 22689304 | 22134428.84 | -554875.16
Additional comments:
Wa Arts - June 2026 - Artist selected and in design

## Lists (hidden)
Construction Type | Y/N | PM Admin |  |  | Date | Type of Report
Apartment | Yes | DES | 2003-05 | Design-Bid-Build | Select Date from Dropdown | WASHINGTON STATE MAJOR PROJECT STATUS REPORT
Archive building | No | Agency | 2004 | GCCM | August 2026 | WASHINGTON STATE MAJOR PROJECT FINAL CLOSE-OUT REPORT
Armories |  | Other (explain below) | 2005-07 | Design-Build | September 2026
Art galleries |  |  | 2006 | Other (explain below) | October 2026
Auditorium with stage |  |  | 2007-09 |  | November 2026
Auditorium without stage |  |  | 2008 |  | December 2026
Civil Construction | Estimate at PD to Estimate as Funded Variance |  | 2009-11 |  | January 2027
College classroom facilities | Estimate at PD to Actuals Variance |  | 2010 |  | February 2027
Communications Building | Estimate as Currently Funded to Actuals Variance |  | 2011-13 |  | March 2027
Computer rooms |  |  | 2012 |  | April 2027
Convention facilities |  |  | 2013-15 |  | May 2027
Courthouses |  |  | 2014 |  | June 2027
Day care facilities |  |  | 2015-17 |  | July 2027
Detention/correctional facilities - maximum |  |  | 2016 |  | August 2027
Detention/correctional facilities - min & max |  |  | 2017-19 |  | September 2027
Dining halls/institute |  |  | 2018 |  | October 2027
Dormatories |  |  | 2019-21 |  | November 2027
Emergency generator facilities |  |  | 2020 |  | December 2027
Exposition building |  |  | 2021-23 |  | January 2028
Extended care facilities |  |  | 2022 |  | February 2028
Farm structures |  |  | 2023-25 |  | March 2028
Fire and police stations |  |  | 2024 |  | April 2028
Fish hatcheries |  |  |  |  | May 2028
Greenhouses |  |  |  |  | June 2028
Guard towers |  |  |  |  | July 2028
Gymnasiums
Heating and power plants
Hospitals
Industrial buildings without special facilities
Laboratories (Research)
Laundry and cleaning facilities
Libraries
Medical office and clinics
Mental Institutions
Museums
Neighborhood centers and similar recreation facilities
Nursing homes
Observatories
Office buildings
Parking structures and garages
Printing plants
Prototype facilities
Recreational building
Research Facilities
Residence
Schools (primary and secondary)
Science labs (teaching)
Service garages
Sewer treatment plants
Shop and maintenance facilities
Simple loft-type structures (w/o special equipment)
Special schools for physically disadvantaged
Stadium-grandstand type
Stadiums multi-purpose
Storage-cold
Theaters and similar facilities
Transportation terminals
Veterinary hospitals
Vocational schools
Warehouses
Water treatment plants
Other Sch. A Projects
Other Sch. B Projects
Other Sch. C Projects
Formulas:
Date = TEXT(DATE(YEAR(TODAY()), MONTH(TODAY())+ROWS(M2:[Date])-1, DAY(1)), "MMMM YYYY")