## Major Project Report
OFFICE OF FINANCIAL MANAGEMENT
2025-27 Biennium
WASHINGTON STATE MAJOR PROJECT STATUS REPORT
December 2025
| Agency | 699
| Project Name | Seattle Central EcoDistrict Decarbonization
| OFM Project Number(s) | 40001348
Contact Information
| Name | La-Keisha Harrell
| Phone Number | 206-934-6375
| Email | La-Keisha.Harrell@seattlecolleges.edu
Project Information
| Project Description: (Include a brief summary of the project and the programs it supports.) | This funding will support Seattle Central College’s implementation of a shovel-ready project to decarbonize its state-owned district energy system in compliance with the Clean Buildings Performance Standard, Annex W (HB 1390), as well as state and City of Seattle greenhouse gas reduction requirements. The project will replace an aging, unreliable steam system, currently dependent on a sole-source provider with rising costs and high emissions, with an all-electric system using heat pumps and large-scale thermal storage. This system will provide heating, cooling, and hot water to approximately 600,000 square feet of campus facilities, significantly reducing emissions and long-term operating costs while improving safety and reliability. Project completion is anticipated by fall 2029.
| Project Status: (Include scope or budget changes, phase updates, identified project delivery issues, discussion of critical path for construction and any potential for project cost overruns or claims.) | Seattle Central College’s decarbonization project is advancing with refined scope and coordinated use of multiple funding sources, including $11.0 million from the 2026 Supplemental Capital Budget (SSB 6003), $4.0 million from Department of Commerce (SSB 5195), and a $438,154 Commerce grant supporting electrical upgrades and efficiency improvements. The project will replace an aging, high-cost steam system with an all-electric district energy system using heat pumps, thermal storage, and supporting infrastructure, with design progressing and early implementation work underway. Key delivery challenges include maintaining campus operations during phased construction, long lead times for electrical and mechanical equipment, and coordination with utilities for increased electrical capacity. The critical path is driven by electrical infrastructure upgrades, procurement and installation of major equipment, and phased decommissioning of the existing steam system ahead of the planned 2029 completion. While no major scope reductions have occurred, there is moderate risk of cost escalation and potential claims due to market volatility, contractor capacity constraints, and unforeseen conditions associated with retrofitting an active campus. 6-26-2026: Progress continues in defining project scope and financial modeling for the Energy as a Service (EaaS) approach, with ongoing coordination among key stakeholders including the Office of the State Treasurer, SBCTC, DES, AAG/SAG, and Seattle Central College; the $4 million in funding is allocated toward electrical vault upgrades to support the EcoDistrict and is already under contract through the DES Energy Program with construction scheduled for late summer 2026, while additional investments in air handler coil conversions and building automation system modernization are currently concluding the Investment Grade Audit (IGA) phase under the DES Energy Program, with construction anticipated in Q4 2026 and Q1 2027.
Funding
All State & Local Sources, Project Transfers and Amounts
|  | Expenditures |  | Current Plan
| Phase & Fund Type | Prior Expended | 2025-27 Expended | 2025-27 Remaining | 2027-29 Plan | Future Plan | TOTAL | Notes
| Predesign | 0 | 0 | 0 | 0 | 0 | 0
| 057 - State Bldg. Const Acct | [5 empty] | 0
| XXX - Other State Funding | [5 empty] | 0
| Local Funds | [5 empty] | 0
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| Design | 0 | 0 | 0 | 0 | 0 | 0
| 057 - State Bldg. Const Acct | [5 empty] | 0
| XXX - Other State Funding | [5 empty] | 0
| Local Funds | [5 empty] | 0
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| Construction | 0 | 0 | 15483154 | 0 | 0 | 15483154
| 057 - State Bldg. Const Acct | [5 empty] | 0
| 26C - Other State Funding-CCA | 0 | 0 | 11000000 |  |  | 11000000 | Sxxx
| Local Funds - DOC Grant | 0 | 0 | 4000000 |  |  | 4000000 | 145 - S696
| Local Funds - DOC Grant | 0 | 0 | 483154 |  |  | 483154 | 145 - Sxxx
| Other Funds & Transfers - Insert Row Here | [5 empty] | 0
| TOTALS | 0 | 0 | 15483154 | 0 | 0 | 15483154
Details
| Construction Type | College classroom facilities |  | Project Administered By |  | DES
| % of Bldg. Area that is being remodeled |  |  | Art Requirement Applies |  | No
| Procurement Method | GCCM |  | Higher Ed Institution |  | Yes
Statistics
| Complete the table below with information from the cost estimate submitted with the predesign study, the cost estimate of the project as funded and the actual cost data to date or at completion. Explain any variances in the Notes column or below. |  |  | Estimate at Approved Predesign | Estimate of the Project as Currently Funded | Actuals to Date | Estimate as Currently Funded to Actuals Variance | Notes
| Gross Sq Ft (GSF) |  |  | 568158 | 568158 |  | -568158
| Usable Sq Ft (USF) |  |  | 568158 | 568158 |  | -568158
| Space Efficiency (USF/GSF %): |  |  | 100% | 100%
| Site Work SF: | [5 empty] | 0
| Demolition SF (provide building names in comments): |  |  | 0 | 0 |  | 0
| MACC/Bid Award COST/GSF |  |  | 32.0368 | 32.0368
| Construction Subtotal COST/GSF (Includes change orders) |  |  | 45.2232 | 45.2232
Milestone Dates
| Predesign Complete |  |  | 2020-12-01 | 2020-12-01
| Start Design |  |  | 2021-01-01 | 2021-01-01
Bid Due Date
Notice to Proceed
| Substantial Completion |  |  | 2028-07-01 | 2028-07-01
Final Acceptance/Project Close-out Date
Project Costs
| Complete the table below with information from the cost estimate submitted with the predesign study, the cost estimate of the project as funded and the actual cost data to date or at completion. Explain any variances in the Notes column or below. |  |  | Cost Estimate at Approved Predesign | Cost Estimate of the Project as Currently Funded | Actual Costs to Date | Estimate as Currently Funded to Actuals Variance | Notes
Acquisition
|  |  | Acquisition Costs Total |  |  |  | 0
Consultant Services
| Pre-Schematic Design Services |  |  | 1549163 | 1549163 |  | -1549163
| AE Basic Service Fee - Construction Documents | [5 empty] | 0
| Extra Services - Pre-Bid | [5 empty] | 0
| AE Basic Service Fee - Bid/Construction/Closeout | [5 empty] | 0
| Other Services - Post Bid | [5 empty] | 0
| Design Services Contingency | [5 empty] | 0
|  |  | Consultant Services Total | 1549163 | 1549163 | 0 | -1549163
Construction
| Site Work | [5 empty] | 0
| Related Project Costs | [5 empty] | 0
| Facility Construction |  |  | 18201943 | 18201943 |  | -18201943
|  |  | Maximum Allowable Construction Cost (MACC) Subtotal | 18201943 | 18201943 | 0 | -18201943
| Construction Contingencies | [5 empty] | 0
| Non-Taxable Items | [5 empty] | 0
| Sales Tax |  |  | 2409895 | 2409895 |  | -2409895
| GCCM Costs |  |  | 5082066 | 5082066 |  | -5082066
| GCCM Risk Contingency | [5 empty] | 0
|  |  | Construction Contracts Total | 25693904 | 25693904 | 0 | -25693904
Other Project Costs
| Equipment |  |  | 0 |  |  | 0
| Art Work |  |  | 0 |  |  | 0
| Project Management |  |  | 292366 | 292366 |  | -292366
| Other Costs (Hazardous materials abatement) |  |  | 413680 | 413680 |  | -413680
|  |  | Other Project Costs Total | 706046 | 706046 | 0 | -706046
| Total Project Costs |  |  | 27949113 | 27949113 | 0 | -27949113
Additional comments:

## Lists (hidden)
Construction Type | Y/N | PM Admin |  |  | Date | Type of Report
Apartment | Yes | DES | 2003-05 | Design-Bid-Build | Select Date from Dropdown | WASHINGTON STATE MAJOR PROJECT STATUS REPORT
Archive building | No | Agency | 2004 | GCCM | July 2026 | WASHINGTON STATE MAJOR PROJECT FINAL CLOSE-OUT REPORT
Armories |  | Other (explain below) | 2005-07 | Design-Build | August 2026
Art galleries |  |  | 2006 | Other (explain below) | September 2026
Auditorium with stage |  |  | 2007-09 |  | October 2026
Auditorium without stage |  |  | 2008 |  | November 2026
Civil Construction | Estimate at PD to Estimate as Funded Variance |  | 2009-11 |  | December 2026
College classroom facilities | Estimate at PD to Actuals Variance |  | 2010 |  | January 2027
Communications Building | Estimate as Currently Funded to Actuals Variance |  | 2011-13 |  | February 2027
Computer rooms |  |  | 2012 |  | March 2027
Convention facilities |  |  | 2013-15 |  | April 2027
Courthouses |  |  | 2014 |  | May 2027
Day care facilities |  |  | 2015-17 |  | June 2027
Detention/correctional facilities - maximum |  |  | 2016 |  | July 2027
Detention/correctional facilities - min & max |  |  | 2017-19 |  | August 2027
Dining halls/institute |  |  | 2018 |  | September 2027
Dormatories |  |  | 2019-21 |  | October 2027
Emergency generator facilities |  |  | 2020 |  | November 2027
Exposition building |  |  | 2021-23 |  | December 2027
Extended care facilities |  |  | 2022 |  | January 2028
Farm structures |  |  | 2023-25 |  | February 2028
Fire and police stations |  |  | 2024 |  | March 2028
Fish hatcheries |  |  |  |  | April 2028
Greenhouses |  |  |  |  | May 2028
Guard towers |  |  |  |  | June 2028
Gymnasiums
Heating and power plants
Hospitals
Industrial buildings without special facilities
Laboratories (Research)
Laundry and cleaning facilities
Libraries
Medical office and clinics
Mental Institutions
Museums
Neighborhood centers and similar recreation facilities
Nursing homes
Observatories
Office buildings
Parking structures and garages
Printing plants
Prototype facilities
Recreational building
Research Facilities
Residence
Schools (primary and secondary)
Science labs (teaching)
Service garages
Sewer treatment plants
Shop and maintenance facilities
Simple loft-type structures (w/o special equipment)
Special schools for physically disadvantaged
Stadium-grandstand type
Stadiums multi-purpose
Storage-cold
Theaters and similar facilities
Transportation terminals
Veterinary hospitals
Vocational schools
Warehouses
Water treatment plants
Other Sch. A Projects
Other Sch. B Projects
Other Sch. C Projects
Formulas:
Date = TEXT(DATE(YEAR(TODAY()), MONTH(TODAY())+ROWS(M2:[Date])-1, DAY(1)), "MMMM YYYY")