# CTE Dual Credit ctcLink Pilot

## Project and Readiness Elements

## 1. Commitment & Governance

☐ Executive sponsorship secured

☐ Cross-functional team (Admissions, Registration, IT, Instruction)

☐ Commitment to implementation timeline

☐ Agreement to follow statewide processes

☐ Agreement to bring forward questions and concerns in a timely manner

## 2. Staffing

☐ Admissions staff available

☐ Registration staff available

☐ ctcLink/IT support assigned

☐ Dual credit/K-12 liaison assigned

☐ Faculty/program leads engaged

☐ Direct student support

☐ Instruction/course builders

## 3. Application & Enrollment

☐ Plan for student self-enrollment (ctcLink)

☐ Backup process for manual enrollment if needed

☐ Strategy to address shopping cart/enrollment errors

☐ Student instructions and support materials prepared

☐ Outreach and engagement with students and families, communication plan

## 4. Course Build & Academic Decisions

☐ Adherence to business process document

☐ Census date approach defined

☐ Withdrawal & transcript rules clarified

☐ Alignment with articulation agreements confirmed

☐ Student fees and policies

## 5. Student Coding & Program Management

☐ Student group assignment process defined

☐ Plan for manual vs automated coding

☐ Process for multi-program students established

## 6. Grading & Transcript Processes

☐ Grade submission method defined

☐ Policy for minimum grades established

☐ Plan for removing or retaining courses clarified (prior to grade process/posting)

☐ Clear communication with high schools/districts

☐ Alignment with CiHS/Running Start policies considered

## 7. High School Partnerships

☐ Communication plan with districts

☐ Clear training plan for high school staff, ongoing support

☐ Instructor onboarding/training plan

☐ Agreement on grading workflows

☐ Alignment on timelines

## 8. Technical Aspects

☐ OAAP

☐ Student groups

☐ Course attributes

☐ Instructor setup approach decided (POI or other)

☐ Technical assistance via Solar Winds ticketing system

## 9. Data & Reporting

☐ Staff trained in queries/reports

☐ Plan to track students by high school

☐ Data validation/cleanup process established

## 10. Policy Impacts

☐ Academic standing implications

☐ Enrollment restriction policies

☐ Credit portability considerations

Please submit any questions related to this information to Bill Belden at wbelden@sbctc.edu.